## Slide 1
Commissioning Support Lead Provider Framework Agreement
Provisional statement on our approach
This short discussion document aims to:
Provide an update on the purpose of the framework and the timeline for its development
Test NHS England’s offer and overall package of support to CCGs around procurement
Test NHS England’s current thinking around some of the key strategic issues that need to be developed and agreed for the framework strategy, including:
  What do we mean by lead provider?
  What is the scope of the framework and how many lots will there be?
  How many places would there be under each lot?
  How will CCGs gain access to the best in class commissioning support services?
  Who can bid to provide services on the framework and who can use the framework?
  What will suppliers need to demonstrate in order to meet the framework requirements?
  How can we make it as easy as possible for buyers to call down from the framework?
  What are the contractual terms for the framework?
We are looking for feedback on these topics (any comments about our approach, concerns or queries) by close of play 15 October to philip.walker2@nhs.net. Following a discussion at the CCG Commissioning Assembly CS Working Group on 16 October a revised position statement will be circulated ahead of further engagement in November at a series of regional workshops (further information to be circulated).

## Slide 2
Rationale for the framework agreement
Our engagement over the summer indicated that many CCGs (76% of CCG respondents to the survey) supported the development of a lead provider framework
CCGs need simple mechanisms to buy commissioning support - framework agreements can significantly reduce the timescales (typically 2-3 months for call-offs versus 9-12 months for full OJEU procurement) and minimise transaction costs
There is no other comparable framework for end to end commissioning support services.
The framework will give customers assurance that organisations meet high quality criteria and minimum standards so that only the best commissioning support suppliers are accredited
There may be a reduced risk of legal challenge for buyers at further competition stage compared to OJEU because much of the legwork (pre-qualification, testing capacity and capability of suppliers) has been carried out at framework stage
User guides and standard documentation (contract and standard specifications) can be developed for customers to tailor and use, including e-procurement tools
Customers generally require less legal and procurement support when using a framework agreement
Lead provider concept means CCGs have fewer contracts to source and manage

## Slide 3
1. Business need, approval and market analysis
3. Establish framework structure and identify procurement strategy
6. Supplier Notification, publish OJEU, PQQ and evaluate PQQs
7.Issue ITT and evaluate responses
7. Framework Award and Signature
Pre procurement Market Engagement
Sourcing & Contracting
Preparing for Procurement
4. Establishing the requirements and evaluation criteria
5. PQQ requirement and spec
Sept
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sept
Oct
Nov
Dec
Jan
Feb
Mar
2. Ensure all stakeholders are clear on project
2013
2014
2015
Jan 14 – Publish standards and criteria
Nov 13 – 6 regional engagement events to work through standards with CCGs, CSUs and other suppliers
3 Mar 14 – Launch OJEU alongside NHSE Expo
By Nov 14 – all supplier bids evaluated
Framework live early 2015
Jan & Feb – Finalise procurement documentation, PQQ and ITT evaluation strategy and confirm customer evaluation panels
Timeline
Support available to CCGs to support specification development and coordination of tenders
From 2015 - CCGs run mini competitions

## Slide 4
Coordinating CCG tenders centrally (or regionally) supporting aggregation of requirements where appropriate and allowing suppliers to respond with the best and most efficient response.
Identifying practical hands on support for CCGs through ‘Trusted Advisors’ to work through Make Share Buy decisions, develop specifications and undertake mini competitions
Developing a range of model procurement documentation and templates (contract and specifications) that CCGs can use via the framework or independently if choosing to procure through an OJEU process
Establishing a Lead Provider Framework that CCGs can run simple mini competitions from to secure some or all of their commissioning support services
Publishing a set of criteria and standards that CCGs can use to assess the quality of commissioning support services and which can be applied through a Lead Provider Framework to accredit a range of excellent affordable commissioning support suppliers
January 2014
OJEU launched Mar 14
F/W goes live early 15
Autumn 2014
Package in place Autumn 2014
What is NHS England’s procurement offer to CCGs?

## Slide 5
What do we mean by lead provider?
A Lead Provider of commissioning support services is an organisation that:
Is capable of securing all commissioning support services through in-house capability or through sub-contracting or partnership arrangements. It is likely that there will be a minimum threshold of services/capability that Lead Providers will need to be able to demonstrate they carry out themselves in-house so that we can ensure there is resilience and a sound level of knowledge for those core commissioning services that CCGs and other commissioners will need to access.
Actively seeks out and embraces the best services provided by other organisations including voluntary organisations and Small and Medium Enterprises (SMEs), and works in partnership to develop the best in class commissioning support
Evolves with its customers to meet their ongoing needs
The principle of lead provider allows CCGs and other buyers to choose to source some or all of their commissioning support requirements from the framework to meet the different needs of CCGs and other commissioners.

## Slide 6
What is the scope of the framework?
The framework aims to allow CCGs and other buyers to source the entirety of their commissioning support needs, from the more transactional back office support services to local and large scale transformational change projects.
CCGs are currently spending over £550m on commissioning support services from CSUs, which will need to be openly competed before CSUs can move to more autonomous forms. Based on current CCG running costs allowance, we estimate the total potential size of the market is just over £1bn, however, CCGs are able to determine what is the best mixture of in-house, shared and bought in commissioning support.
The next slide illustrates our current thinking around the different lots. We are currently proposing two lots that separate out the clinical support services, which require different governance arrangements and operating structures (for example, significant clinical leadership input), from the integrated end to end package of commissioning support.
Under lot 1 (lead provider) CCGs could choose to source any mixture of services listed in the boxes. We propose that CCGs would be able to choose to go to each lot independently or, where they require the full breadth of services that the framework offers, CCGs could invite the suppliers that sit across both lots to bid for their specification.

## Slide 7
Lot 1 – Lead provider
Comms and PPI
Strategic communications – reputation and media management, FOI, complaints, consultations, local stakeholder management and briefing, digital comms
Patient experience – patient advice and liaison support, experience monitoring
Patient involvement –local patient groups, patient information
Business Intelligence, Data management and information governance
Data safe haven for patient related information – through ASH process or sub-con arrangements
Data management, collection of national data sets, validation and cleansing of data (through arrangement with HSCIC)
Contract and financial activity information – tracking cost and activity, invoice validation
Health needs forecasting – risk stratification, analysis of current pathways
  Business support and transactional services
Financial management and budgeting
Payroll
HR Ad-hoc legal services
Infrastructure services – IT and desktop support
Corporate governance and risk management
  Healthcare procurement and provider management
Market assessment – provider landscape, analysis
Contract requirement, definition and renegotiation
End to end procurement
Provider and contract management
Quality and governance
Outcome based commissioning
  Service specific redesign
Planning, management and implementation of service redesign
Change management project management
Quality and value assessment – assessing value of changes and potential opportunities
Clinical support
Medicines optimisation and prescribing services – horizon scanning for new medicines, developing policies and procedures and supporting primary and secondary care contracts
Management of complex case reviews
Case management
Continuing healthcare and funded nursing care
Safeguarding advice and systems support
Lot 2 – Clinical support
Major service transformation
Supporting clinical leaders to drive transformational change successfully
At scale/major service redesign and transformation
Proposed lot solution

## Slide 8
How many places would there be under each lot?
It is important that we get the right number of suppliers on each lot so that:
Customers are not over-burdened with having to evaluate too many bids but continue to benefit from a choice of excellent suppliers
We ensure an optimal balance between delivering economies of scale whilst ensuring sufficient geographical coverage and diversity for customers
Based on our market intelligence from supplier briefing events undertaken over recent months, and lessons learnt from previous and current frameworks, we are proposing that the lead provider lot comprises between 10-15 places and clinical support lot no more than 10 places.
  How will CCGs gain access to the best in class commissioning support services?
It is important that CCGs and other buyers are able to access the best in class commissioning support which might require lead providers to establish partnership and sub-contracting arrangements with a range of niche and more specialist support organisations. We will be considering how we get the right balance between what suppliers will need to demonstrate at framework stage in terms of their supply chain versus that which they will need to provide at call off stage when CCGs and other customers run their mini competitions.
The important thing is that CCGs have confidence that organisations on the framework can provide the full range of commissioning support services excellently, and that when they are calling off, that organisations are able to pull together the best blend of products and services that meet the specific needs of CCGs and other buyers.

## Slide 9
Who can bid for the framework and who can use it?
All organisations from all sectors who can demonstrate that they meet the requirements for the framework can bid, including suppliers in the NHS, the voluntary and independent sector and the wider public sector, for example Local Authorities. We currently anticipate the framework being open to as broader range of public sector organisations as possible. This will be clarified in the OJEU notice.
What will suppliers need to demonstrate?
An OJEU restricted procedure procurement process will be run which comprises a pre-qualification questionnaire (PQQ) stage where organisations will be tested against their financial standing and capability, and an Invitation to Tender (ITT) stage which will delve into more detail around the organisation’s ability to deliver the services, supply chain and service offer.
We expect the evaluation to focus around two domains (largely at ITT stage though some of the criteria may be applied in PQQ as well):
A set of core organisational criteria which tests areas such as the organisation’s financial strength and sustainability, governance, infrastructure and internal systems, quality assurance processes, leadership and organisational capability, supply chain, innovation and continuous improvement and customer responsiveness and evidence of delivery.
A set of service specific criteria and standards across each of the service categories described in the lotting proposals.
These criteria will be co-developed with CCGs and other stakeholders throughout November at a series of workshops to ensure they reflect customer’s needs. More information on the events will be available shortly.

## Slide 10
What are the contractual terms for the framework?
The duration of the framework will be a maximum of 4 years in accordance with Procurement Legislation.
We are currently considering the appropriate contract term for CCGs and other customers when calling off from the framework, which may vary for some of the service categories. Initial indications suggest that a minimum of 5 year contracts with break clauses would be preferable because they offer better value but we are currently seeking views on this.
We expect to provide guidance around the contractual terms next year.
How can we make it as easy as possible for buyers to call down?
Given the complexity of the services, the need for flexibility and bespoke specifications for customers and the importance of facilitating choice it is unlikely that direct award will be an option in most circumstances, though we are continuing to explore the options in more detail.
We are also looking at whether we can build additional steps into the process that might allow CCGs and other customers to issue their tenders to a smaller number of potential suppliers.
We will also be looking to develop a range of standard procurement documentation, specifications and a standard contract that CCGs will be able to use and tailor to fit their needs.