## Sheet1
Trust | Go live date | Problems reported | Source
Barnsley Hospital Foundation Trust | 2014-09-01 | Not going live until September 2014
Birmingham Women's Foundation Trust | 2010-11-01 | The "early adopter" trust paused its deployment of Lorenzo in 2011 because it is not satisfied with the level of functionality delivered. It has made progress since then. The trust reportedly had its business case to deploy the advanced bed management functionality of Lorenzo approved last July. | http://www.networks.nhs.uk/nhs-networks/north-east-clinical-health-informatics-forum/news/birmingham-womens-refuse-to-sign-off-lorenzo/show_all_similar_networks
Derby Hospitals Foundation Trust | 2014-02-01 | The trust failed to submit waiting times data for May. A paper from Southern Derbyshire Clinical Commissioning Group April board meeting said: “The CCG’s main concern is what clinical impact the issues with Lorenzo implementation have on our patients and again this will be a topic of discussion at the [Lorenzo] programme board.” | HSJ research and http://www.derbyshire.nhs.uk/sdccg/2014-04-25-Board-Pack.pdf
George Eliot Hospital Trust | 2014-06-01 | Not going live until June 2014
Ipswich Hospital Trust | 2014-02-01 | The trust failed to submit waiting times data for May. | HSJ research
Hull and East Yorkshire Hospitals Trust | 2014-09-01 | The trust’s May 2014 risk rating said: “Deployment [of Lorenzo] plan may be unrealistic; Unable to reduce planned activity over go-live period (Sept 2014); Insufficient Health Group capacity to support the project. Insufficient funding provision” | HSJ research and http://www.hey.nhs.uk/Pages/About-Us/docs/meetings/14May/Trust%20Board%20Papers%20May%202014.pdf
Humber Foundation Trust | 2012-05-01 | The trust was forced to halt deployement in April 2014. A board paper said: “The current mental health minimum data set, care programme approach and users support issues need to be resolved before further significant Lorenzo deployments are carried out.” | http://www.humber.nhs.uk/Downloads/Board%20papers/Board%20papers%202013/April%202013/Item%207.3%20Lorenzo%20Board%20Report.pdf
Norfolk and Suffolk Foundation Trust | 2015 | Not going live until 2015
South Warwickshire Foundation Trust | 2014-06-01 | Not going live until June 2014
University Hospitals of Morecombe Bay NHS Foundation Trust | 2010-06-01 | Like other earlier adopter trust, Birmingham Women's Foundation Trust, Morecombe Bay has experienced a lot of difficulties with Lorenzo since 2010 but four years and a considerable amount of funding on, experts say the Morecombe Bay is finally seeing considerably improvements and the signs of a credible system. | HSJ research
Tameside Hospital Trust | 2013-10-01 | The trust failed to submit waiting times data for May. The trust has also given its Lorenzo project the highest risk risk rating possible in its April 2014 risk register. It says: "Continuing implementation of Lorenzo (risks to patient safety quality, information governance and performance trajectories). Whilst Lorenzo related issues relating to appointment letters not being sent out." | HSJ research and http://www.tamesidehospital.nhs.uk/Documents/TrustBoardPapersApril2014.pdf
Walsall Healthcare Trust | 2014-03-01 | The trust failed to submit waiting times data for May. Additionally, a Lorenzo report from the trust’s May 2014 board meeting said: “A number of issues have arisen as Lorenzo moves to business as usual including backlogs, clinic restructuring and un-outcomed outpatient clinic forms; This is having an impact on staff in terms of a sense of frustration particularly in terms of getting a day’s work completed in a day….25 additional staff have been recruited.” | https://www.walsallhealthcare.nhs.uk/Data/Sites/1/documents/board-papers/2014/may/g---enc-5-lorenzo-stabilisation-update-board-report---29-may-2014v2.pdf