## 2011-12
¸ | Red
ü | Amber
û | Green
SHA NAME: London | [25 empty] | û | Milestone not achieved
[26 empty] | ¸ | Milestone not yet due
MILESTONES FOR TRANSFORMATIONAL CHANGE ON QIPP AND REFORM 2011/12 | [25 empty] | ü | Milestone achieved
Monthly Assurance Update
Domains | Sub-domains | Workstreams | Milestones for month (complete/not complete) | [23 empty] | RAG Risk to future delivery | Commentary including description of risk to future delivery
|  |  | 2011-04-01 |  | 2011-05-01 |  | 2011-06-01 |  | 2011-07-01 |  | 2011-08-01 |  | 2011-09-01 |  | 2011-10-01 |  | 2011-11-01 |  | 2011-12-01 |  | 2012-01-01 |  | 2012-02-01 |  | 2012-03-01
QIPP transformational change | Engagement, ownership & governance | Key milestones to be extracted from QIPP plans |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸
|  |  |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸
|  |  |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸
| Programme delivery | Key milestones to be extracted from QIPP plans |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸
|  |  |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸
|  |  |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸
Commissioning Development | Clinical Commissioning Groups | Delegated Responsibilities |  |  | First 2 cluster reviews of delegated responsibility applications, according to locally agreed processes based on London regional guidance. | ü | First SHA assurance of the cluster process for application from pathfinder.Delegation on 5 / 7 carried out for South West London. Future pipeline includes assurance for North West London on 15 / 7 and Outer North East London on 18 / 7. NHS London holds full knowledge of the application pipeline for outstanding clusters. | û | [17 empty] | ¸
|  | Development Support |  |  |  | ¸ | Framework of providers for development support launched. Development support procurement pipeline finalised. This will allow further milestones to be populated. | ü
|  | Authorisation |  |  |  | ¸ |  | ¸
| Commissioning support | Business review stocktake |  |  | All clusters have completed business review stocktake | ü |  | ¸
|  | Diagnostic assessment |  |  | Diagnostic assessment of CSU has commenced in all Clusters | ü | Validation Workshop scompleted in all Clusters | ü
|  | CSU roadmap |  |  |  | ¸ |  | ¸
| Transfer of functions to NHS CB | MILESTONES TO BE DETERMINED FOLLOWING OUTCOME OF LONDON OPERATING MODEL PROPOSAL |  |  |  | ¸ |  | ¸
[6 empty] | ¸ |  | ¸
[6 empty] | ¸ |  | ¸
Development of PCT clusters | Setting up functions of clusters | Risks (at cluster level) that are keeping clusters from fulfilling core statutory functions |  |  |  | ¸ | No (6 Clusters)
|  | Financial information is brought together at a cluster level |  |  |  | ¸ | Yes (6 Clusters) | ü
|  | Clusters failing to fulfil a function due to capacity issues? |  |  |  | ¸ | No (6 Cluster)
|  | Cluster Board meetings inquorate? |  |  |  | ¸ | No (6 Clusters)
| Development activity to be renamed Transfer of Cluster functions | MILESTONES TO BE DETERMINED FOLLOWING OUTCOME OF LONDON OPERATING MODEL PROPOSAL
Relationships with partners during transition | Health and Wellbeing Boards | There is a Health and Wellbeing Board in every local authority area |  |  | 33/33 |  | 32/33
|  | Joint commissioning arrangments are stable or increasing in every local authority area |  |  | 29/33 |  | 33/33
TBD WHEN MORE DETAIL EMERGES FROM DH
| Engagement with Local Authorities | Cluster establishes regular and routine dialogue with LA Health Scrutiny Committee to ensure engagement on emerging service change. |  |  | 33/33 |  | 33/33
|  | There is clearly defined engagement with LA at cluster and borough level (eg MEMORANDUM OF UNDERSTANDING or equaivalent document in place) |  |  | 29/33 (negotiating Memorandum Of Understanding, a partnership agreement with local authority) |  | 33/33 (negotiating Memorandum of Understanding, a partnership agreement with local authority)
TBD WHEN MORE DETAIL EMERGES FROM DH
| Transfer of functions to Local Authorities (excluding public health) | Establsihment of HealthWatch is actively being pursued in every local authority area |  |  | 29/33 (agreeing tansition of advocacy and complaints with local authority) |  | 29/33 (agreeing transition of advocacy and complaints with local authority)
TBD WHEN MORE DETAIL EMERGES FROM DH
TBD WHEN MORE DETAIL EMERGES FROM DH
Public Health to be re-named Relationships with partners during transition | Health and Wellbeing Boards | There is a Health and Wellbeing Board in every local authority area | X/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33
|  | Joint commissioning arrangments are stable or increasing in every local authority area | X/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33
TBD
| Engagement with Local Authorities | Cluster establishes regular and routine dialogue with LA Health Scrutiny Committee to ensure engagement on emerging service change. | X/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33
|  | There is clearly defined engagement with LA at cluster and borough level (eg MOU or equaivalent document in place) | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33
TBD
| Transfer of functions to Local Authorities (excluding public health) | Establsihment of HealthWatch is actively being pursued in every local authority area | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33
|  | Plans in place to transfer functions (other than PH) eg advocacy | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33 |  | x/33
TBD
Provider Development | FT pipeline | Ealing Hospital |  |  | SOC Approval |  |  |  | OBC Approval | [5 empty] | Review of Q2 Finance |  | FBC Approval |  |  |  | Review of Q3 Finance |  |  |  | Merger s.t. FBC approval |  |  | Behind plan. Used up contingency time.
SHA financial challenge and productivity opportunities assessment
Review of Q1 Finance
|  | Imperial College Healthcare |  |  | Appointment of Chief Financial Officer |  | Agreement of 2011/12 financial plan |  | SHA financial challenge and productivity assessment. | [5 empty] | Completion of modelling of strategic development. | [12 empty] | Have not started clinical strategy. Missed first 3 milestones but new CE taking ownership. New DoF appointed.
[9 empty] | Achievement of Q1 CIP. | [5 empty] | Achievement of Q2 CIP. | [5 empty] | Achievement of Q3 CIP.
[9 empty] | Q1 - review finance, quality and performance. | [5 empty] | Q2 - review finance, quality and performance. | [5 empty] | Q3 - review finance, quality and performance.
|  | North West London Hospitals |  |  | SOC Approval |  |  |  | OBC Approval | [5 empty] | Review of Q2 Finance |  | FBC Approval |  |  |  | Review of Q3 Finance |  |  |  | Merger s.t. FBC approval |  |  | Linked to Ealing. Contingency time used up. Emergency care (A&E) performance and financial issues
SHA financial challenge and productivity opportunities assessment
Review of Q1 Finance
|  | West Middlesex University Hospital | [6 empty] | SHA financial challenge and productivity opportunities assessment | [5 empty] | Challenged Trust Board decision on historic deficit - Autumn 2011 |  |  |  | Completion of the Joint Clinical Strategy Review with Imperial Healthcare |  | Q3 review of finance (including achievement and trajectory on CIPs), quality and performance |  | Option 2 – merger with NHS Trust - Procurement of external support to assist with transaction process |  |  |  |  | Revised TFA submitted. If Standalone option evaluation does not prove to be a viable option by Jan 2012, the trust will work on Option 2 - Merger with NHS Trust or Option 3 - Acquisition with FT
[9 empty] | Q1 review of finance (including achievement and trajectory on CIPs), quality and performance | [5 empty] | Q2 review of finance (including achievement and trajectory on CIPs), quality and performance | [5 empty] | Completion of Evaluation of Stand Alone Option and Board approval of the decision
|  | Central London Community Health Services |  |  |  |  | QIPP programme plan approved by Trust Board |  | Estates transfer plan agreed |  |  |  | Clinical management restructure implemented |  | Admin and clerical review implemented |  | Social Care Integration proposal to Trust Board | [7 empty] | First draft IBP and LTFM to NHS London |  |  | Nothing to note except transfer of property milestone not achieved pending DH decision on the transfer of property to aspirant CFTs.
[7 empty] | Funding/access to support for Board development, Organisational diagnostic agreed |  | Alignment between Trust QIPP programme and commissioners’ activity plans |  |  |  | Variations to RIO licenses agreed
[7 empty] | Completion of PCT community property transactions |  | Corporate functions integrated
|  | London Ambulance Service |  |  | Secure full support with the cluster for the financial model and submit to NHSL |  | Submit revised IBP with signed cluster support. | [5 empty] | Formal submission to Secretary of State | [14 empty] | Have signed off financial plans with cluster. SUI re. system being down. Will need new TFA date.
QIPP programme alignment with commissioners’ plans agreed.
Receive confirmation in writing on the level of DH funding in 2011/12 and 2012/13 for the Olympic Games.
Receive confirmation from the DH of future contractual commitment for CBRN funding.
SHA Board-to-Board
|  | West London Mental Health |  |  | - Clarity/ agreement on the future direction of the St Bernard’s |  | Planned date for Broadmoor OBC approval by DH/ treasury (critical path date - DH) (ref 4.2a) |  | London services implementation plan agreed with commissioners (ref 4.1) |  | Final draft IBP and LTFM |  | Historical Due Diligence part one |  | Alignment between Trust QIPP programme and commissioners’ plans |  | Final IBP and LTFM |  | Historical Due Diligence part two | [8 empty] | Issues re capital to watch.
[5 empty] | Forensic OBC agreed with Commissioners (London SCG) |  | Trust plans to submit a planning application in support of the Broadmoor Redevelopment (ref 4.2a) | [5 empty] | North West London Mental Health Strategy agreed |  |  |  | Commissioner convergence letter (NHS NWL)
[5 empty] | Confirmation that plans to transform local services are in line with the New Mental Health Strategy for the sector (NHS NWL) (ref 4.2b) |  | London services clinical model developed (ref 4.1)
Funding for Trust Board Development programme agreed
|  | Barnet & Chase Farm | [6 empty] | SoS decision on BEH clinical strategy | [5 empty] | Completion of option appraisal on organisational form |  |  |  | Decision on CTB Funding |  | Review of Q3 Finance | [6 empty] | Need decision on BEH clinical strategy. SoS has asked IRP for desktop review. Major dependency before trust can decide about organisational future. Missed milestones.
[9 empty] | SHA financial challenge and productivity opportunities assessment | [5 empty] | Review of Q2 Finance |  |  |  | Decision on Transitional funding
Review of Q1 Finance
|  | Great Ormond Street Hospital | [25 empty] | Nothing to note
|  | North Middlesex University Hospital | [6 empty] | SoS decision on BEH clinical strategy | [5 empty] | Completion of option appraisal on organisational form | [5 empty] | Review of Q3 Finance | [6 empty] | Linked to Barnet and Chase Farm. SoS has asked IRP for desktop review. Major dependency before trust can decide about organisational future. Missed milestones.
[9 empty] | SHA financial challenge and productivity opportunities assessment | [5 empty] | Review of Q2 Finance
Review of Q1 Finance
|  | Royal Free Hampstead | Achievement of written commissioner support |  | Stage 2 HDD |  | QIPP programmes in place for 2011/12 and 2012/13. |  | SHA Board-to-Board and CIC |  | Formal submission to Secretary of State | [16 empty] | Board to Board took place on 1st July. Need to resolve CQC issue before coming to DH
Clearance of CQC compliance actions
|  | Royal National Orthopaedic Hospital | [8 empty] | RNOH board agreement on preferred option and approach to future organisational form |  | NHS L CIC consideration of options | [14 empty] | Board exploring options for future organisational shape . Decision by Sept 2011. Need partner. Financial challenge
|  | Whittington Hospital | Community services transfer to Trust and ICO created |  | Third NED appointed |  | All NEDs have undergone induction and orientation to the ICO |  |  |  | Quality and safety dashboard developed |  | Board to discuss recruitment plan for fourth new NED |  | 2012/13 QIPP plan finalised |  |  |  | Agree new ICO payment mechanisms that might be reflected in 2012/13 contract |  | First draft Foundation Trust Integrated Business Plan (IBP) and Long Term Financial Model (LTFM) approved by ICO Trust Board & submitted to NHS London |  |  |  | ICO Historic Due Diligence part one undertaken |  |  | Nothing to note
|  |  | Acute contract signed |  | Haringey children’s services contract signed by Trust and commissioners and services transferred to Trust |  | 2011/12 QIPP plan approved by Trust Board | [5 empty] | FT public consultation begins
|  |  | Newly appointed NEDs commence Trust Board duties |  |  |  | ICO senior management structure revised and new structure in place
ICO service development priorities agreed and transformation work underway
|  | Barnet, Enfield & Haringey MHT |  |  |  |  | NHS NCL completes review of sector commissioning planning assumptions. |  | HDD1 |  |  |  | Alignment of trust CIPs and cluster QIPP requirements. |  |  |  | HDD2 |  |  |  | SHA Board-to-Board |  | Formal submission to Secretary of State
Agreement of cluster Mental Health Strategy.
|  | Barking, Havering & Redbridge Hospitals |  |  |  |  | Agreement reached on BHRUT assuming reasonability for integrated elderly pathway with transfer of staffing and assets during 2011/12 |  | SHA financial challenges and productivity opportunities assessment |  |  |  | Review and refresh of IBP and LTFM following Independent Reconfiguration Panel decision | [5 empty] | Financial return at month 8 on target to meet £28.8m (including IFRS) control total. | [5 empty] | £28.8m deficit control total for 2011/12 projected to be met |  |  | Struggling with finance and performance. Will update after SHA led Board review
[7 empty] | BHRUT achieving 95th percentile standard for all A&E departments- then sustained to year end. | [5 empty] | Review of Q1 and Q2 quality, service and financial performance. Tri-partite agreement to implement plans in light of the above reviews and assessments to meet the agreed FT trajectory timeline | [11 empty] | No CQC conditions
[7 empty] | BHRUT achieving all Cancer targets- then sustained to year end | [5 empty] | Financial return at month 5 on target to meet £28.8m (including IFRS) control total
[7 empty] | Agreement of volumes and value of transfer of elective work from Whipps Cross and tertiary providers during 2011/12 and 2012/13 | [5 empty] | Application to CQC for removal of conditions
Financial return at month 2 on target against plan YTD and year-end projection in control
|  | Whipps Cross University Hospital | [6 empty] | OBC finalised and taken to Trust board |  | NHS L CIC consideration of OBC |  |  |  | CCP response expected |  | FBC finalised and taken to Trust board |  |  |  | Q3 routine performance and finance review |  |  |  | Trust dissolved; BELH established (subject to approvals) |  |  | OBC/FBC progressing; risk regarding implementation and integration. Cash funding issue needs resolution. Need to monitor in year performance. Overall high CIP targets and merger savings.
[9 empty] | Q1 routine performance and finance review | [5 empty] | Q2 routine performance and finance review |  | NHS L CIC consideration of FBC
|  | Barts & The London | [6 empty] | OBC finalised and taken to Trust board |  | NHS L CIC consideration of OBC |  |  |  | CCP response expected |  | FBC finalised and taken to Trust board |  |  |  | Q3 routine performance and finance review |  |  |  | Trust dissolved; BELH established (subject to approvals) |  |  | OBC/FBC progressing; risk regarding implementation and integration. Cash funding issue needs resolution. Need to monitor in year performance. Overall high CIP targets and merger savings.
[9 empty] | Q1 routine performance and finance review | [5 empty] | Q2 routine performance and finance review |  | NHS L CIC consideration of FBC
|  | Newham University Hospital | [6 empty] | OBC finalised and taken to Trust board |  | NHS L CIC consideration of OBC |  |  |  | CCP response expected |  | FBC finalised and taken to Trust board |  |  |  | Q3 routine performance and finance review |  |  |  | Trust dissolved; BELH established (subject to approvals) |  |  | OBC/FBC progressing; risk regarding implementation and integration. Cash funding issue needs resolution. Need to monitor in year performance. Overall high CIP targets and merger savings.
[9 empty] | Q1 routine performance and finance review | [5 empty] | Q2 routine performance and finance review |  | NHS L CIC consideration of FBC
|  | Lewisham Hospital |  |  | DH guidance - ownership of community estate as integrated trust. Safety and quality assurance gateway review - desktop |  | Board to review analysis of public consultation and revise constitution as appropriate. Delivery of HDD1 Action Plan in readiness for HDD2 process. LTFM re-modelled to include QIPP and agreed SLA. CIPs developed with sufficient granularity. Final NED appointment made to complete NED team. |  | SHA financial challenge and productivity opportunities assessment |  |  |  | Referral To Treatment (RTT) on track against 2011/12 plan |  | Commence work on IBP and LTFM | [5 empty] | Review of Q3 quality, service and financial performance(including achievement and trajectory of CIPs) | [6 empty] | Will reprovide the TFA. Do not sign off current TFA. Will need to adjust timeline.
|  | South London Healthcare |  |  | External Strategic Review report to Trust Board (Impacts the content of the IBP and LTFM) | [7 empty] | QMS Campus Review Strategic Outline Case (impacts IBP/LTFM) | [14 empty] | Underlying performance issues. Have not yet signed off operating plan with SHA. Reviewing end Q1.
[5 empty] | QMS Campus Review (Impacts the content of the IBP and LTFM) | [7 empty] | Review of Q1 and Q2 quality, service and financial performance (including achievement and trajectory of CIPs). Tripartite agreement to implementation plan in light of the 3 strategic reviews and assessments above to achieve the agreed FT trajectory timeline.
[5 empty] | Commence Phase 2 CTB Process | [9 empty] | Formal submission to Secretary of State
|  | Croydon Healthcare | [25 empty] | CQC compliance issue re Maternity services, action plan in place. New Director of Nursing, Interviewing new MD.
|  | Epsom & St Helier University Hospital | [6 empty] | Q1 routine performance and finance review |  |  |  | OBC finalised and taken to Trust board |  | NHS L CIC consideration of OBC | [5 empty] | FBC finalised and taken to Trust board |  | NHS L CIC consideration of FBC |  |  |  |  | Progressing to plan (against the context of challenged financial position). Need decision on preferred bidders by Oct 2011
[15 empty] | Q2 routine performance and finance review | [5 empty] | Q3 routine performance and finance review
|  | Kingston Hospital |  |  | 1st draft IBP and LTFM to SHA including remodelled downside |  |  |  | Historical Due Diligence stage one | [5 empty] | Commissioner letter of support |  | 2nd formal draft IBP and LTFM to SHA |  |  |  | Board to Board with SHA |  |  |  | SHA Board Approval |  |  | Good quality IBP/LTFM. HDD1 commences July 2011.
[9 empty] | Consultation ends | [7 empty] | Historical Due Diligence stage two |  |  |  | Final IBP/ LTFM to SHA |  |  |  | Deliver productivity programme
Deliver waiting list improvement project action plan
Deliver urgent care service project plan
|  | St Georges Healthcare | [6 empty] | SHA financial challenge and productivity opportunities assessment. |  |  |  | Submit detailed bid for merging with St Helier Hospital |  | Board decision on FT timeline. | [12 empty] | Interim CE Appointing new Chair by Sept 2011. Current Perf. Issues
[9 empty] | Q1 - Review of finance, quality & performance. | [5 empty] | Q2 - Review of finance, quality & performance | [5 empty] | Q3 - Review of finance, quality & performance
|  | Hounslow & Richmond Community Healthcare | Established as NHS Trust |  |  |  | Updated quality and performance report to Board |  | Alignment between projected community QIPP initiatives / savings and commissioners’ activity plans |  |  |  | Clinical strategy to Board |  | Estates strategy to Board | [12 empty] | Nothing to note.
[7 empty] | Report to Board on performance metrics, including DH TCS indicators and Monitor proposals | [5 empty] | Completion of PCT community property transactions (title and circular flow of funds)
Funding / access to support for Board development, Organisational diagnostic - NHSL
|  | South West London & St Georges |  |  | End of public consultation |  | Induction of new Trust chair completed |  | CQC organisational risk profile |  | IBP updated following HDD1 |  | Independent accountant review, HDD2 |  | SHA Board to Board |  | SHA and Trust Board approval of FT application |  | Site rationalisation – Consultation plans for Sutton and Barnes to be agreed with stakeholders. Consultation expected to be concluded by Autumn 2012 (post authorisation) |  |  |  | QIPP for 2012/13 and onwards to be agreed with commissioners. This may require support from the Cluster and SHA. |  |  |  |  | Chief Executive on 3/12 sick leave and a new chair. HDD1 commenced June 2011.
[5 empty] | IBP 3rd submission |  | Independent accountant review, HDD1 |  | SHA executive interview, Board observation | [5 empty] | QIPP intentions for 2012/13 advised by commissioners |  |  |  | FT submission to Department of Health
Commissioner support of Trust FT application
Corporate Development | Handover of SHA functions, where not covered above
TBC following further guidance on implications of SHA clustering
Closedown of SHA functions, where relevant
TBC following further guidance on implications of SHA clustering
Note on H101: Author: NB Performance are not yet recoding data for 95th percentile so this relates to the 95% target

## 2012-13
¸ | Red
ü | Amber
û | Green
SHA NAME | [24 empty] | û | Milestone not achieved
[25 empty] | ¸ | Milestone not yet due
MILESTONES FOR TRANSFORMATIONAL CHANGE ON QIPP AND REFORM 2012/13 | [24 empty] | ü | Milestone achieved
Monthly Assurance Update
Domains | Sub-domains | Milestones for month (complete/not complete) | [23 empty] | RAG Risk to future delivery | Commentary including description of risk to future delivery
|  | 2012-04-01 |  | 2012-05-01 |  | 2012-06-01 |  | 2012-07-01 |  | 2012-08-01 |  | 2012-09-01 |  | 2012-10-01 |  | 2012-11-01 |  | 2012-12-01 |  | 2013-01-01 |  | 2013-02-01 |  | 2013-03-01
QIPP transformational change |  |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ | Amber
|  |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸
|  |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸
|  |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ | Red
|  |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸
|  |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸ |  | ¸
Commissioning Development | GP Consortia
Commissioning support
Transfer of functions to NHS CB
Development of PCT clusters | Setting up functions of clusters
Development activity
Public Health | Health and Wellbeing Boards
Engagement with Local Authorities
Transfer of functions to Local Authorities
Provider Development | FT pipeline
TCS development
NTDA
Corporate Development | Handover of SHA functions, where not covered above
Closedown of SHA functions, where relevant