## SummaryReformMilestonesM&E WM
NHS Midlands and East: - West Midlands Area PCT cluster RAG ratings for progress against QIPP initiatives - 2012-13
For SHA USE Summary commentry on PCT clusters Summary commentry for SHA cluster
Report for the month of: | 2012-09-30 |  |  | PCT Clusters
Domains | Totals for RAG Rating |  |  | Arden | Birmingham and Solihull | Black Country | Staffordshire | West Mercia | PCT cluster 6 | PCT cluster 7
| Red | Amber | Green
Initiative 1 | 2 | 2 | 1 | Red | Red | Amber | Green | Amber | RAG Rating | RAG Rating
| Narrative |  |  |  | Most milestones on track however two projects delayed and actiity against plan indicates higher than predicted activity hence red status | Validated M4 elective activity data shows that actual activity levels are just 1.3% more than the same period last year with some high levels of over-performance seen in M4. I/P admissions are significantly below 11/12 levels however daycases remain above 11/12 levels. This over-performance is due in part to a double-counting issue at Walsall (which has been notified to and agreed with the Provider) and a delay in implementing some QIPP schemes at Wolverhampton which are specifically aimed at reducing elective activity. Both of these issues are on the scrutiny agenda and will be closely managed over the coming months. In addition, Wolverhampton are also counting specialised service activity in the 'actual' trajectory. | The reconfiguration of Mental Health services across Staffordshire continues to make good progress with all individual milestones on target to deliver | Activity: M5 Unify Figure show a Cluster-wide 3.2% overperformance against the planned figures which represents a consistent shift across the cluster. M5 SUS showed a 5.8% YTD decrease over last year compared to a planned decrease of 6%. FIMS: M5 FIMS shows a 7% over achievement of savings. Progress: In general, progress is good against the milestones. Rating: Rating to be retained at Amber. Though the finance data shows an over achiechievement of savings at this stage, this may be optimistic. The activity data is solidly amber; we are expecting an increase in demand due to the over performance in GP referrals and 1st outpatients attendendances in parts of the cluster. | 0 | 0
Initiative 2 | 3 | 2 | 0 | Red | Amber | Amber | Red | Red | RAG Rating | RAG Rating
| Narrative |  |  | GP Referral Management (electives) impact variable across cluster: Exceeding planned reductions within SWCCG; below plan for CRCCG and WNCCG. IMSK/Physio CRCCG - not delivering planned activity reductions. The Cluster has requested action plans from CCGS to address this. | Some slipage against milestones and some over perfromance against plan within the amber SHA threshold hence amber rating | M4 activity over-performance is showing YTD activity over-performing by 4.9% against plan which places the domain in the amber rating. This over-perfomance may be largely attributed to Sandwell and Wolves where performance is 6-6.5% above plan. This is in part due to QIPP initiative funding being tied up in the 2% NR pool which has now been approved for use and should start to show improvement against this over-performance during the second half of the year. Additionally, Wolverhampton continues to include specialised services activity in their actual activity and have also seen an increase in A&E activity which may be impacting through more emergency admissions. | Although the majority of QIPP schemes are on track for delivery the activity levels are above plan across the main acute providers (exl. MSFT) in Staffordshire. Commissioners continue to review the situation with the main providers | Activity: M5 Unify Figure show a Cluster-wide 9.2% overperformance against the planned figures which represents a consistent shift across the cluster. M5 SUS showed a 10% YTD increase over last year against a planned 2% increase. FIMS: M5 FIMS shows a 25% underachievement of against the savings profile. Progress: In general, progress is good against the declared milestones and a number of alternative schemes have been implemented to address the significant overperformance. Rating: Rating to be retained at Red. The activity measures continue to overheat andthis is reflected in the financial data. The over performance shows no pattern across the cluster and each CCG has implemented local initiatives to bring down the level of over performance. Though these will not have an impact on activity until October/November the Cluster and CCGs are focusing on the progress of these new schemes in the short term. | 0 | 0
Initiative 3 | 4 | 0 | 1 | Red | Red | Green | Red | Red | RAG Rating | RAG Rating
| Narrative |  |  | 0 | Slipage on some key projects particularly in planned care plus oer performance against activity plan hence red rating | Direct year on year YTD comparision shows that GP and other referral activity are higher than at the same point in 11/12 however, despite the increases in referral activity, Month 4 validated data shows that there is a marginal increase in actual 1st O/P activity at the same point in 2011/12 and that collectively the cluster is only 1.7% over plan against its 2012/13 trajectory. The QIPP outpatient profile is broadly on target to deliver financially. Referral patterns are being analysed and results of this analysis will be shared in due course. | Progress on the shift of activity from acute to community settings is good. Due to the high levels of referrals into the system this domain is rated as Red. Commissioners continue to review and explore redesign options | Activity: M5 Unify data show a Cluster-wide 5% overperformance against the planned level. M5 SUS showed a 4.1% YTD increase over last year. FIMS: M5 FIMS data shows a 6% over achievement of savings against the profile. Progress: In general, progress against declared milestones is good. Rating: Rating to be retained as RED. Activity shows sustained over performance, and though the Financial returns show signs of optimism the individual schemes are heavily weighted to the later part of the year, and must therefore be considered a risk. | 0 | 0
Initiative 4 | 2 | 0 | 3 | Red | Green | Green | Red | Green | RAG Rating | RAG Rating
| Narrative |  |  | Sommunity Early Supported Discharge schemes, admission avoidance schemes are not delivering anticipated ativity and finance reductions RAID schemes due to implementation from October 2012. | QIPP savings forcast reported to the Board indicate savings are on track to be delivered | Milestones and financial performance for this domain are both on track. On-going issues at Penn Hospital in Wolves have been downgraded in terms of their severity rating and is no longer of 'major concern' to the CQC. QIPP schemes are realising fewer out of area placements for MH/LD. | Due to a high level referrals into the system this domain is rated as Red | Activity: No activity data is available. FIMS: The M5 FIMS shows a 35% over achievement of savings against profile. Progress: In general, progress is good against the declared milestones Rating: Rating to be retained at GREEN. | 0 | 0
Initiative 5 | 1 | 3 | 1 | Red | Amber | Green | Amber | Amber | RAG Rating | RAG Rating
| Narrative |  |  | Continuing Care savings below planned levels. CHC Trusted Assessment in line with planned savings. Cluster has requested action plans from CCGS to address this. | Mental Health programme remains on track to deliver panned savings at month 5 | No significant issues with this work stream to date. Financial performance is slightly behind YTD trajectory however FOT is for the plan to be achieved. All milestones have been met. | Based on the progress on the delivery of QIPP projects and the unavailability of prescribing data this domain has been rated as amber. Further interal review planned in July 2012 | Activity: No activity data is available. FIMS: The M5 FIMS shows a 3.5% under achievement of savings against profile. Progress: In general, progress is good against the milestones. Rating: Rating to be retained at AMBER. The general progress against milestones is good and and small shortfall in savings is not causing concern at this stage. | 0 | 0
Initiative 6 | 1 | 1 | 2 | Red | Amber | Green | Green | RAG Rating | RAG Rating | RAG Rating
| Narrative |  |  | Mental Health Out of Area Scheme current below planned savings levels. Cluster has requested action plans from CCGS to address this. | Programe of work remains on plan year to date to deliver planned savings but some project slipage though it is anticipated that this will be accounted for by other projets over delivering | No significant issues with this work stream to date although the list size validation project will take longer to deliver than initially anticipated. Financial performance is slightly behind YTD trajectory however FOT is on plan. All milestones have been met. | Based on the progress on the delivery of QIPP projects and the unavailability of prescribing data this domain has been rated as amber. Further interal review planned in July 2012 | 0 | 0 | 0
Initiative 7 | 1 | 2 | 0 | Amber | Red | Amber | RAG Rating | RAG Rating | RAG Rating | RAG Rating
| Narrative |  |  | GP Prescribing schemes delivering above planned level for Warwickshire North and South Warwickshire CCGS. However, they are below plan for Coventry & Rugby CCG. Cluster has requested action plans from CCGS to address this. | Management cost savings delayed untill MARS role out is implimeted | All bar one of the milestones have been achieved and while the cluster is slightly behind in its YTD savings position, it fully expects to deliver the year-end running cost target. The risk to ICT requirements of receiver organisations remains and this may impact on some receiver organisations ability to operate effectively on a day to day basis. Mitigating actions continue to be tested by both applicable clusters. | 0 | 0 | 0 | 0
PCT narrative on cluster progress |  |  |  | The Cluster rates itself as Red. Analysis of UNIFY Data shows over activity across the basket of indicators relating to QIPP and there is also underperformance 'year-to-date' against QIPP Savings Plan. The Cluster has requested action plans from CCG's to address this and this will be discussed at the monthly 'Checkpoint' meetings and Cluster Sub-committees. | No narrative provided | The Cluster has rated itself as Amber. Month 4 activity data has not shown an improvement against plan but it has not shown a significant deterioration to push the cluster into red-rated territory. There is some slippage in milestone delivery which is not expected to impact on overall QIPP delivery targets for 12/13. The financial FOT position remains for full achievement against plan despite slight slippage seen in the year to date performance and an issue with the modernisation programme in Wolverhampton which is being mitigated against through alternative schemes. | The Staffordshire Cluster is making good progress in the delivery of the planned service redesign and the transfer of activity to community settings. Although progress is good, activity and increased demand in the system continues to be over plan. The Staffordshire Cluster will be undertaking confirm and challenge meetings with providers and CCGs to fully understand the risks and thier mitigatings actions (incl. additional QIPPs) to address this by year end. Analysis is currently taking place to understand the discrepancies between SUS and Unify information systems | The cluster continues with significant areas of over performance, particularly for non-elective admissions. The root causes vary throughout the cluster and the CCGs have implemented a number of additional schemes to specifically address these issues within the local footprint. Though the effect will not be seen in the performance data for some months the cluster are focusing effort on assessing the planning and implementation of the new schemes.
Overall RAG rating for PCT cluster QIPP programme PCT cluster to complete |  |  |  | Red | Red | Amber | Red | Red | RAG Rating | RAG Rating
SHA narrative on PCT RAG rating |  |  |  | The SHA agrees with the Cluster RAG or RED based on the continuing overperformance of activity against plan and the impact of this on the QIPP savings. The Cluster has undertaken confirm and challenge meetings with the CCG's in relation to the under performance of QIPP delivery. Further updates are to be discussed at the next Finanance & Performance sub comommittee and the Board | The Cluster is making progress with service transformation and is making progress on further financial savings. Activity is beginning to show some over performance in NEL and referrals | The Cluster is maintaining the current level of financial savings although activity is over performing. The Cluster is confident that over delivery in other QIPP schemes will address the impact of activity levels and therefore the cluster is rated amber | Activity remains a concern within the Cluster, the PCT is seeing some slippage in QIPP delivery but is able to address this with non recurrent funding. The Cluster continues to work with CCG's to identify revised QIPP intiatives. | Further work is being undertaken by the CCG's to identify schemes to address shortfall in delivery of activity changes and QIPP savings. The Cluster continues to hold the CCG to account for QIPP delivery
Quarterly assurance of QIPP delivery |  |  |  | Comments
i. Confirmation that all elements of assurance as set out in the planning round have been transposed into the QIPP milestone tracker
ii. Quarterly assessment of progress in delivering transactional change completed. Supported by evidence of impact demonstrated through finance, activity, performance and workforce change whilst maintaining or improving quality
iii. Quarterly assessment of progress in delivering transformational change completed. Supported by evidence that in-year milestones which are required ensure delivery in 2013-14 and 2014-15, (e.g. those associated with building the case for reconfiguration or invest to save schemes), are on track.
Q1 - Quarterly Overall RAG rating for QIPP programme To be completed by SHA cluster |  |  |  | Red | Amber | Amber | Red | Red | RAG Rating | RAG Rating
Q2 - Quarterly Overall RAG rating for QIPP programme To be completed by SHA cluster |  |  |  | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating
Q3- Quarterly Overall RAG rating for QIPP programme To be completed by SHA cluster |  |  |  | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating
Q4- Quarterly Overall RAG rating for QIPP programme To be completed by SHA cluster |  |  |  | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating

## Arden_QIPPmilestones
2012- 2013 Milestone Tracker |  |  | Acute Contracts (Outpatients) subcode 130 | [32 empty] | Acute Contracts (Elective) subcode 100 | [32 empty] | Acute Contracts (Other) Subcode 150 | [32 empty] | Acute Contracts (Non Elective) subcode 120 | [32 empty] | Continuing Healthcare subcode 210 | [32 empty] | Mental Health & Learning Disabilities Contracts subcode 160 | [32 empty] | Primary care Prescribing subcode 220
QIPP Overview and finances
SHA cluster: |  | NHS Midlands and East
PCT Cluster : |  | Arden
Number of CCGs in cluster: |  | 3
Report for the month of:
QIPP Challenge (£000s)
FIMS Plan: Savings for CSR period (£000s) |  | 270549.1084
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s) |  | 99841
Yr 2 Plan FIMS savings for 2012-13 (£000s) |  | 70289
Yr 3 Plan FIMS savings for 2013-14 (£000s) |  | 57090
Yr 4 Plan FIMS savings for 2014-15 (£000s) |  | 43330
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 270550
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be <50% of years 2-4 (Cells C11:C13)) |  | 106346
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale | PCT cluster |  | Title | Acute Contracts (Outpatients) subcode 130 | [28 empty] | Scale | PCT cluster |  | Title | Acute Contracts (Elective) subcode 100 | [28 empty] | Scale | PCT cluster |  | Title | Acute Contracts (Other) Subcode 150 | [28 empty] | Scale | PCT cluster |  | Title | Acute Contracts (Non Elective) subcode 120 | [28 empty] | Scale | PCT cluster |  | Title | Continuing Healthcare subcode 210 | [28 empty] | Scale | PCT cluster |  | Title | Mental Health & Learning Disabilities Contracts subcode 160 | [28 empty] | Scale | PCT cluster |  | Title | Primary care Prescribing subcode 220
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 | 8764 | FIMS savings 2013-14 | 6972 | FIMS savings 2014-15 | 0 | Total for CSR period | 15736 | [25 empty] | FIMS savings 2012-13 | 6569 | FIMS savings 2013-14 | 3766 | FIMS savings 2014-15 | 0 | Total for CSR period | 10335 | [25 empty] | FIMS savings 2012-13 | 9114 | FIMS savings 2013-14 | 2380 | FIMS savings 2014-15 | 0 | Total for CSR period | 11494 | [25 empty] | FIMS savings 2012-13 | 19310 | FIMS savings 2013-14 | 17331 | FIMS savings 2014-15 | 0 | Total for CSR period | 36641 | [25 empty] | FIMS savings 2012-13 | 3438 | FIMS savings 2013-14 | 5371 | FIMS savings 2014-15 | 0 | Total for CSR period | 8809 | [25 empty] | FIMS savings 2012-13 | 7333 | FIMS savings 2013-14 | 3058 | FIMS savings 2014-15 | 0 | Total for CSR period | 10391 | [25 empty] | FIMS savings 2012-13 | 6470 | FIMS savings 2013-14 | 6470 | FIMS savings 2014-15 | 0 | Total for CSR period | 12940
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 13-14 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative. |  |  |  |  | No practices with greater than 30 QOF markers in the bottom quartile of Cluster performance, leading to reduction in new referrals to acute and a reduction in acute outpatient follow up | New community dermatology service for North Warwickshire commissioned | New T&O pathways added to Coventry RSS process | New Orthotics commissioning policy for South Warwickshire goes live | Risk stratified follow up agreed for cancer patients | New pulmonary rehab service for North Warwickshire commissioned | Decommission BUPA healthdialog risk strat tool. Roll out new risk strat tool to primary care | New outpatient pathways implemented at UHCW. | Cluster-wide Primary Care benchmarking of practices performance against QOF clinical markers undertaken. | Evaluate potential connections between combined risk stratification tool and primary care urgent care dashboard | Cluster-wide Primary Care benchmarking of practices performance against QOF clinical markers undertaken. | [22 empty] | Hold growth in activity levels at no more than 2% from 12/13 outturn | Revised LPP Policy implemented | Enhanced Recovery implemented and in contractual agreements with providers for the 4 nationally identified specialties. | Revised LPP Policy implemented | [29 empty] | Reduce use and cost of specific HCD to bring Cluster spend in line with NICE indicative usage and hold growth for 12/13 at maximum 5% | Blueteq system implemented for all specialities in all providers | Homecare roll-out programme under way | Implement plan for reviewing existing patients with long term conditions and discontinuing drugs if patients do not meet criteria | Blueteq system implemented for all specialities in all providers | Homecare roll-out programme under way | All patients receiving HCDs in line with NICE/ local criteria | [26 empty] | Reduce A&E attendance levels to 2008/09 baseline, reduce acute admissions in this age group by 17% against 11/12 outturn, reduce LOS for adults over 75 and thus reduce acute bed capacity requirement by 50 beds | Introduce IV therapy capability in Warwickshire community services and cellulitis pathway goes live in North Warwickshire | CERT Warwickshire: Reduce admissions by 2 per day, increase discharges | Introduce telehealth care monitoring as part of Warwickshire nursing home support and range of services to support hospital discharge | Introduce IV therapy capability to Warwickshire nursing home support | Increase number of discharges to reablement homecare by 2 per day | 6 new ambulatory care pathways will be in place | 50 -75 patients supported using simple Telehealth | Annual survey of tele care completed providing an indication of the number of service users with long term conditions who use assistive technology including simple tele-health | Phase 1 of crisis resolution services implemented for organic MH issues (dementia) in Warwickshire | Audit numbers on Palliative Register and compare with deaths in community statistics | All new patient and client contacts will have a lifestyle risk management discussion as part of their initial assessment, signposting appropriate people to other services | Phase 2 of crisis resolution in Warwickshire implemented | Unplanned admissions for >75yr age group reduced by 23% from 2011/12 baseline | [19 empty] | Sustain review level between 450 and 500 per year | Expected reviews completed for 5 months - 235. | Expected reviews completed for 9 months - 423 | [30 empty] | Reduce out of area placements by 5 patients on 2012/13 outturn | Complete phase 1 capital works. Decant & refurbishment to increase current bed provision. Repatriation commences | Target 12 patients repatriated | Target further 11 patients supported. Complete phase 2 capital works. Repatriation programme for phase 2 commences | Recommissioning of LD day and respite services complete | Refurbishment of low secure facilities complete. Enhanced capacity available to further reduce out of area placements | [27 empty] | Reduce primary care prescribing spend by 4.9% (assuming 4% growth) | Review elements reporting below expectations and remedial action taken as agreed with the CCGs. | Red and amber elements below expectations reviewed comprehensively and remedial action taken. | Review elements reporting below expectations and remedial action taken as agreed with the CCGs. | Review elements reporting below expectations and remedial action taken as agreed with the CCGs. | Red and amber elements below expectations reviewed comprehensively and remedial action taken. | Review elements reporting below expectations and remedial action taken as agreed with the CCGs. | Review elements reporting below expectations and remedial action taken as agreed with the CCGs. | Red and amber elements below expectations reviewed comprehensively and remedial action taken. | Review elements reporting below expectations and remedial action taken as agreed with the CCGs.
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones |  |  | All first outpatient attendances (consultant-led) in general and acute specialties | [32 empty] | Total number of FFCEs in the period | [65 empty] | Number of G&A non-elective FFCEs in the period
(UNIFY indicators) Anticipated performance at period end |  |  | 239800 | 244593 | 249485 | [30 empty] | 111256 | 113480 | 115750 | [63 empty] | 76884 | 78424 | 79992
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s))) |  |  | Number of 1st outpatient attendances (consultant-led) following GP referral in general and acute specialties | [32 empty] | Number of elective FFCEs - ordinary admissions
(Other KPIs) Anticipated performance at period end |  |  | 130356 | 132964 | 135623 | [30 empty] | 23558 | 24028 | 24509
QIPP Initiative Reporting
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2013-08-31 | 2013-06-30 | 2014-03-31 | [20 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2013-03-31 | 2013-04-30 | [27 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-09-30 | 2012-12-31 | 2013-04-30 | 2013-09-30 | 2013-12-31 | 2014-04-30 | [24 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2015-03-31 | [17 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-11-30 | 2013-01-31 | [28 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-07-31 | 2012-10-31 | 2013-01-31 | 2014-03-31 | 2014-04-30 | [25 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-05-31 | 2013-09-30 | 2013-12-31 | 2014-05-31 | 2014-09-30 | 2014-12-31
Progress reporting against milestones and Initiative 1 |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall progress of the initiative along with risks, issues and mitigating actions where relevant ▪ Quarterly (required) Report overall progress of the initiative and supporting workstreams including an assessment of progress against performance indicators and finance. Include narrative on risks, issues and mitigating actions where relevant |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (optional) to report overall progress of the initiative along with risks, issues and mitigating actions ▪ Quarterly (required) and should give narrative on overall progress of the initiative and supporting workstreams. It should include an assessment of progress against performance indicators, and finance along with risks and mitigating actions |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (optional) to report overall progress of the initiative along with risks, issues and mitigating actions ▪ Quarterly (required) and should give narrative on overall progress of the initiative and supporting workstreams. It should include an assessment of progress against performance indicators, and finance along with risks and mitigating actions |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (optional) to report overall progress of the initiative along with risks, issues and mitigating actions ▪ Quarterly (required) and should give narrative on overall progress of the initiative and supporting workstreams. It should include an assessment of progress against performance indicators, and finance along with risks and mitigating actions |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (optional) to report overall progress of the initiative along with risks, issues and mitigating actions ▪ Quarterly (required) and should give narrative on overall progress of the initiative and supporting workstreams. It should include an assessment of progress against performance indicators, and finance along with risks and mitigating actions |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (optional) to report overall progress of the initiative along with risks, issues and mitigating actions ▪ Quarterly (required) and should give narrative on overall progress of the initiative and supporting workstreams. It should include an assessment of progress against performance indicators, and finance along with risks and mitigating actions |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (optional) to report overall progress of the initiative along with risks, issues and mitigating actions ▪ Quarterly (required) and should give narrative on overall progress of the initiative and supporting workstreams. It should include an assessment of progress against performance indicators, and finance along with risks and mitigating actions |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber
[8 empty] | Policy awaiting sign off and agreement with CCG and Provider. |  | Implementation delayed - will be implemented from October 2012. | The tool is ready for practices that are able to implement. Access training to be completed across CCGs - delayed until October 2012. | [23 empty] | GP Referral Management (Outpatients) delivering required reductions in Coventry but not in Warwickshire. Outpatient Follow Ups rate reductions in WNCCG and Coventry but not at planned levels. Outpatient Follow Ups are above plan for Rugby and South Warwickshire. Cluster has requested action plans from CCGS to address this. | [32 empty] | GP Referral Management (electives) impact variable across cluster: Exceeding planned reductions within SWCCG; below plan for CRCCG and WNCCG. IMSK/Physio CRCCG - not delivering planned activity reductions. The Cluster has requested action plans from CCGS to address this. |  |  |  |  | 3.1: Blueteq will be implemented in several specialities but not all as per the agreed roll out programme. | [26 empty] | Community admission avoidance scheme for care home largely on tracker for delivery. Other Community avoidance schemes are not deliverng planned levels. High Cost Drugs schemes are only delivering in South Warwickshire due to issues embedding the schemes in both George Eliot and University Hospitals Coventry & Warwickshire. Cluster has requested action plans from CCGS to address this. | [6 empty] | Introduce Telehealth as part of care home support: This has slipped until January 2013. An initial meeting has taken place and action plans are being developed with each CCG. Telephealth to support early hospital discharge: An initial meeting took place during the second week of September 2012. The next meeting with SWFT will take place in October to demonstrate Florence to the respiratory and health failure teams, which will include consultant attendance and roll out is expected to happen quickly. Rollout plan to be agreed. | [26 empty] | Sommunity Early Supported Discharge schemes, admission avoidance schemes are not delivering anticipated ativity and finance reductions RAID schemes due to implementation from October 2012. | [32 empty] | Continuing Care savings below planned levels. CHC Trusted Assessment in line with planned savings. Cluster has requested action plans from CCGS to address this. |  |  |  | The building works have slipped and are still red; however, the mitigating action is that there has been additional performance in repatriation not dependent on the refurbishment so the financial trajectory is on target. | [28 empty] | Mental Health Out of Area Scheme current below planned savings levels. Cluster has requested action plans from CCGS to address this. |  |  |  |  | Milestone is on track for completion although this will not be accounted for until November 2012 when September's prescribing data is received. | [27 empty] | GP Prescribing schemes delivering above planned level for Warwickshire North and South Warwickshire CCGS. However, they are below plan for Coventry & Rugby CCG. Cluster has requested action plans from CCGS to address this.
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Delayed - amber | Completed | Delayed - amber | Delayed - amber | In progress | In progress | In progress | In progress | [20 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | In progress | In progress | [27 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Delayed - amber | In progress | In progress | In progress | In progress | In progress | [24 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Delayed - amber | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | [17 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | In progress | In progress | [28 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Delayed - amber | In progress | In progress | In progress | In progress | [25 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | In progress | In progress | In progress | In progress | In progress | In progress | In progress
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-09-30 | 2012-10-31 | 2013-08-31 | 2013-06-30 | 2014-03-31 | [19 empty] | 2.0333 |  |  |  | 2012-06-30 | 2013-03-31 | 2013-04-30 | [26 empty] | 2.0333 |  |  |  | 2012-12-31 | 2012-12-31 | 2013-04-30 | 2013-09-30 | 2013-12-31 | 2014-04-30 | [23 empty] | 3.0667 |  |  |  | 2012-04-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2015-03-31 | [16 empty] | 0 |  |  |  | 2012-11-30 | 2013-01-31 | [27 empty] | 0 |  |  |  | 2012-07-31 | 2012-10-31 | 2013-01-31 | 2014-03-31 | 2014-04-30 | [24 empty] | 0 |  |  |  | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-05-31 | 2013-09-30 | 2013-12-31 | 2014-05-31 | 2014-09-30 | 2014-12-31 | [20 empty] | 0
| Month 2 | 2012-05-31 |  |  | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-09-30 | 2012-10-31 | 2013-08-31 | 2013-06-30 | 2014-03-31 | [19 empty] | 2.0333 |  |  | 2015-03-31 | 2012-06-30 | 2013-03-31 | 2013-04-30 | [26 empty] | 2.0333 |  |  | 2015-03-31 | 2012-12-31 | 2012-12-31 | 2013-04-30 | 2013-09-30 | 2013-12-31 | 2014-04-30 | [23 empty] | 3.0667 |  |  | 2015-03-31 | 2012-04-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2015-03-31 | [16 empty] | 0 |  |  | 2015-03-31 | 2012-11-30 | 2013-01-31 | [27 empty] | 0 |  |  | 2015-03-31 | 2012-07-31 | 2012-10-31 | 2013-01-31 | 2014-03-31 | 2014-04-30 | [24 empty] | 0 |  |  | 2015-03-31 | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-05-31 | 2013-09-30 | 2013-12-31 | 2014-05-31 | 2014-09-30 | 2014-12-31 | [20 empty] | 0
| Month 3 | 2012-06-30 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-07-31 | 2012-07-31 | 2012-10-31 | 2012-09-30 | 2012-10-31 | 2013-08-31 | 2013-06-30 | 2014-03-31 | [19 empty] | 3.0667 |  |  |  | 2012-07-31 | 2013-03-31 | 2013-04-30 | [26 empty] | 3.0667 |  |  |  | 2012-12-31 | 2012-12-31 | 2013-04-30 | 2013-09-30 | 2013-12-31 | 2014-04-30 | [23 empty] | 3.0667 |  |  |  | 2012-04-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2015-03-31 | [16 empty] | 0 |  |  |  | 2012-11-30 | 2013-01-31 | [27 empty] | 0 |  |  |  | 2012-07-31 | 2012-10-31 | 2013-01-31 | 2014-03-31 | 2014-04-30 | [24 empty] | 0 |  |  |  | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-05-31 | 2013-09-30 | 2013-12-31 | 2014-05-31 | 2014-09-30 | 2014-12-31 | [20 empty] | 0
| Month 4 | 2012-07-31 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-08-31 | 2012-07-31 | 2012-10-31 | 2012-09-30 | 2012-10-31 | 2013-08-31 | 2013-06-30 | 2014-03-31 | [19 empty] | 4.1 |  |  |  | 2012-07-31 | 2013-03-31 | 2013-04-30 | [26 empty] | 3.0667 |  |  |  | 2012-12-31 | 2012-12-31 | 2013-04-30 | 2013-09-30 | 2013-12-31 | 2014-04-30 | [23 empty] | 3.0667 |  |  |  | 2012-04-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2015-03-31 | [16 empty] | 0 |  |  |  | 2012-11-30 | 2013-01-31 | [27 empty] | 0 |  |  |  | 2012-09-30 | 2012-10-31 | 2013-01-31 | 2014-03-31 | 2014-04-30 | [24 empty] | 2.0333 |  |  |  | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-05-31 | 2013-09-30 | 2013-12-31 | 2014-05-31 | 2014-09-30 | 2014-12-31 | [20 empty] | 0
| Month 5 | 2012-08-31 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-09-30 | 2012-07-31 | 2012-10-31 | 2012-09-30 | 2012-10-31 | 2013-08-31 | 2013-06-30 | 2014-03-31 | [19 empty] | 5.1 |  |  |  | 2012-07-31 | 2013-03-31 | 2013-04-30 | [26 empty] | 3.0667 |  |  |  | 2012-12-31 | 2012-12-31 | 2013-04-30 | 2013-09-30 | 2013-12-31 | 2014-04-30 | [23 empty] | 3.0667 |  |  |  | 2012-04-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-01-31 | 2014-03-31 | 2014-04-30 | 2015-03-31 | [16 empty] | -5 |  |  |  | 2012-11-30 | 2013-01-31 | [27 empty] | 0 |  |  |  | 2012-09-30 | 2012-10-31 | 2013-01-31 | 2014-03-31 | 2014-04-30 | [24 empty] | 2.0333 |  |  |  | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-09-30 | 2013-12-31 | 2014-05-31 | 2014-09-30 | 2014-12-31 | [20 empty] | -2.0333
| Month 6 | 2012-09-30 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-10-31 | 2012-07-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2013-08-31 | 2013-06-30 | 2014-03-31 | [19 empty] | 7.1667 |  |  |  | 2012-06-30 | 2013-03-31 | 2013-04-30 | [26 empty] | 2.0333 |  |  |  | 2012-12-31 | 2012-12-31 | 2013-04-30 | 2013-09-30 | 2013-12-31 | 2014-04-30 | [23 empty] | 3.0667 |  |  |  | 2012-04-30 | 2012-06-30 | 2013-01-31 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-01-31 | 2014-03-31 | 2014-04-30 | 2015-03-31 | [16 empty] | -1.9333 |  |  |  | 2012-11-30 | 2013-01-31 | [27 empty] | 0 |  |  |  | 2013-01-31 | 2012-10-31 | 2013-01-31 | 2014-03-31 | 2014-08-31 | [24 empty] | 10.2333 |  |  |  | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-09-30 | 2013-12-31 | 2014-05-31 | 2014-09-30 | 2014-12-31 | [20 empty] | -2.0333
| Month 7 | 2012-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone | [5 empty] | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | [23 empty] | 3 | 3 | 3 | [30 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [27 empty] | 3 | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [20 empty] | 3 | 3 | [31 empty] | 3 | 3 | 3 | 3 | 3 | [28 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Number of CCGs who have completed this milestone | [5 empty] | 1 | 1 |  | 3 | [29 empty] | 3 | [65 empty] | 2012-04-30: 3
Percentage of PCTs completing this milestone |  |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 0% | 0% | 0% | #DIV/0! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## B'ham&Solihull_QIPPmilestones
2012- 2013 Milestone Tracker | [35 empty] | Acute Contracts elective | [32 empty] | Acute Contracts outpatients | [32 empty] | Primary Care Prescribing | [32 empty] | Mental Health and Learning disabilities | [32 empty] | Continuing Health Care | [32 empty] | PCT Efficiencies
QIPP Overview and finances
SHA cluster: |  | NHS Midlands and East
PCT Cluster : |  | Birmingham and Solihull
Number of CCGs in cluster: |  | 5
Report for the month of:
QIPP Challenge (£000s) |  | 454893
FIMS Plan: Savings for CSR period (£000s) |  | 487388
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s) |  | 142414
Yr 2 Plan FIMS savings for 2012-13 (£000s) |  | 128846
Yr 3 Plan FIMS savings for 2013-14 (£000s) |  | 122874
Yr 4 Plan FIMS savings for 2014-15 (£000s) |  | 93254
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 487388
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be <50% of years 2-4 (Cells C11:C13)) |  | 196692
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale | PCT cluster |  | Title | Acute Contracts non elective | [28 empty] | Scale | PCT cluster |  | Title | Acute Contracts elective | [28 empty] | Scale | PCT cluster |  | Title | Acute Contracts outpatients | [28 empty] | Scale | PCT cluster |  | Title | Primary Care Prescribing | [28 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) | 10271 | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 | 22824 | FIMS savings 2013-14 | 21766 | FIMS savings 2014-15 | 16519 | Total for CSR period | 61109 | [25 empty] | FIMS savings 2012-13 | 9090 | FIMS savings 2013-14 | 8668 | FIMS savings 2014-15 | 6579 | Total for CSR period | 24337 | [25 empty] | FIMS savings 2012-13 | 13162 | FIMS savings 2013-14 | 12552 | FIMS savings 2014-15 | 9526 | Total for CSR period | 35240 | [25 empty] | FIMS savings 2012-13 | 3730 | FIMS savings 2013-14 | 3557 | FIMS savings 2014-15 | 2700 | Total for CSR period | 9987 | [25 empty] | FIMS savings 2012-13 | 9406 | FIMS savings 2013-14 | 8973 | FIMS savings 2014-15 | 6810 | Total for CSR period | 25189 | [25 empty] | FIMS savings 2012-13 | 6500 | FIMS savings 2013-14 | 6199 | FIMS savings 2014-15 | 4704 | Total for CSR period | 17403 | [25 empty] | FIMS savings 2012-13 | 8750 | FIMS savings 2013-14 | 8344 | FIMS savings 2014-15 | 6333 | Total for CSR period | 23427
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative. |  |  |  |  | 2% reduction on11/12 out turn activity across non elective | BCHC community specification Agreed and in contract | NHS pathways implemented which will support 111 mobilisation | Expansion of telemonitoring devices across the cluster achieved | Medical Assessment Centres Go live across the cluster | 111 provider identified and confirmed | Redesign of respiratory pathway completed | Multidisciplinary teams supporting community management of LTC operational across the cluster. Active case management of EoL Clients goes live. | Revised service model for care homes operating in 50% of care homes across cluster. | Urgent care Strategy implementation mobilised | Supported discharge in place across cluster reducing excess bed days | Community and Primary Care service for diabetes, respiratory and heart failure in place across the cluster | 111 goes live | Evaluation of self management models completed | Revised service model for care homes operating across the Cluster | Services prioritised to be concentrated into centres of excellence | Work programme to implement outcome of walk in centre consultation goes live | Frail elderly 13/14 service redesign goes live | Phase 2 service transformation and revised pathways for end of life goes live | Alcohol frequent flyer impact evaluation completed | CQUINS to support delivery of QIPP identified | Urgent Care strategy implementation review completed | Phase 3 Urgent Care programme agreed | Targeted reduction in repeat hospital visits for diabetes, respiratory and of heart failure achieved | Walk in centre work programme completed | Frail elderly 14/15 service redesign goes live | Phase 3 service transformation and revised pathways for end of life goes live | CQUINS to support delivery of QIPP identified | Urgent Care strategy refresh completed | Phase 3 Urgent Care programme agreed | Manual estimate for non elective admissions in the period Apr-Aug2012 = 65,933. UNIFY plan for the period was 56,695. Actual performance is 16.29% above plan therefore is RAG rated as RED. Note: Due to the recent confirmation by HoEFT of the scale of the errors in their data systems this period's actuals have been manually estimated pending the formal correction of their data errors. |  |  | 0.5% reduction of Elective based on 11/12 out turn activity | Managed Risk 1% v 2% growth agreed with HEFT Elective risk share agreed with SWB | Maternity capacity review launched | Phase 3 roll out of PLCV across the Cluster - goes live | Nurse led clinics negotiated and agreed for designated specialities with acute trusts at 50% tariff | Extension of emergency pathway across HEFT and SWBHT GOES LIVE | Priority pathway redesign identified | Enhanced speciality pathways for HRG NZ goes live Mainstream CAMHS Home Treatment Pilot | Revised Maternity capacity model goes live | Managed risk share agreement with provider | Expansion of nurse led clinics agreed | Priority redesign pathways go live | Extension of emergency pathway across HEFT and SWBHT evaluated | Revised Maternity capacity model evaluated | Refreshed CQUINS to support delivery of QIPP identified | Managed risk share agreement with provider | Expansion of nurse led clinics agreed | Surgical never events eliminated | Refreshed priority redesign pathways work streams operational | Priority pathways implemented | Priority pathways implemented | Refreshed CQUINS to support delivery of QIPP identified | [8 empty] | Actual electives in the period Apr-Aug 2012 = 66,668. UNIFY plan for the period is 63,892. Actual performance is 4.34% over plan therefore RAG rating is AMBER. |  |  | Reduction in GP new referrals by 2.5% based on 11/12 activity outturn and 2% reduction in day cases based on 11/12 | AQP for defined services launched | Revised new to review ratios agreed with trusts for over performing specialities | Demand management operational across the cluster to reduce GP new referrals | AQP completed for defined services and contracts awarded | Advice and guidance operational at UHB, HEFT and SWB | Access to Direct Diagnostic for target specialities operational across the cluster | AQP for defined services mobilised and implemented across the cluster | Programme to move agreed minor procedures from day to outpatient procedures at BCH goes live Establish and go live with childrens demand management scheme. | Phase 2 AQP services identified | Refreshed CQUINs to support delivery of QIPP identified | Enhanced recovery for the 4 clinical specialties identified by the national programme implemented by all providers. | Demand management priorities and targets agreed with CCGs and providers | Revised new to review ratios agreed with trusts for over performing specialities | Refresh demand management operational across the cluster to reduce GP new referrals in target specialities | AQP service contracts evaluated | Advice and guidance expansion operational at UHB, HEFT and SWB | Expanded access to Direct Diagnostic for target specialities operational across the cluster | Evaluate move of minor procedures from day to outpatient procedures at BCH Evaluate Childrens and maternity demand management programme | Refreshed CQUINs to support delivery of QIPP identified | Evaluation of enhanced recovery for the 4 clinical specialties identified by the national programme. | Demand management priorities and targets agreed with CCGs and providers | Revised new to review ratios agreed with trusts for over performing specialities | Refresh demand management operational across the cluster to reduce GP new referrals in target specialities | Advice and guidance expansion operational at UHB, HEFT and SWB | Expanded access to Direct Diagnostic for target specialities operational across the cluster | Expansion of move of minor procedures from day to outpatient procedures across providers - No longer seperate initiative part of Children and Maternity demand management scheme Refresh children and maternity deman management programme - Identify referal out lyers and high demand high cost specialities. | Refreshed CQUINs to support delivery of QIPP identified |  |  | Actual GP referrals in the period Apr-Aug 2012 = 123,340. UNIFY plan for the period is 109,424. Actual performance is 12.72% over plan therefore performance is RAG rated as RED. However, this is an improvement on the Apr-Jul position of 15.56% above plan. |  |  | 4.6% reduction in spend based on 2012/13 baseline spend for primary care | Contract agreement with BCH re: cost and quality of unlicensed specials achieved | Quality Dash Board agreed to monitor primary care | Implementation of discretionary payments policy commenced. | Cost improvement areas of prescribing agreed with GP practices and improvement objectives agreed | Benefit realisation and financial savings on discretionary payments goes live | Better procurement and use of dressings pilot completed and decision regarding further roll out or not Contract agreed with BCHC for a Bham dietician service to review oral nutrician (SIP feeds) with target (30) GP practices. | PMS farer funding contract adjustments goes live. | Quality Improvement Targets agreed and benchmarking undertaken | Commissioning for quality requirements evaluated. | Cost improvement areas for prescribing identified | Quality Dash Board agreed to monitor primary care | Commissioning for quality requirements defined in all trust policies | Cost improvement areas of prescribing agreed with GP practices and improvement objectives agreed | Quarterly monitoring of primary care Established and initial base line identified | Quality refinements achieved and new areas identified | Quality Improvement Targets agreed and benchmarking undertaken | Cost improvement areas for prescribing achieved and new cost improvements identified | Cost improvement areas for prescribing identified | Quality Dash Board agreed to monitor primary care | Commissioning for quality requirements defined in all trust policies | Cost improvement areas of prescribing agreed with GP practices and improvement objectives agreed | Cost improvements areas of prescribing agreed with GP practices and improvement objectives agreed | Quarterly monitoring of primary care against refreshed base lines agreed | Quality refinements achieved and new areas identified | Quality Improvement Targets agreed and benchmarking undertaken | Cost improvement areas for prescribing achieved and new cost improvements identified | [6 empty] | 17.2%reduction in spend based on 12/13 base line spend for mental health and Learning disabilities | Day Service operational / go live | Redesign plan for LD care pathway included in SDIP with BCHC | Transformation Work programme for Dementia agreed | BSMHFT Redesign implementation goes live | Learning and work service go live | STR service decommissioned | Phase one Service Transformation and revised pathways for Dementia agreed | RAID initial benefit realization review completed | LD redesign and new specification agreed | Scope and prioritise phase 2Transformation work programme for Dementia |  | RAID - Associate Commissioner FD’s (UHB/HEFT/City) agree with Cluster FD to extend pilot period to allow full evaluation. | RAID - Full evaluation documents available – decision taken by Associate Commissioners re: future commissioning of RAID. | RAID established as sustainable model commissioned directly by Acute Providers (UHB/HEFT/City). | LD revised specification evaluated | Raid model embedded in Acute Contracts | Phase 2 specification redesign for LD agreed based on evaluation. | Phase 2 specification redesign for LD evaluated. | [14 empty] | 12.3% reduction in spend against 12/13 base line for CHC | Decision to tender or renegotiate nursing home beds contracts made | Review of equipment completed | Extended assessment service goes live | Fast track end of life CHC goes live. Sign off and go liveof the Joint Operational Policy | High cost packages reduced in line with bench marking | Nursing Home Beds revised contract / tender operational | Revised arrangements for Equipment implemented across the cluster | Identify 2nd phase high cost packages not representing VFM and initiate negotiation to reduce costs in line with benchmark costs | nursing home beds contracts reviewed and VFM assessment completed | Extended assessment service Evaluation and impact completed | Joint Operational Policy CHC evaluation and impact assessment completed | Phase 2 high cost packages reduced in line with bench marking | Revised arrangements for Equipment implemented across the cluster | Identify all high cost packages not representing VFM and initiate negotiation to reduce costs in line with benchmark costs | Nursing home beds contracts reviewed and VFM assessment completed | Extended assessment service Evaluation and impact completed | Joint Operational Policy CHC evaluation and impact assessment completed | Nursing home beds contracts reviewed to assure continued VFM | All high cost packages not representing VFM Identified and initiate negotiation to reduce costs in line with benchmark costs | High cost packages reduced in line with bench marking | Revised arrangements for Equipment evaluated | [11 empty] | 13.5% reduction in spend based on 12/13 base line spend | FYE of 11/12 disinvestment goes live | Work programme to reduce management costs and running costs agreed | Management and running cost reduction programme goes line | Manage and running cost reductions benefit realisation commenced | Management reduction evaluated | Next phase management reductions agreed | Next phase Management and running cost reduction programme goes line | Next phase Manage and running cost reductions benefit realisation commenced | Next Phase Management reduction evaluated
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones |  |  | Number of G&A non-elective FFCEs in the period | [32 empty] | Total number of FFCEs in the period | [32 empty] | All first outpatient attendances (consultant-led) in general and acute specialties
(UNIFY indicators) Anticipated performance at period end |  |  | 134701 | 133354 | 132007 | [30 empty] | 160225 | 158997 | 157581 | [30 empty] | 415509 | 411400 | 408662
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s))) | [35 empty] | Number of elective FFCEs - ordinary admissions | [32 empty] | Number of 1st outpatient attendances (consultant-led) following GP referral in general and acute specialties
(Other KPIs) Anticipated performance at period end | [35 empty] | 37356 | 37356 | 37169 | [30 empty] | 224158 | 220049 | 217311
QIPP Initiative Reporting
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-01-31 | 2014-02-28 | 2014-03-31 | 2014-08-31 | 2014-09-30 | 2014-10-31 | 2014-12-31 | 2015-01-31 | 2015-02-28 |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-06-30 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-09-30 | 2015-01-31 | 2015-02-28 | [9 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-09-30 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-11-30 | 2015-01-31 |  |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-07-31 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-12-31 | 2012-10-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-01-31 | 2015-03-31 |  |  |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | [12 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-10-31 | 2012-12-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-02-28 | [9 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2013-02-28 | 2013-05-31 | 2013-07-31 | 2013-10-31 | 2014-02-28
Progress reporting against milestones and Initiative 1 |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall prog |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly ( |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red
[35 empty] | Most milestones on track however two projects delayed and actiity against plan indicates higher than predicted activity hence red status | [6 empty] | Role out of nurse led clinics being undertaken in some proider trusts but not across all targeted specialities and not at scale across targeted provider trusts - not likely to delier planned savings - needs to be renegotiated as part of 2013/14 comntracting round | [5 empty] | The expansion of nurse led clinics will depend on contract negotiations and willing ness of proiders to build on piolet work to date - as initial phase of role out has been delayyed the further expnsion will also be delayed | [5 empty] | The expansion of nurse led clinics will depend on contract negotiations and willing ness of proiders to build on piolet work to date - as initial phase of role out has been delayyed the further expnsion will also be delayed | [13 empty] | Some slipage against milestones and some over perfromance against plan within the amber SHA threshold hence amber rating |  |  |  |  | new to review ratios projects in place at some target trusts but not across scope or scale initially planned for - need to pick up as part of commissioning and contracting round | Demand management initiatives operational across the cluster - however impact on referals and 1st patient appointements is not reflected in unify though sus ata indicates impact |  | Advice and guidance operational projects being taken forward however scale and scope more limited than initially planned | Work is still ongoing but project progressing with range of direct diagnosis access operational | [23 empty] | Slipage on some key projects particularly in planned care plus oer performance against activity plan hence red rating | [7 empty] | Delivery has been delayed by human resource issues (MARS/Staff Sickness Absence), but planned financial savings for 12/13 will be delivered by end of financial year. |  | Stage 1 visits now due to commence in September so work programme is on track for revised timetable. | [22 empty] | QIPP savings forcast reported to the Board indicate savings are on track to be delivered |  |  |  |  | Redesign plan for LD care pathways being actively progressed with BCHC | Work programme scoped - need to confirm approval status with programme lead and implimentation role out time scale | [26 empty] | Mental Health programme remains on track to deliver panned savings at month 5 |  |  |  |  | Project has been delayed due to capacity and has been assessed as having least impact hence resource deflected from the is project |  |  |  |  | as per comment in FQ initial delay will require subsequent project milestones to be reprofiled | [21 empty] | . | Programe of work remains on plan year to date to deliver planned savings but some project slipage though it is anticipated that this will be accounted for by other projets over delivering | [6 empty] | Management cost reductions not likely to be realised untill later than planed once MARs schemme takes effect | [25 empty] | Management cost savings delayed untill MARS role out is implimeted
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | Completed | Delayed - amber | Completed | Delayed - amber | In progress | In progress | In progress | In progress | Work not yet commenced | Work not yet commenced | In progress | In progress | In progress | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Delayed - red | Delayed - amber | In progress | In progress | In progress | In progress | Delayed - red | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Delayed - red | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [9 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Delayed - red | Completed | Completed | Delayed - amber | In progress | In progress | In progress | In progress | In progress | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced |  |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | Delayed - amber | In progress | Delayed - red | In progress | Work not yet commenced | Completed | Completed | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced |  |  |  | Green | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | In progress | Completed | Completed | In progress | In progress | In progress | In progress | Work not yet commenced |  | In progress | In progress | In progress | In progress | In progress | In progress | In progress | [12 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Delayed - red | Completed | Completed | In progress | In progress | Delayed - red | In progress | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [9 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Delayed - amber | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 |  |  |  | 2012-07-31 | [28 empty] | 0 | [9 empty] | 2012-12-31 | [22 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 |  |  |  | 2012-07-31 | [28 empty] | 0 | [9 empty] | 2012-12-31 | [22 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-10-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-01-31 | 2013-07-31 | 2013-04-30 | 2013-09-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-01-31 | 2014-02-28 | 2014-03-31 | 2014-08-31 | 2014-09-30 | 2014-10-31 | 2014-12-31 | 2015-01-31 | 2015-02-28 | -14.2 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2012-11-30 | 2013-06-30 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-09-30 | 2015-01-31 | 2015-02-28 | [8 empty] | 2.0333 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-09-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-09-30 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-05-31 | 2014-08-31 | 2014-09-30 | 2014-11-30 | 2015-01-31 |  |  | 2.0667 |  |  |  | 2012-07-31 | 2012-05-31 | 2012-05-31 | 2012-07-31 | 2012-08-31 | 2012-12-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2012-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-09-30 | 2014-12-31 | [5 empty] | -11.1333 |  |  |  | 2012-04-30 | 2012-04-30 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 |  | 2013-05-31 | 2013-08-31 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | [11 empty] | -1.0333 |  |  |  | 2012-04-30 | 2012-12-31 | 2012-04-30 | 2012-07-31 | 2012-11-30 | 2012-10-31 | 2013-02-28 | 2012-04-30 | 2013-03-31 | 2013-06-30 | 2013-06-30 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-10-31 | 2015-02-28 | [8 empty] | -8.2 |  |  |  | 2012-04-30 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2013-02-28 | 2013-05-31 | 2013-07-31 | 2013-10-31 | 2014-02-28 | [20 empty] | 0
| Month 2 | 2012-05-31 |  |  |  |  | 2012-05-31 | 2012-06-30 | 2012-01-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-10-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-01-31 | 2013-07-31 | 2013-04-30 | 2013-09-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-01-31 | 2014-02-28 | 2014-03-31 | 2014-08-31 | 2014-09-30 | 2014-10-31 | 2014-12-31 | 2015-01-31 | 2015-02-28 | -19.2333 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2012-11-30 | 2013-06-30 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-09-30 | 2015-01-31 | 2015-02-28 | [8 empty] | 2.0333 |  |  |  | 2012-04-30 | 2012-06-30 | 2012-09-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-09-30 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-11-30 | 2015-01-31 |  |  | 4.0667 |  |  |  | 2012-07-31 | 2012-05-31 | 2012-05-31 | 2012-07-31 | 2012-08-31 | 2012-12-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2012-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-01-31 | 2015-03-31 |  |  |  | -12.1667 |  |  |  | 2012-04-30 | 2012-04-30 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 |  | 2013-05-31 | 2013-08-31 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | [11 empty] | -1.0333 |  |  |  |  | 2012-12-31 | 2012-04-30 | 2012-07-31 | 2012-11-30 | 2012-10-31 | 2013-02-28 | 2013-04-30 | 2013-03-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-02-28 | [8 empty] | 7.0333 |  |  |  | 2012-04-30 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2013-02-28 | 2013-05-31 | 2013-07-31 | 2013-10-31 | 2014-02-28 | [20 empty] | 0
| Month 3 | 2012-06-30 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-06-30 | 2012-10-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-04-30 | 2013-09-30 | 2013-10-31 | 2013-03-31 | 2013-12-31 | 2014-01-31 | 2014-02-28 | 2014-03-31 | 2014-08-31 | 2014-09-30 | 2014-10-31 | 2014-12-31 | 2015-01-31 | 2015-02-28 | -18.3667 |  |  |  |  | 2012-05-31 | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2012-11-30 | 2013-06-30 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-09-30 | 2014-01-31 | 2015-02-28 | [8 empty] | -10.1333 |  |  |  |  | 2012-07-31 | 2012-09-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-09-30 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-11-30 | 2015-01-31 |  |  | 5.1 |  |  |  | 2012-08-31 |  | 2012-05-31 | 2012-07-31 | 2012-08-31 | 2012-12-31 | 2013-04-30 | 2013-01-31 | 2013-03-31 |  | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-03-31 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-01-31 | 2015-01-31 |  |  |  | 3.1 |  |  |  | 2012-04-30 | 2012-08-31 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 |  | 2013-05-31 | 2013-08-31 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | [11 empty] | 4.1 |  |  |  |  | 2012-12-31 |  | 2012-07-31 | 2012-11-30 | 2012-10-31 | 2013-02-28 | 2013-04-30 | 2013-03-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-02-28 | [8 empty] | 10.1 |  |  |  |  | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2013-02-28 | 2013-05-31 | 2013-07-31 | 2013-10-31 | 2014-02-28 | [20 empty] | 0
| Month 4 | 2012-07-31 | [7 empty] | 2012-08-31 | 2012-09-30 |  | 2012-10-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-04-30 | 2013-09-30 | 2013-10-31 | 2013-03-31 | 2013-12-31 | 2014-01-31 | 2014-02-28 | 2014-03-31 | 2014-08-31 | 2014-09-30 | 2014-10-31 | 2014-12-31 | 2015-01-31 | 2015-02-28 | -14.2667 | [6 empty] | 2012-09-30 | 2012-12-31 | 2012-11-30 | 2013-06-30 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-09-30 | 2015-01-31 | 2015-02-28 | [8 empty] | 2.0333 |  |  |  |  | 2012-09-30 | 2012-09-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-09-30 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-11-30 | 2015-01-31 |  |  | 7.1333 |  |  |  | 2012-08-31 |  |  | 2012-07-31 | 2012-08-31 | 2012-12-31 | 2013-04-30 | 2013-01-31 | 2013-03-31 |  |  | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-03-31 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-01-31 | 2015-01-31 |  |  |  | 4.1 |  |  |  | 2012-04-30 | 2012-09-30 | 2012-09-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 |  | 2013-05-31 | 2013-08-31 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | [11 empty] | 7.1333 |  |  |  |  | 2012-12-31 |  |  | 2012-11-30 | 2012-10-31 | 2013-02-28 | 2013-04-30 | 2013-01-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-02-28 | [8 empty] | 8.1333 | [5 empty] | 2012-07-31 | 2012-09-30 | 2013-02-28 | 2013-05-31 | 2013-07-31 | 2013-10-31 | 2014-02-28 | [20 empty] | 0
| Month 5 | 2012-08-31 | [7 empty] | 2012-08-31 | 2012-09-30 |  | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-04-30 | 2013-09-30 | 2013-10-31 | 2013-03-31 | 2013-12-31 | 2014-01-31 | 2014-02-28 | 2014-03-31 | 2014-08-31 | 2014-09-30 | 2014-10-31 | 2014-12-31 | 2015-01-31 | 2015-02-28 | -12.2333 | [6 empty] | 2012-09-30 | 2012-12-31 | 2012-11-30 | 2013-06-30 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-09-30 | 2015-01-31 | 2015-02-28 | [8 empty] | 2.0333 |  |  |  |  | 2013-04-30 | 2012-09-30 |  | 2012-10-31 | 2012-09-30 | 2012-10-31 | 2012-09-30 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-03-31 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-11-30 | 2015-01-31 |  |  | 14.2 |  |  |  | 2012-08-31 |  |  |  | 2012-12-31 | 2012-12-31 | 2013-04-30 | 2013-01-31 | 2013-03-31 |  |  | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-03-31 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-01-31 | 2015-01-31 |  |  |  | 8.1667 |  |  |  |  | 2012-09-30 | 2012-09-30 |  | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 |  | 2013-05-31 | 2013-08-31 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | [11 empty] | 7.1333 |  |  |  |  | 2012-12-31 |  |  | 2012-11-30 | 2012-10-31 | 2013-02-28 | 2013-04-30 | 2013-03-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-02-28 | [8 empty] | 10.1 | [6 empty] | 2013-01-31 | 2013-02-28 | 2013-05-31 | 2013-07-31 | 2013-10-31 | 2014-02-28 | [20 empty] | 4.1
| Month 6 | 2012-09-30 | [8 empty] | 2012-10-31 |  | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-04-30 | 2013-09-30 | 2013-10-31 | 2013-03-31 | 2013-12-31 | 2014-01-31 | 2014-02-28 | 2014-03-31 | 2014-08-31 | 2014-09-30 | 2014-10-31 | 2014-12-31 | 2015-01-31 | 2015-02-28 | -11.2 | [6 empty] | 2012-09-30 | 2012-12-31 | 2012-11-30 | 2013-06-30 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-09-30 | 2015-01-31 | 2015-02-28 | [8 empty] | 2.0333 |  |  |  |  | 2013-04-30 |  |  | 2012-10-31 | 2013-01-31 | 2012-10-31 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-03-31 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-11-30 | 2015-01-31 |  |  | 16.2667 | [7 empty] | 2013-03-31 | 2012-12-31 | 2013-04-30 | 2013-01-31 | 2013-03-31 |  |  | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-03-31 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-01-31 | 2015-03-31 |  |  |  | 12.1 |  |  |  |  | 2012-09-30 | 2012-12-31 |  | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 |  | 2013-05-31 | 2013-08-31 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | [11 empty] | 10.2 |  |  |  |  | 2012-12-31 |  |  | 2012-11-30 | 2012-10-31 | 2013-02-28 | 2013-04-30 | 2013-03-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-02-28 | [8 empty] | 10.1 | [6 empty] | 2013-01-31 | 2013-02-28 | 2013-05-31 | 2013-07-31 | 2013-10-31 | 2014-02-28 | [20 empty] | 4.1
| Month 7 | 2012-10-31 | [8 empty] | 2012-10-31 | [23 empty] | 1.0333 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone | [5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [11 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [7 empty] | 4 | 4 | 5 | 5 | 4 | 4 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 4 | 4 | [14 empty] | 5 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [13 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Number of CCGs who have completed this milestone | [5 empty] | 5 | 5 | 5 |  |  |  | 5 | 5 | [25 empty] | 5 | 5 | 5 | [31 empty] | 1 |  |  |  | 5 | [27 empty] | 5 |  | 5 | [6 empty] | 5 | 5 | [22 empty] | 4 | [32 empty] | 2 |  | 5 | [30 empty] | 5 | 5
Percentage of PCTs completing this milestone |  |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 20% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Blackcountry_QIPPmilestones
2012- 2013 Milestone Tracker |  |  | 100 - Acute Contracts (Elective) | [32 empty] | 120 - Acute Contracts (non-elective) | [32 empty] | 130 - Acute Contracts (outpatients) | [32 empty] | 160 - MH / LD | [32 empty] | 220 - Primary Care Prescribing | [32 empty] | 240 - Primary Care / Dental / Pharmacy / Opthalmic | [32 empty] | 250 - PCT Running Costs
QIPP Overview and finances
SHA cluster: |  | NHS Midlands and East
PCT Cluster : |  | Black Country
Number of CCGs in cluster: |  | 4
Report for the month of:
QIPP Challenge (£000s) |  | 338535
FIMS Plan: Savings for CSR period (£000s) |  | 399514.6156
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s) |  | 126494
Yr 2 Plan FIMS savings for 2012-13 (£000s) |  | 99047
Yr 3 Plan FIMS savings for 2013-14 (£000s) |  | 95648
Yr 4 Plan FIMS savings for 2014-15 (£000s) |  | 78326
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 399515
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be <50% of years 2-4 (Cells C11:C13)) |  | 184140
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale | PCT cluster |  | Title | Planned Care Strategic Change Programme | [28 empty] | Scale | PCT cluster |  | Title | Unscheduled Care Strategic Change Programme | [28 empty] | Scale | PCT cluster |  | Title | Planned Care Strategic Change Programme | [28 empty] | Scale | PCT cluster |  | Title | Mental Health and Learning Disabilities Strategic Change Programme | [28 empty] | Scale | PCT cluster |  | Title | Better Prescribing and Medicines Management | [28 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 | 12750 | FIMS savings 2013-14 | 13969 | FIMS savings 2014-15 | 11604 | Total for CSR period | 38323 | [25 empty] | FIMS savings 2012-13 | 18759 | FIMS savings 2013-14 | 15626 | FIMS savings 2014-15 | 13415 | Total for CSR period | 47800 | [25 empty] | FIMS savings 2012-13 | 12354 | FIMS savings 2013-14 | 10582 | FIMS savings 2014-15 | 7735 | Total for CSR period | 30671 | [25 empty] | FIMS savings 2012-13 | 6280 | FIMS savings 2013-14 | 6459 | FIMS savings 2014-15 | 6573 | Total for CSR period | 19312 | [25 empty] | FIMS savings 2012-13 | 8645 | FIMS savings 2013-14 | 8308 | FIMS savings 2014-15 | 7315 | Total for CSR period | 24268 | [25 empty] | FIMS savings 2012-13 | 5545 | FIMS savings 2013-14 | 5664 | FIMS savings 2014-15 | 2697 | Total for CSR period | 13906 | [25 empty] | FIMS savings 2012-13 | 5102 | FIMS savings 2013-14 | 3462 | FIMS savings 2014-15 | 1296 | Total for CSR period | 9860
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative. |  |  |  |  | Planned decrease in elective activity of 4% from 2011/12 levels. Activity shifts from secondary to primary/community care settings through service re-design | Activity modelling for Quality and Sustainability Review (QSR) review complete (NB - QSR will cover several categories of activity types) | Clinical Senate signs-off cluster-wide Planned Care Strategic Change Programme (SCP) | All CCGs have in place confirmed priorities for local and cluster-wide changes for inclusion in QSR. | Proposals for cluster-wide planned care SCP service re-design / re-configuration agreed by Clinical Senate | Undertake assessment by each provider of extent of implementation of enhanced recovery programme in colroectal, gynaecology, hips and knees and urology. | Consider requirements for public consultation for planned care SCP service re-design and agree with HOSCs (commence consultation where required) | Agree forward plans with providers to achieve full roll out of Enhanced Recovery Programme in four specialites | Review providers' progress in delivering planned actions for implementing Enhanced Recovery Programmes and agree further actions | Public Consultation for planned care SCP service re-design ends and decision to implement taken by Clinical Senate and CCG Boards. | All providers agreed contractual agreements for Enhanced Recovery for the 4 Right Care national programme clinical specialties | Develop an overarching strategy for planned care which is sensitive to CCG specific plans and priorities in addition to establishing a strategic black country vision for the development of services | Evaluate con to con referral schemes, New to review schemes, PoLCV schemes, OP redesign schemes, Daycase to OP procedures coding changes | Disseminate and share best practice on to con referral schemes, New to review schemes, PoLCV schemes, OP redesign schemes, Daycase to OP procedures coding changes | Evaluate con to con referral schemes, New to review schemes, PoLCV schemes, OP redesign schemes, Daycase to OP procedures coding changes. Evaluate Gynaecology / Dermatology | Disseminate and share best practice on to con referral schemes, New to review schemes, PoLCV schemes, OP redesign schemes, Daycase to OP procedures coding changes | [14 empty] | There is a risk that not enough resource exists to ensure that the Strategic Change Programme will be managed and delivered effectively. Potential service re-configuration will require Provider buy-in which may be difficult to achieve. CCGs are focussed on authorisation process and LAs are looking at NHSCB footprints which is impacting on time to work on SCP functions. Staff moves to new structures are impacting on business continuity. |  |  | Non-elective activity remains consistent with 2011/12 levels. 4% reduction in A&E activity through improved triage systems | Analysis of opportunities for reduction of Urgent Care activity through pathway re-design / improved triage / service re-design through contract negotiations complete. | Clinical Senate signs-off cluster-wide Unscheduled Care Strategic Change Programme (SCP), with project content identified, incl plans for UC service change/activity shifts/workforce/finance (PID) | Local QIPP Board decisions to implement reduction of Urgent Care activity projects achieved (incl decision on whether public consultation is required) achieved | Agree proposal for annual survey of telehealth care use | Proposals for cluster-wide SCP service re-design / re-configuration agreed by Clinical Senate | Consider requirements for public consultation for unscheduled care SCP service re-design and agree with HOSCs (commence consultation where required) | Undertake annual survey of tele care usage showing number of LTC service users accessing assistive technology | Public Consultation for unscheduled care SCP service re-design ends and decision to implement taken by Clinical Senate and CCG Boards | Agree changes to contracts with providers to deliver increased usage of tele care 111 Service commissioned | Develop an overarching clinical strategy which is sensitive to CCG specific plans and priorities in addition to establishing a strategic black vision for the development of services Commissioning strategy and supporting plan for the roll-out of telecare for LTC patients Dudley: implement urgent care in the community, 111 and EAU/CDU/SAU | Walsall: Evaluation of urgent, OOH and EoL schemes Evaluation of all UC schemes across all PCTs | Evaluation of all UC schemes across all PCTs | [17 empty] | There is a risk that not enough resource exists to ensure that the Strategic Change Programme will be managed and delivered effectively. Potential service re-configuration will require Provider buy-in which may be difficult to achieve. CCGs are focussed on authorisation process which is impacting on time to work on SCP functions. Staff moves to new structures are impacting on business continuity. |  |  | Nearly 2.5% reduction in 1st O/P and 5% reduction in follow-up O/P attendances through adoption of revised clinically agreed policies | Local content identified for outpatient modernisation plans / referral management plans / pathway re-design projects - content identified, incl plans for service change/activity shifts/workforce/finance (PID) | Local QIPP Board decisions taken to implement outpatient modernisation plans / referral management plans / pathway re-design achieved (incl decision on whether public consultation is required) | Implementation of service change begins in Wolverhampton for RWHT Modernisation Plan Phase 1 | Planned Care SCP to disseminate and share best practice for C2C referral schemes, New to review schemes, PoLCV schemes, OP redesign schemes, Daycase to OP procedures coding changes | Consider requirements for public consultation for planned care SCP service re-design and agree with HOSCs (commence consultation where required) | Public Consultation for planned care SCP service re-design ends and decision to implement taken by Clinical Senate and CCG Boards. | Evaluation of schemes completed | [22 empty] | There is an issue in that the Wolverhampton modernisation programme will not deliver the required savings for 2012/13. This is being mitigated through other progojects and the PCT still anticipates achieving its QIPP target for the financial year. |  |  | £19m reduction in spend across MH/LD including reducing out of area and high cost placements within continuing care through re-patriation of clients | Local project content identified, including plans for service change/activity shifts/workforce/finance (PID) for reduction of MH/LD Out of Area Placements and better use of anti-psychotic drugs across Primary and Secondary Care | Clinical Senate signs-off MH/LD cluster-wide Strategic Change Programme (SCP) | Proposals for cluster-wide MH/LD SCP service re-design / re-configuration agreed by Clinical Senate | Consider requirement for MH/LD SCP public consultation and agree with HOSCs for cluster-wide service re-design. Commence consultation where required | Public Consultation on proposed service re-design ends. Decision to implement taken by Clinical Senate and CCG Boards | Develop an overarching strategy for mental health and LD which is sensitive to CCG specific plans and priorities in addition to establishing a strategic black country vision for the development of services | Evaluation of schemes completed | [22 empty] | Potential service re-configuration will require Provider buy-in which may be difficult to achieve. CCGs are focussed on authorisation process and LAs are looking at NHSCB footprints which is impacting on time to work on SCP functions. |  |  | 2.5% reduction in planned spend through better prescribing and medicines management | Local QIPP Board decisions to implement Medicines Management and Primary Care projects achieved (incl decision on whether public consultation is required) | Clinical Senate signs-off Primary Care and Medicines Management Strategic Change Programme (SCP) | Proposals for Medicines Management and Primary Care SCP service re-design / re-configuration agreed by Clinical Senate | Consider requirement for Medicines Management and Primary Care SCP public consultation and agree with HOSCs and commence consultation where required | Public Consultation on proposed service re-design ends. Decision to implement taken by Clinical Senate and CCG Boards | Develop an overarching strategy for meds management and Primary Care which is sensitive to CCG specific plans and priorities in addition to establishing a strategic black vision for the development of services • Transfer of primary care contracting responsibilities | Commence implementation of primary care quality improvement schemes | Evaluation of schemes completed | Complete Evaluation of range of QIPP schemes throughout the cluster | Disseminate good practice across all Black Country CCGs March | Evaluate primary care quality improvement schemes • Commence implementation of primary care provider development schemes following piloting phase | Evaluation of schemes completed | [17 empty] | There is a lack of clarity about the precise role of the NHSCB. Possible lack of GP support of MM strategies. CCGs remain focussed on authorisation process and LAs are looking at NHSCB footprints which is impacting on time to work on SCP functions. |  |  | 2.5% reduction in planned spend through refreshed GP list size validation, re-configured dental services, GMS/PMS cost control, better use of PC facilities and improved waste management controls. | GP list size validation projects implemented cluster-wide | Local QIPP Board decisions to implement Medicines Management and Primary Care projects achieved (incl decision on whether public consultation is required) | Clinical Senate signs-off Primary Care and Medicines Management Strategic Change Programme (SCP) | GP list size validation project complete for 2012/13 | Proposals for Medicines Management and Primary Care SCP service re-design / re-configuration agreed by Clinical Senate | Consider requirement for Medicines Management and Primary Care SCP public consultation and agree with HOSCs and commence consultation where required | Public Consultation on proposed service re-design ends. Decision to implement taken by Clinical Senate and CCG Boards | Develop an overarching strategy for meds management and Primary Care which is sensitive to CCG specific plans and priorities in addition to establishing a strategic black vision for the development of services • Transfer of primary care contracting responsibilities | Commence implementation of primary care quality improvement schemes | Evaluation of schemes completed | Complete Evaluation of range of QIPP schemes throughout the cluster | Disseminate good practice across all Black Country CCGs March | Evaluate primary care quality improvement schemes • Commence implementation of primary care provider development schemes following piloting phase | Evaluation of schemes completed | [15 empty] | There is a lack of clarity about the precise role of the NHSCB. Possible lack of GP support of MM strategies. CCGs remain focussed on authorisation process and LAs are looking at NHSCB footprints which is impacting on time to work on SCP functions. |  |  | Achievement of £14.6m reduction in operating costs. | Project content identified, incl plans for service change/activity shifts/workforce/finance (PID) for HQ Shared Costs / aggregation of Informatics and IT costs / re-configuration of estates complete | Cluster Board decision to implement HQ Shared Costs / aggregation of Informatics and IT costs / re-configuration of estates achieved | Development of estates contract exit strategies commences. | Completion of Estates Rationalisation Plan. | [25 empty] | There is a significant risk and challenge in developing timely and robust responses to the ICT requirements of all receiver orginisations. This is further compunded by the need to integrate with BSoL cluster.
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones |  |  | Total number of FFCEs in the period | [32 empty] | Number of G&A non-elective FFCEs in the period | [32 empty] | All first outpatient attendances (consultant-led) in general and acute specialties
(UNIFY indicators) Anticipated performance at period end |  |  | 158610 | 155724 | 156463 | [30 empty] | 118180 | 117789 | 118018 | [30 empty] | 372499 | 371495 | 373182
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s))) |  |  | Number of elective FFCEs - ordinary admissions | [65 empty] | Number of 1st outpatient attendances (consultant-led) following GP referral in general and acute specialties
(Other KPIs) Anticipated performance at period end |  |  | 32187 | 31772 | 31978 | [63 empty] | 219135 | 217093 | 216025
QIPP Initiative Reporting
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-07-31 | 2012-07-31 | 2012-11-30 | 2012-10-31 | 2013-01-31 | 2012-12-31 | 2013-01-31 | 2013-04-30 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-10-31 | 2014-07-31 | 2014-10-31 | [15 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-07-31 | 2012-06-30 | 2012-08-31 | 2012-11-30 | 2013-01-31 | 2012-12-31 | 2013-04-30 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2014-07-31 | [18 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-05-31 | 2012-06-30 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-02-28 | 2013-07-31 | [23 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-06-30 | 2012-07-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [23 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-06-30 | 2012-07-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [18 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [16 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-05-31 | 2012-06-30 | 2012-08-31 | 2013-03-31
Progress reporting against milestones and Initiative 1 |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall prog |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly ( |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber
[6 empty] | The modelling work is complete and will inform the QSR as implementation of the review progresses | Planned Care leads have been identified and a meeting is being organised to kick-start the project. | Meetings are proving difficult to arrange due to CCG authorisation so comments have been requested via email and compiled into a response document. This will form the basis for further discussion at meetings to be arranged Sept-Dec 12. | [26 empty] | Validated M4 elective activity data shows that actual activity levels are just 1.3% more than the same period last year with some high levels of over-performance seen in M4. I/P admissions are significantly below 11/12 levels however daycases remain above 11/12 levels. This over-performance is due in part to a double-counting issue at Walsall (which has been notified to and agreed with the Provider) and a delay in implementing some QIPP schemes at Wolverhampton which are specifically aimed at reducing elective activity. Both of these issues are on the scrutiny agenda and will be closely managed over the coming months. In addition, Wolverhampton are also counting specialised service activity in the 'actual' trajectory. |  |  |  | This milestone is complete as the baseline QIPP plan and contracts for 2012/13 have been agreed. | Proposals to adopt cluster-wide SCP service re-design projects has been approved by the clinical senate. Milestone complete. | Milestone complete as all local QIPP projects have been agreed and are under implementation. No schemes are currently deemed to require public consultation. | [26 empty] | M4 activity over-performance is showing YTD activity over-performing by 4.9% against plan which places the domain in the amber rating. This over-perfomance may be largely attributed to Sandwell and Wolves where performance is 6-6.5% above plan. This is in part due to QIPP initiative funding being tied up in the 2% NR pool which has now been approved for use and should start to show improvement against this over-performance during the second half of the year. Additionally, Wolverhampton continues to include specialised services activity in their actual activity and have also seen an increase in A&E activity which may be impacting through more emergency admissions. |  |  |  | The Wolverhampton modernisation programme is not delivering the requied levels of savings. Mitigating actions have been put in place to ensure the QIPP financial target will be delivered. | This milestone is interdependent with QIPP LM 3.1 and will therefore mirror that milestone's status profile. | This milestone is interdependent with QIPP LM 3.1 and will therefore mirror that milestone's status profile. | [26 empty] | Direct year on year YTD comparision shows that GP and other referral activity are higher than at the same point in 11/12 however, despite the increases in referral activity, Month 4 validated data shows that there is a marginal increase in actual 1st O/P activity at the same point in 2011/12 and that collectively the cluster is only 1.7% over plan against its 2012/13 trajectory. The QIPP outpatient profile is broadly on target to deliver financially. Referral patterns are being analysed and results of this analysis will be shared in due course. |  |  |  | All MH/LD QIPP schemes for 12/13 have been identified and included in the QIPP portfolio. | Clinical Senate has authorised the approach to develop MH strategy in May. Milestone complete. | [27 empty] | Milestones and financial performance for this domain are both on track. On-going issues at Penn Hospital in Wolves have been downgraded in terms of their severity rating and is no longer of 'major concern' to the CQC. QIPP schemes are realising fewer out of area placements for MH/LD. |  |  |  | All local QIPP MM/PC projects are in progress with no requirement for public consultation currently required. Milestone complete. | CS endorsement to proceed with the SCP has been achieved. Milestone complete. | [27 empty] | No significant issues with this work stream to date. Financial performance is slightly behind YTD trajectory however FOT is for the plan to be achieved. All milestones have been met. |  |  |  | GP list size validation programme has commenced across the cluster. Milestone complete. | All local QIPP MM/PC projects are in progress with no requirement for public consultation currently required. Milestone complete. | CS endorsement to proceed with the SCP has been achieved. Milestone complete. | A consistent approach for list cleansing has been developed, quantification of financial savings as a consequence of implementation is outstanding. Full delivery of all LSV is on a rolling programme and will not be completed until the end of 2012/13 | [25 empty] | No significant issues with this work stream to date although the list size validation project will take longer to deliver than initially anticipated. Financial performance is slightly behind YTD trajectory however FOT is on plan. All milestones have been met. |  |  |  | All local QIPP requirements for 2012/13 have been identified and profiled for delivery. | The cluster board has taken the decision to implement the re-configuration work, however some challenges remain to achieve the delivery of full ICT enablement and integration. | Contract stock-take has been undertaken and is now in the stabilisation phase. Premises catalogueing is underway and is scheduled for completion within the national timetable of 31 October. | [26 empty] | All bar one of the milestones have been achieved and while the cluster is slightly behind in its YTD savings position, it fully expects to deliver the year-end running cost target. The risk to ICT requirements of receiver organisations remains and this may impact on some receiver organisations ability to operate effectively on a day to day basis. Mitigating actions continue to be tested by both applicable clusters.
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Delayed - amber | Delayed - amber | In progress | In progress | Work not yet commenced | In progress | Work not yet commenced | Work not yet commenced | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [15 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | In progress | In progress | Work not yet commenced | In progress | Work not yet commenced | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | [18 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Delayed - red | Delayed - red | In progress | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | [23 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [23 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [18 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Delayed - amber | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [16 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Delayed - amber | Completed | In progress
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 |  |  |  | 2012-04-30 | 2012-07-31 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-10-31 | 2014-07-31 | 2014-10-31 | [14 empty] | -6.1333 |  |  |  | 2012-04-30 | 2012-07-31 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-11-30 | 2012-12-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2014-07-31 | [17 empty] | -6.1333 |  |  |  | 2012-06-30 | 2012-06-30 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-02-28 | 2013-07-31 | [22 empty] | 1 |  |  |  | 2012-06-30 | 2012-07-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [22 empty] | 0 |  |  |  | 2012-06-30 | 2012-07-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [17 empty] | 0 |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [15 empty] | 0 |  |  |  | 2012-05-31 | 2012-06-30 | 2012-08-31 | 2013-03-31 | [25 empty] | 0
| Month 2 | 2012-05-31 |  |  |  | 2012-04-30 | 2012-07-31 | 2012-07-31 | 2012-11-30 | 2012-10-31 | 2013-01-31 | 2012-12-31 | 2013-01-31 | 2013-04-30 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-10-31 | 2014-07-31 | 2014-10-31 | [14 empty] | 0 |  |  |  |  | 2012-07-31 | 2012-06-30 | 2012-08-31 | 2012-11-30 | 2013-01-31 | 2012-12-31 | 2013-04-30 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2014-07-31 | [17 empty] | 0 |  |  |  | 2012-06-30 | 2012-06-30 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-02-28 | 2013-07-31 | [22 empty] | 1 |  |  |  | 2012-06-30 | 2012-07-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [22 empty] | 0 |  |  |  | 2012-06-30 | 2012-07-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [17 empty] | 0 |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [15 empty] | 0 |  |  |  | 2012-05-31 | 2012-06-30 | 2012-08-31 | 2013-03-31 | [25 empty] | 0
| Month 3 | 2012-06-30 |  |  |  |  | 2012-08-31 | 2012-07-31 | 2012-11-30 | 2012-10-31 | 2013-01-31 | 2012-12-31 | 2013-01-31 | 2013-04-30 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-10-31 | 2014-07-31 | 2014-10-31 | [14 empty] | 1.0333 |  |  |  |  | 2012-08-31 | 2012-06-30 | 2012-08-31 | 2012-11-30 | 2013-01-31 | 2012-12-31 | 2013-04-30 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2014-07-31 | [17 empty] | 1.0333 |  |  |  | 2012-08-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-02-28 | 2013-07-31 | [22 empty] | 5.1333 |  |  |  | 2012-06-30 | 2012-06-30 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [22 empty] | -1.0333 |  |  |  | 2012-06-30 | 2012-06-30 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [17 empty] | -1.0333 | [6 empty] | 2012-09-30 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [15 empty] | 0 |  |  |  |  | 2012-12-31 | 2012-08-31 | 2013-03-31 | [25 empty] | 6.1333
| Month 4 | 2012-07-31 |  |  |  |  | 2012-08-31 | 2012-09-30 | 2012-11-30 | 2012-10-31 | 2013-01-31 | 2012-12-31 | 2013-01-31 | 2013-04-30 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-10-31 | 2014-07-31 | 2014-10-31 | [14 empty] | 3.0667 |  |  |  |  | 2012-07-31 |  | 2012-08-31 | 2012-11-30 | 2013-01-31 | 2012-12-31 | 2013-04-30 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2014-07-31 | [17 empty] | 0 |  |  |  | 2012-09-30 | 2012-09-01 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-02-28 | 2013-07-31 | [22 empty] | 6.1667 | [5 empty] | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [22 empty] | 0 | [5 empty] | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [17 empty] | 0 | [6 empty] | 2012-09-30 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [15 empty] | 0 |  |  |  |  | 2012-12-31 | 2012-08-31 | 2013-03-31 | [25 empty] | 6.1333
| Month 5 | 2012-08-31 |  |  |  |  | 2012-11-30 | 2012-09-30 | 2012-11-30 | 2012-10-31 | 2013-01-31 | 2012-12-31 | 2013-01-31 | 2013-04-30 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-10-31 | 2014-07-31 | 2014-10-31 | [14 empty] | 6.1 | [6 empty] | 2012-09-30 | 2012-11-30 | 2013-01-31 | 2012-12-31 | 2013-04-30 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2014-07-31 | [17 empty] | 1 |  |  |  | 2012-09-30 | 2012-09-01 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-02-28 | 2013-07-31 | [22 empty] | 6.1667 | [5 empty] | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [22 empty] | 0 | [5 empty] | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [17 empty] | 0 | [6 empty] | 2012-09-30 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [15 empty] | 0 |  |  |  |  | 2012-12-31 | 2012-08-31 | 2013-03-31 | [25 empty] | 6.1333
| Month 6 | 2012-09-30 |  |  |  |  | 2012-11-30 | 2012-11-30 | 2012-11-30 | 2012-10-31 | 2013-01-31 | 2012-12-31 | 2013-01-31 | 2013-04-30 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-10-31 | 2014-07-31 | 2014-10-31 | [14 empty] | 8.1333 | [7 empty] | 2012-11-30 | 2013-01-31 | 2012-12-31 | 2013-04-30 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2014-07-31 | [17 empty] | 0 |  |  |  | 2013-03-31 | 2013-03-31 | 2013-03-31 | 2012-10-31 | 2012-11-30 | 2013-02-28 | 2013-07-31 | [22 empty] | 25.3333 | [5 empty] | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [22 empty] | 0 | [5 empty] | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [17 empty] | 0 | [6 empty] | 2013-03-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | 2014-07-31 | [15 empty] | 6.0667 |  |  |  |  | 2012-12-31 | 2012-09-30 | 2013-03-31 | [25 empty] | 7.1333
| Month 7 | 2012-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [17 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [20 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [25 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [25 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [20 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [18 empty] | 4 | 4 | 4 | 4 | 4
Number of CCGs who have completed this milestone | [5 empty] | 2012-04-30: 4 | [18 empty] | 4 | 4 | 4 | [30 empty] | 3 | 3 | [31 empty] | 4 | 4 | [31 empty] | 4 | 4 | [30 empty] | 4 | 4 | 4 | 4 | [30 empty] | 4 |  | 4
Percentage of PCTs completing this milestone |  |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | 0% | 75% | 75% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | 0% | 100% | 0% | 100% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Staffordshire_QIPPmilestones
2012- 2013 Milestone Tracker |  |  | Mental Health | [32 empty] | Acute NEL | [32 empty] | Acute Elective | [32 empty] | Acute Outpatient | [32 empty] | Prescribing | [32 empty] | Primary Care | [32 empty] | QIPP Initiative 7
QIPP Overview and finances
SHA cluster: |  | NHS Midlands and East
PCT Cluster : |  | Staffordshire
Number of CCGs in cluster: |  | 6
Report for the month of:
QIPP Challenge (£000s) |  | 226000
FIMS Plan: Savings for CSR period (£000s) |  | 365569.7058
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s) |  | 101979
Yr 2 Plan FIMS savings for 2012-13 (£000s) |  | 100279
Yr 3 Plan FIMS savings for 2013-14 (£000s) |  | 89392
Yr 4 Plan FIMS savings for 2014-15 (£000s) |  | 73922
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 365572
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be <50% of years 2-4 (Cells C11:C13)) |  | 174101
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale | PCT cluster |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 | 7726 | FIMS savings 2013-14 | 5324 | FIMS savings 2014-15 | 5373 | Total for CSR period | 18423 | [25 empty] | FIMS savings 2012-13 | 18632 | FIMS savings 2013-14 | 19772 | FIMS savings 2014-15 | 11842 | Total for CSR period | 50246 | [25 empty] | FIMS savings 2012-13 | 9755 | FIMS savings 2013-14 | 6891 | FIMS savings 2014-15 | 6960 | Total for CSR period | 23606 | [25 empty] | FIMS savings 2012-13 | 10283 | FIMS savings 2013-14 | 8158 | FIMS savings 2014-15 | 6576 | Total for CSR period | 25017 | [25 empty] | FIMS savings 2012-13 | 11658 | FIMS savings 2013-14 | 11387 | FIMS savings 2014-15 | 8468 | Total for CSR period | 31513 | [25 empty] | FIMS savings 2012-13 | 8922 | FIMS savings 2013-14 | 8146 | FIMS savings 2014-15 | 8228 | Total for CSR period | 25296 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative. |  |  |  |  | Reconfigured Mental Health Services across Staffordshire. Reduction of 40 acute Mental Health beds supported by enhanced Community provision. | North LHE, Phase 1 implementation - Relocation of wrds to new site resulting in closure of Bucknall Hospital site in North. Phase 2 Consultation commences on the new model of care reviewing role of Day hospitals and bed based services with a view to improving access to care closer to home | Revised Dementia action plan in place which will allow better management of patients in the community | South Staffs - Crisis Resolution and Home Treatment services expanded which will reduce the admissions to acute hospital settings | In North,Phase 2 Implementation of new model of care following Consultation. Activity planned to be closer to home with proposed community beds reducing by 15 | Margaret Stanhope - 25 beds decommissioned | FYE of reconfigured community Mental Health provision | Evaluation of service change implemented in 12/13 leading to continued roll out or further redesign | [25 empty] | Acute non elective activity to be reduced by 23050 by March 2014. In the Northern LHE the benefits of new services implemented in 2011/12 will be realised in future years. In the Southern LHE the benefits of new services implemented in 2012/13 will be realised in future years. | Integration of Adult Social Care with SSOTP go live | Formal consultation commences on Urgent Care Centre Model at MSFT ( CSIP) | Rollout of Risk Stratification and Telehealth in South Staffordshire in 4 Pilot sites | NHS 111 Contract awarded | South - Integrated Community teams -case management model of care in place focusing on admission avoidance for patients with LTC | Redesigned service model in place for frail elderly resulting in relocation of services from the Outwood site in East Staffordshire | Implementation of New Emergency & Urgent care Model MSFT ( CSIP) | South West - Integrated Community teams -Frail Elderly model of care in place focusing on admission avoidance | Staffordshire wide remodel of Joint equipment provision new contract awarded | Go Live of NHS 111 | Full rollout of Risk Stratification & Telehealth to all GP practices in South Staffordshire. This will allow improved management of patients in community and reduced NEL admissions | Full roll out & Evaluation of New Emergency & Urgent care Model MSFT implemented Oct 12/13 (CSIP) resulting in reduced NEL attendances and admissions | Joint Equipment Service implemented - Staffordshire Wide | LTC Care pathways and Services Roll out in south West Staffordshire (CSIP) | Roll out of Case mananagement, integrated community teams for LTC, Frail elderly and EOLC East and West Staffordshire (CSIP & Burton Programme) | Continued Roll out & Evaluation of Risk Stratification & Telehealth Care accross staffordshire | Ongoing roll out of Public Health inititiatives focused on prevention | Continued activity reduction anticipated by Front of House Service initiated in 2012/13 in the Northern LHE | Redesigned Children's Services in place in South Staffordshire (CSIP) | Continued benefits realised from the full roll out & Evaluation of New Emergency & Urgent care Model MSFT implemented Oct 12/13 (CSIP) resulting in reduced NEL attendances and admissions | [12 empty] | Reduction in Acute activity to Community Services. (elective) | New Community Service implemented for Minor Hand Surgery in SOT | Full Tongue Tie service for Babies up to 6 months implemented | Review of Supportive Therapies Service with view to Expanding Service to deliver more care outside of Acute Hospital - NS & SOT | Embedding POLCV as routine practice in Primary Care Demand management | Continuing Healthcare - All providers signed upto NHS Contract | 75% of Elective Surgery at BHFT to be done as Day case Proceedures | FYE of reconfigured Outpatient redesign, follow up, demand management, care pathway redesign | Continuing Healthcare - All providers signed upto NHS Contract | FYE of all revised services realised | [23 empty] | Managed Demand, transfer of activity to Community. Activity reduced by 18502 | Full implementation of Direct Access to Diagnostics in the community in the North | Phased implementation of Clinical Pathways to reduce First to Follow ups in West Staffordshire | MSK Triage Service - phased implementation in South West Staffordshire | POLCV policy in place for West and East Staffordshire | Full implementation of Clinical Pathways to reduce First to Follow ups in East and West Staffordshire | Community Dermatology Serivce in place in South West Staffordshire | Full implementation of MSK Triage Service in West Staffordshire | LTC Care pathways and Services rolled out in South West Staffordshire (CSIP) | Full roll out and activity reductions anticipated for Clinical Pathways implemented in 12/13 to reduce First to Follow ups in East and West Staffordshire | FYE of POLCV policy in place for West and East Staffordshire | [22 empty] | Full Price efficiency realised through pro active medicine managment in Primary Care, reduced usage, appropriate choice of antibiotics | Prescribing Support in place. Planning phase complete, Scriptswitch , SIP feeds and TTOs implemented and benefits realised, Review of antibiotic prescribing guidelines completed | Prescribing Support - full Benefits to be evaluated before continued roll out or redesign | Benefits of ongoing programme of work realised e.g. prescribing Support in place, Scriptswitch , SIP feeds and TTOs implemented and benefits realised, Review of antibiotic prescribing guidelines completed | Continued Roll out of and evaluation of impact of prescribing Support - Scriptswitch , SIP feeds and TTOs implemented and benefits realised, | [28 empty] | Primary Care review for quality and efficiencies accross the Cluster | FYE of contractual changes
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones | [35 empty] | Number of G&A non-elective FFCEs in the period | [32 empty] | Total number of FFCEs in the period | [32 empty] | All first outpatient attendances (consultant-led) in general and acute specialties
(UNIFY indicators) Anticipated performance at period end | [35 empty] | 99051 | 99052 | 99052 | [30 empty] | 159951 | 159951 | 159951 | [30 empty] | 268204 | 268201 | 268201
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s))) | [68 empty] | Number of elective FFCEs - ordinary admissions | [32 empty] | Number of 1st outpatient attendances (consultant-led) following GP referral in general and acute specialties
(Other KPIs) Anticipated performance at period end | [68 empty] | 29510 | 29511 | 29511 | [30 empty] | 165556 | 165557 | 165557
QIPP Initiative Reporting
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2014-04-30 | [23 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-04-30 | [10 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [21 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [20 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-10-31 | 2013-04-30 | 2014-04-30 | [26 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2013-04-30 | [29 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31
Progress reporting against milestones and Initiative 1 |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall prog |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly ( |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating
[6 empty] | Phase 1 relocation complete. Phase 2 consultation commenced | Action plan now completed | Work ongoing | Consultation commenced 10th May 2012 and ends on 1st August 2012 | Bed closure approved by Cluster board. Revised dementia plan and expansion of Crisis resolution service ongoing | FYE effect following known outcomes of consultation | work ongoing | [22 empty] | The reconfiguration of Mental Health services across Staffordshire continues to make good progress with all individual milestones on target to deliver |  |  |  | Full integration of Staffordshire Social Care and Partnership trust goes live | Consultation commencement still unclear - Subject to SHA approval. Awaiting outcome of enquiry | Rolled out 4 pilot sites complete. Rolling out now to other practices. Report due August 2012 for initial 4 sites | On track for delivery. Contract awarded August 2012. Service go live February 2013 | work ongoing | work ongoing | Awaiting outcome of public enquiry | work ongoing | on track to award contract | on track to go live | Practices across South Staffs are signing up to implementing risk stratification and undertaking MDTs for 1-5% of practice population in their first year, dependent upon CCG. The MDT will consider options for use of telehealth devises to improve the management of patients. | Subject to outcome of consultation. | Contract on track to be awarded | Work ongoing re: LTC pathway redesign | work ongoing | work ongoing | work ongoing | work ongoing around activity reduction | work ongoing | work ongoing around new model of care | [9 empty] | Although the majority of QIPP schemes are on track for delivery the activity levels are above plan across the main acute providers (exl. MSFT) in Staffordshire. Commissioners continue to review the situation with the main providers |  |  |  | Service up and running | Service up and running | Review ongoing with view to move activity out of acute to community | work ongoing to embed POLCV into routine practice | work ongoing | work ongoing | work ongoing | work ongoing | work ongoing | [20 empty] | Progress on the shift of activity from acute to community settings is good. Due to the high levels of referrals into the system this domain is rated as Red. Commissioners continue to review and explore redesign options |  |  |  | Service up and running | Phasing of pathways ongoing | Phased implementation ongoing. Scheme on track | Work ongoing to embed POLCV across the East and West | work ongoing | work ongoing | on track for delivery | work ongoing | work in progress | work in progress | [19 empty] | Due to a high level referrals into the system this domain is rated as Red |  |  |  | Medicines management phase completed | work ongoing | work ongoing | work ongoing | [25 empty] | Based on the progress on the delivery of QIPP projects and the unavailability of prescribing data this domain has been rated as amber. Further interal review planned in July 2012 |  |  |  | Ongoing | [28 empty] | Based on the progress on the delivery of QIPP projects and the unavailability of prescribing data this domain has been rated as amber. Further interal review planned in July 2012
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | In progress | In progress | In progress | In progress | [23 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Delayed - amber | Completed | Completed | Completed | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | [10 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | In progress | In progress | In progress | In progress | In progress | [21 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | In progress | In progress | In progress | In progress | In progress | In progress | [20 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | In progress | In progress | In progress | [26 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [5 empty] | 2012-06-30 | 2012-07-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | [22 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [5 empty] | 2012-06-30 | 2012-07-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | [22 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2014-04-30 | [22 empty] | 0 |  |  |  | 2012-04-30 | 2012-07-31 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-04-30 | [9 empty] | 2.0333 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2014-03-31 | 2013-04-30 | [20 empty] | -12.1667 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [19 empty] | 0 |  |  |  | 2012-04-30 | 2012-10-31 | 2013-04-30 | 2014-04-30 | [25 empty] | 0 |  |  |  | 2013-04-30 | [28 empty] | 0 | [32 empty] | 0
| Month 2 | 2012-05-31 |  |  |  |  | 2012-05-31 | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2014-04-30 | [22 empty] | 0 |  |  |  | 2012-04-30 | 2012-07-31 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-04-30 | [9 empty] | 2.0333 |  |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2014-03-31 | 2013-04-30 | [20 empty] | -12.1667 |  |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [19 empty] | 0 |  |  |  |  | 2012-10-31 | 2013-04-30 | 2014-04-30 | [25 empty] | 0 |  |  |  | 2013-04-30 | [28 empty] | 0 | [32 empty] | 0
| Month 3 | 2012-06-30 | [5 empty] | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2014-04-30 | [22 empty] | 0 |  |  |  |  | 2012-07-31 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-04-30 | [9 empty] | 0 | [5 empty] | 2012-06-30 | 2012-07-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2014-03-31 | 2013-04-30 | [20 empty] | -12.1667 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [19 empty] | 0 |  |  |  |  | 2012-10-31 | 2013-04-30 | 2014-04-30 | [25 empty] | 0 |  |  |  | 2013-04-30 | [28 empty] | 0 | [32 empty] | 0
| Month 4 | 2012-07-31 | [5 empty] | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2014-04-30 | [22 empty] | 0 |  |  |  |  | 2012-08-31 |  | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-04-30 | [9 empty] | 1.0333 | [6 empty] | 2012-07-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2014-03-31 | 2013-04-30 | [20 empty] | -12.1667 | [6 empty] | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [19 empty] | 0 |  |  |  |  | 2012-10-31 | 2013-04-30 | 2014-04-30 | [25 empty] | 0 |  |  |  | 2013-04-30 | [28 empty] | 0 | [32 empty] | 0
| Month 5 | 2012-08-31 | [5 empty] | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2013-04-30 | [22 empty] | -12.1667 |  |  |  |  | 2012-11-30 |  | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2013-02-28 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-04-30 | [9 empty] | 7.0667 | [7 empty] | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2014-03-31 | 2013-04-30 | [20 empty] | -12.1667 | [7 empty] | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [19 empty] | 0 |  |  |  |  | 2012-10-31 | 2013-04-30 | 2014-04-30 | [25 empty] | 0 |  |  |  | 2013-04-30 | [28 empty] | 0 | [32 empty] | 0
| Month 6 | 2012-09-30 | [5 empty] | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2013-04-30 | [22 empty] | -12.1667 | [7 empty] | 2012-09-30 | 2012-10-31 | 2013-02-28 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-07-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-04-30 | [9 empty] | 0.96667 | [7 empty] | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2014-03-31 | 2013-04-30 | [20 empty] | -12.1667 | [7 empty] | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | [19 empty] | 0 |  |  |  |  | 2012-10-31 | 2013-04-30 | 2014-04-30 | [25 empty] | 0 |  |  |  | 2013-04-30 | [28 empty] | 0 | [32 empty] | 0
| Month 7 | 2012-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone | [5 empty] | 2 | 5 | 4 | 2 | 4 | 6 | 6 | [26 empty] | 5 | 2 | 4 | 6 | 4 | 2 | 2 | 4 | 6 | 6 | 4 | 2 | 6 | 2 | 4 | 6 | 6 | 2 | 2 | 4 | [13 empty] | 2 | 2 | 2 | 2 | 6 | 2 | 6 | 6 | 6 | [24 empty] | 2 | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 4 | 4 | [23 empty] | 6 | 6 | 6 | 6 | [29 empty] | 6
Number of CCGs who have completed this milestone | [5 empty] | 2 | 5 | [31 empty] | 5 |  | 4 | [30 empty] | 2 | 2 | 2 | 2 | [29 empty] | 2 | 2 | 2 | 4 | [29 empty] | 6 | [32 empty] | 6
Percentage of PCTs completing this milestone |  |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 1 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## WestMercia_QIPPmilestones
2012- 2013 Milestone Tracker |  |  | Acute Contracts (Elective) | [32 empty] | Acute Contracts (Non Elective) | [32 empty] | Acute Contracts (Outpatients) | [32 empty] | Continuing Healthcare | [32 empty] | Primary Care Prescribing | [32 empty] | QIPP Initiative 6 | [32 empty] | QIPP Initiative 7
QIPP Overview and finances
SHA cluster: |  | NHS Midlands and East
PCT Cluster : |  | West Mercia
Number of CCGs in cluster: |  | 6
Report for the month of:
QIPP Challenge (£000s) |  | 383638
FIMS Plan: Savings for CSR period (£000s) |  | 382225.449
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s) |  | 103528
Yr 2 Plan FIMS savings for 2012-13 (£000s) |  | 88913
Yr 3 Plan FIMS savings for 2013-14 (£000s) |  | 92209
Yr 4 Plan FIMS savings for 2014-15 (£000s) |  | 97575
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 382225
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be <50% of years 2-4 (Cells C11:C13)) |  | 180079
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 | 10526 | FIMS savings 2013-14 | 16569 | FIMS savings 2014-15 | 17391 | Total for CSR period | 44486 | [25 empty] | FIMS savings 2012-13 | 22082 | FIMS savings 2013-14 | 21679 | FIMS savings 2014-15 | 23950 | Total for CSR period | 67711 | [25 empty] | FIMS savings 2012-13 | 11627 | FIMS savings 2013-14 | 13544 | FIMS savings 2014-15 | 15192 | Total for CSR period | 40363 | [25 empty] | FIMS savings 2012-13 | 2839 | FIMS savings 2013-14 | 1697 | FIMS savings 2014-15 | 1697 | Total for CSR period | 6233 | [25 empty] | FIMS savings 2012-13 | 7261 | FIMS savings 2013-14 | 7042 | FIMS savings 2014-15 | 6983 | Total for CSR period | 21286 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 13-14 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative. |  |  |  |  | Development of Elective Pathways to support the reduction of Elective Admissions by 6% and reduction in Elective Day Cases by 1% from FY11/12 baseline. | Primary Care Demand Management Establish referral assessment centres for each economy | Elective Pathways: Establish cluster-wide evaluation process to benchmark demand management schemes | Elective Pathways TRAQ system go live (Telford & Wrekin CCG) | Herefordshire Workforce Develop local workforce and recruit key posts based on outcome of transformation plan (Herefordshire) | Elective Pathways: Review evaluation and learning on best practice re: performance of different CCG programmes. Actions for implementation to be decided on outcome | Elective Pathways: Report impact of implementation of plans to QIPP Boards and decide action for implementation | Primary Care Demand Management Complete shared evaluation of referal assessment centres and decide appropriate actions for implementation | Elective Pathways Cluster wide review of demand management successes and variations at CCG level and identify local opportunities and action plans | Elective Pathways: Review evaluation and learning on best practice re: performance of different CCG programmes. Actions for implementation to be decided on outcome | Elective Pathways Cluster wide review of demand management successes and variations at CCG level and identify local opportunities and action plans | Elective Pathways: Review evaluation and learning on best practice re: performance of different CCG programmes. Actions for implementation to be decided on outcome | [21 empty] | Development of Elderly and Proactive Care Services to support limiting the Non-elective admissions to 2% increase on FY11/12 baseline. Primary efforts will be in: Mental Health; Community Teams (Worcestershire); Falls (Worcestershire); End of Life; Major Trauma (towards regional targets); Primary Care Schemes; and LTC. | Community Teams Full implementation of 24/7 district nursing across Worcestershire | End of Life RACE (rapid access to carers at end of life) service becomes fully operational (moving from pilot to full service) | LTC (Various schemes) Implementation of Integrated Community Teams (including use of risk stratification tool) (SWCCG) | Mental Health RAID Programme implemented (Worcestershire) RAID team recruited and in place (Telford & Wrekin) | Primary Care Schemes Commence re-procurement of Out of Hours Service (SWCCG) | LTC (Various schemes) Long Term Conditions strategy approved to enable implementation (Shropshire) | End of Life "Frail and Complex" Team Operational (Shropshire) | End of Life Implementation of disease specific end of life pathways pilots for COPD/Heart failure/Parkinson’s Frail elderly commences (Worcestershire) | LTC (Various schemes) Commission 24/7 Psychiatric Liaison Service (SWCCG) | Falls(Worcester) Additional fracture liaison service capacity commences | LTC (Various) Implementation of 24/7 service with second permanent build cardiac catheterisation | Primary Care Schemes Commence re-procurement of urgent care pathway (Walk in Centre alternative) | Primary Care Schemes Start of new Out of Hours Service | Primary Care Schemes Agree revised primary care access service specification for implementation | End of Life Evaluation of disease specific end of life pathways pilots for COPD/Heart failure/Parkinson’s Frail elderly commences | Primary Care Schemes Implement new primary care access strategy through the new service specification | Primary Care Schemes Complete review of Urgent Care pathway, incorporating alternative Walk in Centre arrangements and Out of Hours Service. Commence implementation of agreed actions. | [15 empty] | Development of Elective pathways to support reduction in First Outpatient Attendences by 8% from FY12/13 outturn. Primary efforts will be in: Opthamology (Worcestershire); Radiotherapy (Worcestershire); Outpatient Redesign (Shropshire); and Orthopaedics (Worcestershire). | Orthopeadics (Worcestershire) Evaluation of redesigned orthopaedic pathway across community and secondary care to identify any unintended consequences and subsequent rectification | Radiotherapy (Worcestershire) NHS Midlands and East Approval of Full Business Case for implementation | Outpatient Redesign (Shropshire) Scheduled Care and Outpatient Redesign: 4 new pathways related to pathway redesign in place | Radiotherapy (Worcestershire) Start of construction if Business Case Approved | Orthopeadics (Worcestershire) Detailed review of project outcomes and refresh of modelling to determine whether 2013/14 QIPP savings are achievable. Actions and impact on contractual agreements to be confirmed upon completion of review | Ophthalmology Implement new contractual arrangements (based on outcome of options appraisal recommendations). | Ophthalmology Formal review and report to CCG boards on the performance of the new service and implement necessary actions | Radiotherapy Completion of construction. Commence commissioning of new facility | Radiotherapy Commissioning complete – service opens | [23 empty] | Improved quality of services which are resilient to growing demands. VFM secured from all providers limiting financial growth to c.£7M (c.15%). | Continuing Care Applications made to DH to be allowed to give personal budgets as direct payments (Herefordshire) | Continuing Care development of review into high cost packages of care. Timescales for reporting process agreed (Herefordshire) | Continuing Care Quantify opportunities to bring patients closer to home and commence transfer to personal budgets (assuming status is achieved) (Herefordshire) | Continuing Care Implement CHC policy and re- patriations. | Continuing Care Review impact of implementation and repatriation. Assess opportunities and action for further development | Continuing Care Depending on outcome of DH application, review outcome of Herefordshire's introduction of direct payments and consider potential roll-out across Cluster and actions necessary | Continuing Care Review impact of implementation and repatriation. Assess opportunities and action for further development | [25 empty] | Improved primary care use of medicines, as well as reduced procurement costs for common prescribing areas will lead to a managed growth in total prescribing costs of c.8% (well below increased rate in number of items prescribed). | Medicines Management Agree action plans for delivery of MM QIPP schemes with CCGs | Medicines Management Agree individual action plans with practices where active prescribing change is required to deliver additional savings | Medicines Management To have visited all GP practices and agreed a practice action plan for better value switches and national indicators (Shropshire) | Medicines Management Establish Cluster wide formulary for high cost drugs. | Medicines Management Individual meetings with practices not meeting agreed targets to ensure delivery | Medicines Management Agree action plans for delivery of MM QIPP schemes with CCGs | Medicines Management Agree individual action plans with practices where active prescribing change is required to deliver additional savings | Medicines Management To have visited all GP practices and agreed a practice action plan for better value switches and national indicators | Medicines Management Individual meetings with practices not meeting agreed targets to ensure delivery | Medicines Management Agree action plans for delivery of MM QIPP schemes with CCGs | Medicines Management Agree individual action plans with practices where active prescribing change is required to deliver additional savings | Medicines Management To have visited all GP practices and agreed a practice action plan for better value switches and national indicators | Medicines Management Individual meetings with practices not meeting agreed targets to ensure delivery
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones |  |  | Total number of FFCEs in the period | [32 empty] | Number of G&A non-elective FFCEs in the period | [32 empty] | All first outpatient attendances (consultant-led) in general and acute specialties
(UNIFY indicators) Anticipated performance at period end |  |  | 157920 | 156529 | 156423 | [30 empty] | 106945 | 105993 | 106458 | [30 empty] | 329545 | 318769 | 310946
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s))) |  |  | Number of elective FFCEs - ordinary admissions | [65 empty] | Number of 1st outpatient attendances (consultant-led) following GP referral in general and acute specialties
(Other KPIs) Anticipated performance at period end |  |  | 34038 | 33213 | 32729 | [63 empty] | 174381 | 163451 | 159121
QIPP Initiative Reporting
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-06-30 | 2013-10-31 | 2014-06-30 | 2014-10-31 | [19 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-04-30 | 2014-08-31 | [13 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-06-30 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-12-31 | 2014-03-31 | 2014-06-30 | [21 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-08-31 | 2012-11-30 | 2013-06-30 | 2013-09-30 | 2014-06-30 | [23 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-12-31 | 2013-04-30 | 2013-06-30 | 2013-07-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-12-31 | [17 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31
Progress reporting against milestones and Initiative 1 |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall prog |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly ( |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Red | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating
[35 empty] | Activity: M5 Unify Figure show a Cluster-wide 3.2% overperformance against the planned figures which represents a consistent shift across the cluster. M5 SUS showed a 5.8% YTD decrease over last year compared to a planned decrease of 6%. FIMS: M5 FIMS shows a 7% over achievement of savings. Progress: In general, progress is good against the milestones. Rating: Rating to be retained at Amber. Though the finance data shows an over achiechievement of savings at this stage, this may be optimistic. The activity data is solidly amber; we are expecting an increase in demand due to the over performance in GP referrals and 1st outpatients attendendances in parts of the cluster. | [6 empty] | Telford RAID team being recruited. | Worcestershire OOH is currently supplied by Harmoni with a contract end date of Sept 13. CCGs are gradually taking over their responsibilities and we expect this to be completed over the next month to 6 weeks. Given a number is significant risks in the system and especially the JSR we have written to Harmoni recommending a 12 month extension so that we can understand the implications of any acute reconfiguration. Whilst we have not heard formally from Harmoni, informally they are content with this. | [24 empty] | Activity: M5 Unify Figure show a Cluster-wide 9.2% overperformance against the planned figures which represents a consistent shift across the cluster. M5 SUS showed a 10% YTD increase over last year against a planned 2% increase. FIMS: M5 FIMS shows a 25% underachievement of against the savings profile. Progress: In general, progress is good against the declared milestones and a number of alternative schemes have been implemented to address the significant overperformance. Rating: Rating to be retained at Red. The activity measures continue to overheat andthis is reflected in the financial data. The over performance shows no pattern across the cluster and each CCG has implemented local initiatives to bring down the level of over performance. Though these will not have an impact on activity until October/November the Cluster and CCGs are focusing on the progress of these new schemes in the short term. | [32 empty] | Activity: M5 Unify data show a Cluster-wide 5% overperformance against the planned level. M5 SUS showed a 4.1% YTD increase over last year. FIMS: M5 FIMS data shows a 6% over achievement of savings against the profile. Progress: In general, progress against declared milestones is good. Rating: Rating to be retained as RED. Activity shows sustained over performance, and though the Financial returns show signs of optimism the individual schemes are heavily weighted to the later part of the year, and must therefore be considered a risk. | [32 empty] | Activity: No activity data is available. FIMS: The M5 FIMS shows a 35% over achievement of savings against profile. Progress: In general, progress is good against the declared milestones Rating: Rating to be retained at GREEN. | [32 empty] | Activity: No activity data is available. FIMS: The M5 FIMS shows a 3.5% under achievement of savings against profile. Progress: In general, progress is good against the milestones. Rating: Rating to be retained at AMBER. The general progress against milestones is good and and small shortfall in savings is not causing concern at this stage.
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  |  | Completed | Completed | Completed | In progress | In progress | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [19 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | In progress | Completed | In progress | In progress | In progress | In progress | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [13 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | [29 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | [27 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | [26 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | [21 empty] | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 |  |  |  | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-06-30 | 2013-10-31 | 2014-06-30 | 2014-10-31 | [18 empty] | 3.0333 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-04-30 | 2014-08-31 | [12 empty] | 0 |  |  |  | 2012-06-30 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-12-31 | 2014-03-31 | 2014-06-30 | [20 empty] | 0 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-08-31 | 2012-11-30 | 2013-06-30 | 2013-09-30 | 2014-06-30 | [22 empty] | 0 |  |  |  | 2012-04-30 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-12-31 | 2013-04-30 | 2013-06-30 | 2013-07-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-12-31 | [16 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2012-05-31 |  |  |  |  | 2012-06-30 | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-06-30 | 2013-10-31 | 2014-06-30 | 2014-10-31 | [18 empty] | 1 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-04-30 | 2014-08-31 | [12 empty] | 0 |  |  |  | 2012-06-30 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-12-31 | 2014-03-31 | 2014-06-30 | [20 empty] | 0 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-08-31 | 2012-11-30 | 2013-06-30 | 2013-09-30 | 2014-06-30 | [22 empty] | 0 |  |  |  |  | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-12-31 | 2013-04-30 | 2013-06-30 | 2013-07-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-12-31 | [16 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2012-06-30 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-06-30 | 2013-10-31 | 2014-06-30 | 2014-10-31 | [18 empty] | 0 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-04-30 | 2014-08-31 | [12 empty] | 0 |  |  |  | 2012-06-30 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-12-31 | 2014-03-31 | 2014-06-30 | [20 empty] | 0 | [5 empty] | 2012-08-31 | 2012-11-30 | 2013-06-30 | 2013-09-30 | 2014-06-30 | [22 empty] | 0 |  |  |  |  | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-12-31 | 2013-04-30 | 2013-06-30 | 2013-07-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-12-31 | [16 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2012-07-31 | [6 empty] | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-06-30 | 2013-10-31 | 2014-06-30 | 2014-10-31 | [18 empty] | 0 | [6 empty] | 2012-10-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-04-30 | 2014-08-31 | [12 empty] | 3.0667 |  |  |  |  | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-12-31 | 2014-03-31 | 2014-06-30 | [20 empty] | 0 | [5 empty] | 2012-08-31 | 2012-11-30 | 2013-06-30 | 2013-09-30 | 2014-06-30 | [22 empty] | 0 | [5 empty] | 2012-07-31 | 2012-09-30 | 2012-12-31 | 2013-04-30 | 2013-06-30 | 2013-07-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-12-31 | [16 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2012-08-31 | [7 empty] | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-06-30 | 2013-10-31 | 2014-06-30 | 2014-10-31 | [18 empty] | 0 | [6 empty] | 2012-10-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-04-30 | 2014-08-31 | [12 empty] | 3.0667 |  |  |  |  | 2012-11-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-12-31 | 2014-03-31 | 2014-06-30 | [20 empty] | 2.0333 | [6 empty] | 2012-11-30 | 2013-06-30 | 2013-09-30 | 2014-06-30 | [22 empty] | 0 | [6 empty] | 2012-09-30 | 2012-12-31 | 2013-04-30 | 2013-06-30 | 2013-07-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-12-31 | [16 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2012-09-30 | [7 empty] | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-06-30 | 2013-10-31 | 2014-06-30 | 2014-10-31 | [18 empty] | 0 | [6 empty] | 2012-10-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-09-30 | 2013-11-30 | 2014-01-31 | 2014-04-30 | 2014-08-31 | [12 empty] | 3.0667 |  |  |  |  | 2012-11-30 | 2012-10-31 | 2012-11-30 | 2013-01-31 | 2013-04-30 | 2013-12-31 | 2014-03-31 | 2014-06-30 | [20 empty] | 2.0333 | [6 empty] | 2012-11-30 | 2013-06-30 | 2013-09-30 | 2014-06-30 | [22 empty] | 0 | [6 empty] | 2012-09-30 | 2012-12-31 | 2013-04-30 | 2013-06-30 | 2013-07-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-12-31 | [16 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2012-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone | [5 empty] | 6 | 6 | 1 | 1 | 6 | 6 | 2 | 6 | 6 | 6 | 6 | [22 empty] | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | [16 empty] | 3 | 3 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [26 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Number of CCGs who have completed this milestone | [5 empty] | 6 | 6 | 1 | 1 | [29 empty] | 1 |  | 2012-07-31: 2 | [16 empty] | 3 | [32 empty] | 1 | 1 | [32 empty] | 6 | 6
Percentage of PCTs completing this milestone |  |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 0% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## WM
Arden | Number of Milestones |  | Completed | In progress | Delayed - amber | Delayed - red | Work not yet commenced | Blank Cells | Total (-blanks) | Total | Staffordshire | Number of Milestones |  | Completed | In progress | Delayed - amber | Delayed - red | Work not yet commenced | Blank Cells | Total (-blanks) | Total
Initiative 1 | 10 |  | 3 | 4 | 3 | 0 | 0 | 0 | 10 | 10 | Initiative 1 | 7 |  | 3 | 4 | 0 | 0 | 0 | 0 | 7 | 7
Initiative 2 | 3 |  | 1 | 2 | 0 | 0 | 0 | 0 | 3 | 3 | Initiative 2 | 20 |  | 4 | 15 | 1 | 0 | 0 | 0 | 20 | 20
Initiative 3 | 6 |  | 0 | 5 | 1 | 0 | 0 | 0 | 6 | 6 | Initiative 3 | 9 |  | 4 | 5 | 0 | 0 | 0 | 0 | 9 | 9
Initiative 4 | 13 |  | 2 | 10 | 1 | 0 | 0 | 0 | 13 | 13 | Initiative 4 | 10 |  | 4 | 6 | 0 | 0 | 0 | 0 | 10 | 10
Initiative 5 | 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | Initiative 5 | 4 |  | 1 | 3 | 0 | 0 | 0 | 0 | 4 | 4
Initiative 6 | 5 |  | 0 | 4 | 1 | 0 | 0 | 0 | 5 | 5 | Initiative 6 | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Initiative 7 | 9 |  | 2 | 7 | 0 | 0 | 0 | 0 | 9 | 9 | Initiative 7 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total: | 48 |  | 8 | 34 | 6 | 0 | 0 | 0 | 48 | 48 | Total: | 51 | 0 | 16 | 33 | 1 | 0 | 0 | 1 | 50 | 51
B'Ham & Solihull | Number of Milestones |  | Completed | In progress | Delayed - amber | Delayed - red | Work not yet commenced | Blank Cells | Total (-blanks) | Total | West Mercia | Number of Milestones |  | Completed | In progress | Delayed - amber | Delayed - red | Work not yet commenced | Blank Cells | Total (-blanks) | Total
Initiative 1 | 29 |  | 6 | 9 | 2 | 0 | 12 | 0 | 29 | 29 | Initiative 1 | 11 |  | 3 | 3 | 0 | 0 | 4 | 1 | 10 | 11
Initiative 2 | 21 |  | 3 | 5 | 1 | 3 | 9 | 0 | 21 | 21 | Initiative 2 | 17 |  | 4 | 6 | 0 | 0 | 7 | 0 | 17 | 17
Initiative 3 | 27 |  | 3 | 6 | 1 | 1 | 16 | 0 | 27 | 27 | Initiative 3 | 9 |  | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 9
Initiative 4 | 26 |  | 6 | 2 | 1 | 1 | 16 | 0 | 26 | 26 | Initiative 4 | 7 |  | 3 | 0 | 0 | 0 | 0 | 4 | 3 | 7
Initiative 5 | 17 |  | 4 | 12 | 0 | 0 | 1 | 0 | 17 | 17 | Initiative 5 | 13 |  | 4 | 0 | 0 | 0 | 0 | 9 | 4 | 13
Initiative 6 | 21 |  | 3 | 4 | 0 | 2 | 12 | 0 | 21 | 21 | Initiative 6 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiative 7 | 9 |  | 3 | 1 | 1 | 0 | 4 | 0 | 9 | 9 | Initiative 7 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total: | 150 |  | 28 | 39 | 6 | 7 | 70 | 0 | 150 | 150 | Total: | 57 |  | 15 | 9 | 0 | 0 | 11 | 22 | 35 | 57
Black Country | Number of Milestones |  | Completed | In progress | Delayed - amber | Delayed - red | Work not yet commenced | Blank Cells | Total (-blanks) | Total
Initiative 1 | 15 |  | 1 | 4 | 2 | 0 | 8 | 0 | 15 | 15
Initiative 2 | 12 |  | 3 | 4 | 0 | 0 | 5 | 0 | 12 | 12
Initiative 3 | 7 |  | 0 | 2 | 0 | 2 | 3 | 0 | 7 | 7
Initiative 4 | 7 |  | 2 | 1 | 0 | 0 | 4 | 0 | 7 | 7
Initiative 5 | 12 |  | 2 | 1 | 0 | 0 | 9 | 0 | 12 | 12
Initiative 6 | 14 |  | 3 | 1 | 1 | 0 | 9 | 0 | 14 | 14
Initiative 7 | 4 |  | 2 | 1 | 1 | 0 | 0 | 0 | 4 | 4
Total: | 71 | 0 | 13 | 14 | 4 | 2 | 38 | 0 | 71 | 71
West Midlands | Number of Milestones |  | Completed | In progress | Delayed - amber | Delayed - red | Work not yet commenced | Blank Cells | Total (-blanks) | Total
Initiative 1 | 72 | 0 | 16 | 24 | 7 | 0 | 24 | 1 | 71 | 72
Initiative 2 | 73 | 0 | 15 | 32 | 2 | 3 | 21 | 0 | 73 | 73
Initiative 3 | 58 | 0 | 8 | 18 | 2 | 3 | 19 | 8 | 50 | 58
Initiative 4 | 63 | 0 | 17 | 19 | 2 | 1 | 20 | 4 | 59 | 63
Initiative 5 | 48 | 0 | 11 | 18 | 0 | 0 | 10 | 9 | 39 | 48
Initiative 6 | 41 | 0 | 6 | 9 | 2 | 2 | 21 | 1 | 40 | 41
Initiative 7 | 22 | 0 | 7 | 9 | 2 | 0 | 4 | 0 | 22 | 22
Total: | 377 | 0 | 80 | 129 | 17 | 9 | 119 | 23 | 354 | 377

## PCTcluster6_QIPPmilestones (hidden)
2012- 2013 Milestone Tracker |  |  | QIPP Initiative 1 | [32 empty] | QIPP Initiative 2 | [32 empty] | QIPP Initiative 3 | [32 empty] | QIPP Initiative 4 | [32 empty] | QIPP Initiative 5 | [32 empty] | QIPP Initiative 6 | [32 empty] | QIPP Initiative 7
QIPP Overview and finances
SHA cluster:
PCT Cluster :
Number of CCGs in cluster:
Report for the month of:
QIPP Challenge (£000s)
FIMS Plan: Savings for CSR period (£000s)
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s)
Yr 2 Plan FIMS savings for 2012-13 (£000s)
Yr 3 Plan FIMS savings for 2013-14 (£000s)
Yr 4 Plan FIMS savings for 2014-15 (£000s)
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 0
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be >50% of years 2-4 (Cells C10:C12)) |  | 0
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 13-14 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative.
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones
(UNIFY indicators) Anticipated performance at period end
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s)))
(Other KPIs) Anticipated performance at period end
QIPP Initiative Reporting
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31
Progress reporting against milestones and Initiative 1 |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall prog |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly ( |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2012-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2012-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2012-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2012-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2012-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2012-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone
Number of CCGs who have completed this milestone
Percentage of PCTs completing this milestone |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## PCTcluster7_QIPPmilestones (hidden)
2012- 2013 Milestone Tracker |  |  | QIPP Initiative 1 | [32 empty] | QIPP Initiative 2 | [32 empty] | QIPP Initiative 3 | [32 empty] | QIPP Initiative 4 | [32 empty] | QIPP Initiative 5 | [32 empty] | QIPP Initiative 6 | [32 empty] | QIPP Initiative 7
QIPP Overview and finances
SHA cluster:
PCT Cluster :
Number of CCGs in cluster:
Report for the month of:
QIPP Challenge (£000s)
FIMS Plan: Savings for CSR period (£000s)
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s)
Yr 2 Plan FIMS savings for 2012-13 (£000s)
Yr 3 Plan FIMS savings for 2013-14 (£000s)
Yr 4 Plan FIMS savings for 2014-15 (£000s)
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 0
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be <50% of years 2-4 (Cells C10:C12)) |  | 0
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 13-14 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative.
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones
(UNIFY indicators) Anticipated performance at period end
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s)))
(Other KPIs) Anticipated performance at period end
QIPP Initiative Reporting
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31
Progress reporting against milestones and Initiative |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall prog |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly ( |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2012-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2012-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2012-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2012-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2012-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2012-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone
Number of CCGs who have completed this milestone
Percentage of PCTs completing this milestone |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## lists (hidden)
SHA Milestone Type commissioning support | SHA Milestone end date commissioning support | SHA Milestone Type Clinical Commissioning Groups | SHA Milestone end date Clinical Commissioning Groups | SHA Milestone Type Direct Commissioning | SHA Milestone end date Direct Commissioning | SHA Milestone Type Any Qualified Provider | SHA Milestone end date Any Qualified Provider | SHA Milestone Type Health and Well Being Boards | SHA Milestone end date Health and Well Being Boards | SHA Milestone Type Public Health Transfer to Local Authorities | SHA Milestone end date Public Health Transfer to Local Authorities | SHA Milestone Type Public Health Transfer to Public Health England | SHA Milestone end date Public Health Transfer to Public Health England | PCT Milestone Type commissioning support | PCT Milestone end date commissioning support | PCT Milestone Type Clinical Commissioning Groups | PCT Milestone end date Clinical Commissioning Groups | PCT Milestone Type Direct Commissioning | PCT Milestone end date Direct Commissioning | PCT Milestone Type Any Qualified Provider | PCT Milestone end date Any Qualified Provider | PCT Milestone Type Health and Well Being Boards | PCT Milestone end date Health and Well Being Boards | PCT Milestone Type Public Health Transfer to Local Authorities | PCT Milestone end date Public Health Transfer to Local Authorities | PCT Milestone Type Public Health Transfer to Public Health England | PCT Milestone end date Public Health Transfer to Public Health England | PCT Milestone Type QIPP Initiative 1 | PCT Milestone end date QIPP Initiative 1 | PCT Milestone Type QIPP Initiative 2 | PCT Milestone end date QIPP Initiative 2 | PCT Milestone Type QIPP Initiative 3 | PCT Milestone end date QIPP Initiative 3 | PCT Milestone Type QIPP Initiative 4 | PCT Milestone end date QIPP Initiative 4 | PCT Milestone Type QIPP Initiative 5 | PCT Milestone end date QIPP Initiative 5 | PCT Milestone Type QIPP Initiative 6 | PCT Milestone end date QIPP Initiative 6 | PCT Milestone Type QIPP Initiative 7 | PCT Milestone end date QIPP Initiative 7 | PCT Milestone Type QIPP Initiative 8 | PCT Milestone end date QIPP Initiative 8 | PCT Milestone Type QIPP Initiative 9 | PCT Milestone end date QIPP Initiative 9 | PCT Milestone Type Foundation Trusts | PCT Milestone end date Foundation Trusts | Date | QIPP Workstream focus | Scale of QIPP workstream | FIMS Categories | FIMS Categories Level 2 SHA | Project Categories | RAG Rating | Milestone status | SHA Cluster | PCT cluster | CCG | Number of organisations
SHA CS End state 12-13 | SHA CS End state 12-13 | SHA CCG End state 12-13 | SHA CCG End state 12-13 | SHA DC End state 12-13 | SHA DC End state 12-13 | SHA AQP End state 12-13 | SHA AQP End state 12-13 | SHA HWB End state 12-13 | SHA HWB End state 12-13 | SHA PHT LAs End state 12-13 | SHA PHT LAs End state 12-13 | SHA PHT PHE End state 12-13 | SHA PHT PHE End state 12-13 | PCT CS End state 12-13 | PCT CS End state 12-13 | PCT CCG End state 12-13 | PCT CCG End state 12-13 | PCT DC End state 12-13 | PCT DC End state 12-13 | PCT AQP End state 12-13 | PCT AQP End state 12-13 | PCT HWB End state 12-13 | PCT HWB End state 12-13 | PCT PHT LAs End state 12-13 | PCT PHT LAs End state 12-13 | PCT PHT PHE End state 12-13 | PCT PHT PHE End state 12-13 | QIPP 1 End state 12-13 | QIPP 1 End state 12-13 | QIPP 2 End state 12-13 | QIPP 2 End state 12-13 | QIPP 3 End state 12-13 | QIPP 3 End state 12-13 | QIPP 4 End state 12-13 | QIPP 4 End state 12-13 | QIPP 5 End state 12-13 | QIPP 5 End state 12-13 | QIPP 6 End state 12-13 | QIPP 6 End state 12-13 | QIPP 7 End state 12-13 | QIPP 7 End state 12-13 | QIPP 8 End state 12-13 | QIPP 8 End state 12-13 | QIPP 9 End state 12-13 | QIPP 9 End state 12-13 | FTs End state 12-13 | FTs End state 12-13 | 2011-12-31 | Quality | CCG | Not applicable | Not applicable | Mental health | Red | Completed | NHS London | Bristol & N Somerset & S Gloucestershire |  | N/A
SHA CS NME 1 | SHA CS NME 1 end | SHA CCG NME 1 | SHA CCG NME 1 end | SHA DC NME 1 | SHA DC NME 1 end | SHA AQP NME 1 | SHA AQP NME 1 end | SHA HWB NME 1 | SHA HWB NME 1 end | SHA PHT LAs NME 1 | SHA PHT LAs NME 1 end | SHA PHT PHE NME 1 | SHA PHT PHE NME 1 end | PCT CS NME 1 | PCT CS NME 1 end | PCT CCG NME 1 | PCT CCG NME 1 end | PCT DC NME 1 | PCT DC NME 1 end | PCT AQP NME 1 | PCT AQP NME 1 end | PCT HWB NME 1 | PCT HWB NME 1 end | PCT PHT LAs NME 1 | PCT PHT LAs NME 1 end | PCT PHT PHE NME 1 | PCT PHT PHE NME 1 end | QIPP 1 End state 13-14 | QIPP 1 End state 13-14 | QIPP 2 End state 13-14 | QIPP 2 End state 13-14 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP 4 End state 13-14 | QIPP 4 End state 13-14 | QIPP 5 End state 13-14 | QIPP 5 End state 13-14 | QIPP 6 End state 13-14 | QIPP 6 End state 13-14 | QIPP 7 End state 13-14 | QIPP 7 End state 13-14 | QIPP 8 End state 13-14 | QIPP 8 End state 13-14 | QIPP 9 End state 13-14 | QIPP 9 End state 13-14 | FTs NME 1 | FTs NME 1 end | 2012-01-31 | Activity | PCT | Acute Contracts (Elective) | Productivity | Acute Sector | Amber | In progress | NHS Midlands and East | Bournemouth Poole & Dorset |  | 1
SHA CS NME 2 | SHA CS NME 2 end | SHA CCG NME 2 | SHA CCG NME 2 end | SHA DC NME 2 | SHA DC NME 2 end | SHA AQP NME 2 | SHA AQP NME 2 end | SHA HWB NME 2 | SHA HWB NME 2 end | SHA PHT LAs NME 2 | SHA PHT LAs NME 2 end | SHA PHT PHE NME 2 | SHA PHT PHE NME 2 end | PCT CS NME 2 | PCT CS NME 2 end | PCT CCG NME 2 | PCT CCG NME 2 end | PCT DC NME 2 | PCT DC NME 2 end | PCT AQP NME 2 | PCT AQP NME 2 end | PCT HWB NME 2 | PCT HWB NME 2 end | PCT PHT LAs NME 2 | PCT PHT LAs NME 2 end | PCT PHT PHE NME 2 | PCT PHT PHE NME 2 end | QIPP 1 End state 14-15 | QIPP 1 End state 14-15 | QIPP 2 End state 14-15 | QIPP 2 End state 14-15 | QIPP 3 End state 14-15 | QIPP 3 End state 14-15 | QIPP 4 End state 14-15 | QIPP 4 End state 14-15 | QIPP 5 End state 14-15 | QIPP 5 End state 14-15 | QIPP 6 End state 14-15 | QIPP 6 End state 14-15 | QIPP 7 End state 14-15 | QIPP 7 End state 14-15 | QIPP 8 End state 14-15 | QIPP 8 End state 14-15 | QIPP 9 End state 14-15 | QIPP 9 End state 14-15 | FTs NME 2 | FTs NME 2 end | 2012-02-28 | Workforce | PCT cluster | Acute Contracts (Non Elective) | Integrated care | Primary care productivity | Green | Delayed - amber | NHS North of England | Devon & Torbay |  | 2
SHA CS NME 3 | SHA CS NME 3 end | SHA CCG NME 3 | SHA CCG NME 3 end | SHA DC NME 3 | SHA DC NME 3 end | SHA AQP NME 3 | SHA AQP NME 3 end | SHA HWB NME 3 | SHA HWB NME 3 end | SHA PHT LAs NME 3 | SHA PHT LAs NME 3 end | SHA PHT PHE NME 3 | SHA PHT PHE NME 3 end | PCT CS NME 3 | PCT CS NME 3 end | PCT CCG NME 3 | PCT CCG NME 3 end | PCT DC NME 3 | PCT DC NME 3 end | PCT AQP NME 3 | PCT AQP NME 3 end | PCT HWB NME 3 | PCT HWB NME 3 end | PCT PHT LAs NME 3 | PCT PHT LAs NME 3 end | PCT PHT PHE NME 3 | PCT PHT PHE NME 3 end | QIPP LM 1.1 | QIPP LM 1.1 end | QIPP LM 2.1 | QIPP LM 2.1 end | QIPP LM 3.1 | QIPP LM 3.1 end | QIPP LM 4.1 | QIPP LM 4.1 end | QIPP LM 5.1 | QIPP LM 5.1 end | QIPP LM 6.1 | QIPP LM 6.1 end | QIPP LM 7.1 | QIPP LM 7.1 end | QIPP LM 8.1 | QIPP LM 8.1 end | QIPP LM 9.1 | QIPP LM 9.1 end | FTs NME 3 | FTs NME 3 end | 2012-03-31 | Finance | Pan SHA | Acute Contracts (Outpatients) | Procurement | Community support services | No rating | Delayed - red | NHS South of England | Gloucestershire (& Swindon) |  | 3
SHA CS NME 4 | SHA CS NME 4 end | SHA CCG NME 4 | SHA CCG NME 4 end | SHA DC NME 4 | SHA DC NME 4 end | SHA AQP NME 4 | SHA AQP NME 4 end | SHA HWB NME 4 | SHA HWB NME 4 end | SHA PHT LAs NME 4 | SHA PHT LAs NME 4 end | SHA PHT PHE NME 4 | SHA PHT PHE NME 4 end | PCT CS NME 4 | PCT CS NME 4 end | PCT CCG NME 4 | PCT CCG NME 4 end | PCT DC NME 4 | PCT DC NME 4 end | PCT AQP NME 4 | PCT AQP NME 4 end | PCT HWB NME 4 | PCT HWB NME 4 end | PCT PHT LAs NME 4 | PCT PHT LAs NME 4 end | PCT PHT PHE NME 4 | PCT PHT PHE NME 4 end | QIPP LM 1.2 | QIPP LM 1.2 end | QIPP LM 2.2 | QIPP LM 2.2 end | QIPP LM 3.2 | QIPP LM 3.2 end | QIPP LM 4.2 | QIPP LM 4.2 end | QIPP LM 5.2 | QIPP LM 5.2 end | QIPP LM 6.2 | QIPP LM 6.2 end | QIPP LM 7.2 | QIPP LM 7.2 end | QIPP LM 8.2 | QIPP LM 8.2 end | QIPP LM 9.2 | QIPP LM 9.2 end | FTs NME 4 | FTs NME 4 end | 2012-04-30 | Quality & activity | SHA Cluster | Acute Contracts (Direct Access) | Demand management | Activity shifts |  | Work not yet commenced |  | Swindon (& Gloucestershire) |  | 4
SHA CS NME 5 | SHA CS NME 5 end | SHA CCG NME 5 | SHA CCG NME 5 end | SHA DC NME 5 | SHA DC NME 5 end | SHA AQP NME 5 | SHA AQP NME 5 end | SHA HWB NME 5 | SHA HWB NME 5 end | SHA PHT LAs NME 5 | SHA PHT LAs NME 5 end | SHA PHT PHE NME 5 | SHA PHT PHE NME 5 end | PCT CS NME 5 | PCT CS NME 5 end | PCT CCG NME 5 | PCT CCG NME 5 end | PCT DC NME 5 | PCT DC NME 5 end | PCT AQP NME 5 | PCT AQP NME 5 end | PCT HWB NME 5 | PCT HWB NME 5 end | PCT PHT LAs NME 5 | PCT PHT LAs NME 5 end | PCT PHT PHE NME 5 | PCT PHT PHE NME 5 end | QIPP LM 1.3 | QIPP LM 1.3 end | QIPP LM 2.3 | QIPP LM 2.3 end | QIPP LM 3.3 | QIPP LM 3.3 end | QIPP LM 4.3 | QIPP LM 4.3 end | QIPP LM 5.3 | QIPP LM 5.3 end | QIPP LM 6.3 | QIPP LM 6.3 end | QIPP LM 7.3 | QIPP LM 7.3 end | QIPP LM 8.3 | QIPP LM 8.3 end | QIPP LM 9.3 | QIPP LM 9.3 end | FTs NME 5 | FTs NME 5 end | 2012-05-31 | Quality & workforce |  | Acute Contracts (Other) | Running costs | Long Term Conditions |  |  |  | Bath NE Somerset & Wiltshire |  | 5
SHA CS NME 6 | SHA CS NME 6 end | SHA CCG NME 6 | SHA CCG NME 6 end | SHA DC NME 6 | SHA DC NME 6 end | SHA AQP NME 6 | SHA AQP NME 6 end | SHA HWB NME 6 | SHA HWB NME 6 end | SHA PHT LAs NME 6 | SHA PHT LAs NME 6 end | SHA PHT PHE NME 6 | SHA PHT PHE NME 6 end | PCT CS NME 6 | PCT CS NME 6 end | PCT CCG NME 6 | PCT CCG NME 6 end | PCT DC NME 6 | PCT DC NME 6 end | PCT AQP NME 6 | PCT AQP NME 6 end | PCT HWB NME 6 | PCT HWB NME 6 end | PCT PHT LAs NME 6 | PCT PHT LAs NME 6 end | PCT PHT PHE NME 6 | PCT PHT PHE NME 6 end | QIPP LM 1.4 | QIPP LM 1.4 end | QIPP LM 2.4 | QIPP LM 2.4 end | QIPP LM 3.4 | QIPP LM 3.4 end | QIPP LM 4.4 | QIPP LM 4.4 end | QIPP LM 5.4 | QIPP LM 5.4 end | QIPP LM 6.4 | QIPP LM 6.4 end | QIPP LM 7.4 | QIPP LM 7.4 end | QIPP LM 8.4 | QIPP LM 8.4 end | QIPP LM 9.4 | QIPP LM 9.4 end | FTs NME 6 | FTs NME 6 end | 2012-06-30 | Quality & finance |  | Mental Health & Learning Disabilities Contracts | Clinical overheads | Urgent Care |  |  |  | Cornwall & Isle of Scilly |  | 6
SHA CS NME 7 | SHA CS NME 7 end | SHA CCG NME 7 | SHA CCG NME 7 end | SHA DC NME 7 | SHA DC NME 7 end | SHA AQP NME 7 | SHA AQP NME 7 end | SHA HWB NME 7 | SHA HWB NME 7 end | SHA PHT LAs NME 7 | SHA PHT LAs NME 7 end | SHA PHT PHE NME 7 | SHA PHT PHE NME 7 end | PCT CS NME 7 | PCT CS NME 7 end | PCT CCG NME 7 | PCT CCG NME 7 end | PCT DC NME 7 | PCT DC NME 7 end | PCT AQP NME 7 | PCT AQP NME 7 end | PCT HWB NME 7 | PCT HWB NME 7 end | PCT PHT LAs NME 7 | PCT PHT LAs NME 7 end | PCT PHT PHE NME 7 | PCT PHT PHE NME 7 end | QIPP LM 1.5 | QIPP LM 1.5 end | QIPP LM 2.5 | QIPP LM 2.5 end | QIPP LM 3.5 | QIPP LM 3.5 end | QIPP LM 4.5 | QIPP LM 4.5 end | QIPP LM 5.5 | QIPP LM 5.5 end | QIPP LM 6.5 | QIPP LM 6.5 end | QIPP LM 7.5 | QIPP LM 7.5 end | QIPP LM 8.5 | QIPP LM 8.5 end | QIPP LM 9.5 | QIPP LM 9.5 end | FTs NME 7 | FTs NME 7 end | 2012-07-31 | Activity & Workforce |  | Community Contracts | Reducing drug spend | Planned Care |  |  |  | Somerset |  | 7
SHA CS NME 8 | SHA CS NME 8 end | SHA CCG NME 8 | SHA CCG NME 8 end | SHA DC NME 8 | SHA DC NME 8 end | SHA AQP NME 8 | SHA AQP NME 8 end | SHA HWB NME 8 | SHA HWB NME 8 end | SHA PHT LAs NME 8 | SHA PHT LAs NME 8 end | SHA PHT PHE NME 8 | SHA PHT PHE NME 8 end | PCT CS NME 8 | PCT CS NME 8 end | PCT CCG NME 8 | PCT CCG NME 8 end | PCT DC NME 8 | PCT DC NME 8 end | PCT AQP NME 8 | PCT AQP NME 8 end | PCT HWB NME 8 | PCT HWB NME 8 end | PCT PHT LAs NME 8 | PCT PHT LAs NME 8 end | PCT PHT PHE NME 8 | PCT PHT PHE NME 8 end | QIPP LM 1.6 | QIPP LM 1.6 end | QIPP LM 2.6 | QIPP LM 2.6 end | QIPP LM 3.6 | QIPP LM 3.6 end | QIPP LM 4.6 | QIPP LM 4.6 end | QIPP LM 5.6 | QIPP LM 5.6 end | QIPP LM 6.6 | QIPP LM 6.6 end | QIPP LM 7.6 | QIPP LM 7.6 end | QIPP LM 8.6 | QIPP LM 8.6 end | QIPP LM 9.6 | QIPP LM 9.6 end | FTs NME 8 | FTs NME 8 end | 2012-08-31 | Activity & finance |  | Ambulance Contracts | Unidentified | End of Life Care |  |  |  | Berkshire |  | 8
SHA CS NME 9 | SHA CS NME 9 end | SHA CCG NME 9 | SHA CCG NME 9 end | SHA DC NME 9 | SHA DC NME 9 end | SHA AQP NME 9 | SHA AQP NME 9 end | SHA HWB NME 9 | SHA HWB NME 9 end | SHA PHT LAs NME 9 | SHA PHT LAs NME 9 end | SHA PHT PHE NME 9 | SHA PHT PHE NME 9 end | PCT CS NME 9 | PCT CS NME 9 end | PCT CCG NME 9 | PCT CCG NME 9 end | PCT DC NME 9 | PCT DC NME 9 end | PCT AQP NME 9 | PCT AQP NME 9 end | PCT HWB NME 9 | PCT HWB NME 9 end | PCT PHT LAs NME 9 | PCT PHT LAs NME 9 end | PCT PHT PHE NME 9 | PCT PHT PHE NME 9 end | QIPP LM 1.7 | QIPP LM 1.7 end | QIPP LM 2.7 | QIPP LM 2.7 end | QIPP LM 3.7 | QIPP LM 3.7 end | QIPP LM 4.7 | QIPP LM 4.7 end | QIPP LM 5.7 | QIPP LM 5.7 end | QIPP LM 6.7 | QIPP LM 6.7 end | QIPP LM 7.7 | QIPP LM 7.7 end | QIPP LM 8.7 | QIPP LM 8.7 end | QIPP LM 9.7 | QIPP LM 9.7 end | FTs NME 9 | FTs NME 9 end | 2012-09-30 | Workforce & finance |  | Specialised Commissioning |  | Prevention |  |  |  | Oxfordshire & Buckinghamshire - Oxford |  | 9
SHA CS NME 10 | SHA CS NME 10 end | SHA CCG NME 10 | SHA CCG NME 10 end | SHA DC NME 10 | SHA DC NME 10 end | SHA AQP NME 10 | SHA AQP NME 10 end | SHA HWB NME 10 | SHA HWB NME 10 end | SHA PHT LAs NME 10 | SHA PHT LAs NME 10 end | SHA PHT PHE NME 10 | SHA PHT PHE NME 10 end | PCT CS NME 10 | PCT CS NME 10 end | PCT CCG NME 10 | PCT CCG NME 10 end | PCT DC NME 10 | PCT DC NME 10 end | PCT AQP NME 10 | PCT AQP NME 10 end | PCT HWB NME 10 | PCT HWB NME 10 end | PCT PHT LAs NME 10 | PCT PHT LAs NME 10 end | PCT PHT PHE NME 10 | PCT PHT PHE NME 10 end | QIPP LM 1.8 | QIPP LM 1.8 end | QIPP LM 2.8 | QIPP LM 2.8 end | QIPP LM 3.8 | QIPP LM 3.8 end | QIPP LM 4.8 | QIPP LM 4.8 end | QIPP LM 5.8 | QIPP LM 5.8 end | QIPP LM 6.8 | QIPP LM 6.8 end | QIPP LM 7.8 | QIPP LM 7.8 end | QIPP LM 8.8 | QIPP LM 8.8 end | QIPP LM 9.8 | QIPP LM 9.8 end | FTs NME 10 | FTs NME 10 end | 2012-10-31 | Quality, activity & finance |  | Non-NHS Healthcare Contracts (inc reablement) |  | Staying Healthy |  |  |  | Oxfordshire & Buckinghamshire - Bucks |  | 10
SHA CS NME 11 | SHA CS NME 11 end | SHA CCG NME 11 | SHA CCG NME 11 end | SHA DC NME 11 | SHA DC NME 11 end | SHA AQP NME 11 | SHA AQP NME 11 end | SHA HWB NME 11 | SHA HWB NME 11 end | SHA PHT LAs NME 11 | SHA PHT LAs NME 11 end | SHA PHT PHE NME 11 | SHA PHT PHE NME 11 end | PCT CS NME 11 | PCT CS NME 11 end | PCT CCG NME 11 | PCT CCG NME 11 end | PCT DC NME 11 | PCT DC NME 11 end | PCT AQP NME 11 | PCT AQP NME 11 end | PCT HWB NME 11 | PCT HWB NME 11 end | PCT PHT LAs NME 11 | PCT PHT LAs NME 11 end | PCT PHT PHE NME 11 | PCT PHT PHE NME 11 end | QIPP LM 1.9 | QIPP LM 1.9 end | QIPP LM 2.9 | QIPP LM 2.9 end | QIPP LM 3.9 | QIPP LM 3.9 end | QIPP LM 4.9 | QIPP LM 4.9 end | QIPP LM 5.9 | QIPP LM 5.9 end | QIPP LM 6.9 | QIPP LM 6.9 end | QIPP LM 7.9 | QIPP LM 7.9 end | QIPP LM 8.9 | QIPP LM 8.9 end | QIPP LM 9.9 | QIPP LM 9.9 end | FTs NME 11 | FTs NME 11 end | 2012-11-30 | Quality, activity & workforce |  | Continuing Healthcare |  | Non Clinical Procurement |  |  |  | SHIP |  | 11
SHA CS NME 12 | SHA CS NME 12 end | SHA CCG NME 12 | SHA CCG NME 12 end | SHA DC NME 12 | SHA DC NME 12 end | SHA AQP NME 12 | SHA AQP NME 12 end | SHA HWB NME 12 | SHA HWB NME 12 end | SHA PHT LAs NME 12 | SHA PHT LAs NME 12 end | SHA PHT PHE NME 12 | SHA PHT PHE NME 12 end | PCT CS NME 12 | PCT CS NME 12 end | PCT CCG NME 12 | PCT CCG NME 12 end | PCT DC NME 12 | PCT DC NME 12 end | PCT AQP NME 12 | PCT AQP NME 12 end | PCT HWB NME 12 | PCT HWB NME 12 end | PCT PHT LAs NME 12 | PCT PHT LAs NME 12 end | PCT PHT PHE NME 12 | PCT PHT PHE NME 12 end | QIPP LM 1.10 | QIPP LM 1.10 end | QIPP LM 2.10 | QIPP LM 2.10 end | QIPP LM 3.10 | QIPP LM 3.10 end | QIPP LM 4.10 | QIPP LM 4.10 end | QIPP LM 5.10 | QIPP LM 5.10 end | QIPP LM 6.10 | QIPP LM 6.10 end | QIPP LM 7.10 | QIPP LM 7.10 end | QIPP LM 8.10 | QIPP LM 8.10 end | QIPP LM 9.10 | QIPP LM 9.10 end | FTs NME 12 | FTs NME 12 end | 2012-12-31 | Quality, activity workforce & finance |  | Primary Care Prescribing |  | Decommissioning ineffective procedures |  |  |  | Surrey |  | 12
SHA CS NME 13 | SHA CS NME 13 end | SHA CCG NME 13 | SHA CCG NME 13 end | SHA DC NME 13 | SHA DC NME 13 end | SHA AQP NME 13 | SHA AQP NME 13 end | SHA HWB NME 13 | SHA HWB NME 13 end | SHA PHT LAs NME 13 | SHA PHT LAs NME 13 end | SHA PHT PHE NME 13 | SHA PHT PHE NME 13 end | PCT CS NME 13 | PCT CS NME 13 end | PCT CCG NME 13 | PCT CCG NME 13 end | PCT DC NME 13 | PCT DC NME 13 end | PCT AQP NME 13 | PCT AQP NME 13 end | PCT HWB NME 13 | PCT HWB NME 13 end | PCT PHT LAs NME 13 | PCT PHT LAs NME 13 end | PCT PHT PHE NME 13 | PCT PHT PHE NME 13 end | QIPP LM 1.11 | QIPP LM 1.11 end | QIPP LM 2.11 | QIPP LM 2.11 end | QIPP LM 3.11 | QIPP LM 3.11 end | QIPP LM 4.11 | QIPP LM 4.11 end | QIPP LM 5.11 | QIPP LM 5.11 end | QIPP LM 6.11 | QIPP LM 6.11 end | QIPP LM 7.11 | QIPP LM 7.11 end | QIPP LM 8.11 | QIPP LM 8.11 end | QIPP LM 9.11 | QIPP LM 9.11 end | FTs NME 13 | FTs NME 13 end | 2013-01-31 | Activity workforce & finance |  | Excluded Drugs & Devices |  | Enhanced recovery |  |  |  | Sussex |  | 13
SHA CS NME 14 | SHA CS NME 14 end | SHA CCG NME 14 | SHA CCG NME 14 end | SHA DC NME 14 | SHA DC NME 14 end | SHA AQP NME 14 | SHA AQP NME 14 end | SHA HWB NME 14 | SHA HWB NME 14 end | SHA PHT LAs NME 14 | SHA PHT LAs NME 14 end | SHA PHT PHE NME 14 | SHA PHT PHE NME 14 end | PCT CS NME 14 | PCT CS NME 14 end | PCT CCG NME 14 | PCT CCG NME 14 end | PCT DC NME 14 | PCT DC NME 14 end | PCT AQP NME 14 | PCT AQP NME 14 end | PCT HWB NME 14 | PCT HWB NME 14 end | PCT PHT LAs NME 14 | PCT PHT LAs NME 14 end | PCT PHT PHE NME 14 | PCT PHT PHE NME 14 end | QIPP LM 1.12 | QIPP LM 1.12 end | QIPP LM 2.12 | QIPP LM 2.12 end | QIPP LM 3.12 | QIPP LM 3.12 end | QIPP LM 4.12 | QIPP LM 4.12 end | QIPP LM 5.12 | QIPP LM 5.12 end | QIPP LM 6.12 | QIPP LM 6.12 end | QIPP LM 7.12 | QIPP LM 7.12 end | QIPP LM 8.12 | QIPP LM 8.12 end | QIPP LM 9.12 | QIPP LM 9.12 end | FTs NME 14 | FTs NME 14 end | 2013-02-28 | Quality workforce & finance |  | Primary Care, Dental, Pharmacy, Opthalmic |  | Referral management |  |  |  | Kent & Medway |  | 14
SHA CS NME 15 | SHA CS NME 15 end | SHA CCG NME 15 | SHA CCG NME 15 end | SHA DC NME 15 | SHA DC NME 15 end | SHA AQP NME 15 | SHA AQP NME 15 end | SHA HWB NME 15 | SHA HWB NME 15 end | SHA PHT LAs NME 15 | SHA PHT LAs NME 15 end | SHA PHT PHE NME 15 | SHA PHT PHE NME 15 end | PCT CS NME 15 | PCT CS NME 15 end | PCT CCG NME 15 | PCT CCG NME 15 end | PCT DC NME 15 | PCT DC NME 15 end | PCT AQP NME 15 | PCT AQP NME 15 end | PCT HWB NME 15 | PCT HWB NME 15 end | PCT PHT LAs NME 15 | PCT PHT LAs NME 15 end | PCT PHT PHE NME 15 | PCT PHT PHE NME 15 end | QIPP LM 1.13 | QIPP LM 1.13 end | QIPP LM 2.13 | QIPP LM 2.13 end | QIPP LM 3.13 | QIPP LM 3.13 end | QIPP LM 4.13 | QIPP LM 4.13 end | QIPP LM 5.13 | QIPP LM 5.13 end | QIPP LM 6.13 | QIPP LM 6.13 end | QIPP LM 7.13 | QIPP LM 7.13 end | QIPP LM 8.13 | QIPP LM 8.13 end | QIPP LM 9.13 | QIPP LM 9.13 end | FTs NME 15 | FTs NME end | 2013-03-31 |  |  | PCT Running Costs |  | Back office |  |  |  | Black Country |  | 15
SHA CS NME 16 | SHA CS NME 16 end | SHA CCG NME 16 | SHA CCG NME 16 end | SHA DC NME 16 | SHA DC NME 16 end | SHA AQP NME 16 | SHA AQP NME 16 end | SHA HWB NME 16 | SHA HWB NME 16 end | SHA PHT LAs NME 16 | SHA PHT LAs NME 16 end | SHA PHT PHE NME 16 | SHA PHT PHE NME 16 end | PCT CS NME 16 | PCT CS NME 16 end | PCT CCG NME 16 | PCT CCG NME 16 end | PCT DC NME 16 | PCT DC NME 16 end | PCT AQP NME 16 | PCT AQP NME 16 end | PCT HWB NME 16 | PCT HWB NME 16 end | PCT PHT LAs NME 16 | PCT PHT LAs NME 16 end | PCT PHT PHE NME 16 | PCT PHT PHE NME 16 end | QIPP LM 1.14 | QIPP LM 1.14 end | QIPP LM 2.14 | QIPP LM 2.14 end | QIPP LM 3.14 | QIPP LM 3.14 end | QIPP LM 4.14 | QIPP LM 4.14 end | QIPP LM 5.14 | QIPP LM 5.14 end | QIPP LM 6.14 | QIPP LM 6.14 end | QIPP LM 7.14 | QIPP LM 7.14 end | QIPP LM 8.14 | QIPP LM 8.14 end | QIPP LM 9.14 | QIPP LM 9.14 end | FTs NME 16 | FTs NME 16 end | 2013-04-30 |  |  | Other |  | Estates |  |  |  | Staffordshire |  | 16
SHA CS NME 17 | SHA CS NME 17 end | SHA CCG NME 17 | SHA CCG NME 17 end | SHA DC NME 17 | SHA DC NME 17 end | SHA AQP NME 17 | SHA AQP NME 17 end | SHA HWB NME 17 | SHA HWB NME 17 end | SHA PHT LAs NME 17 | SHA PHT LAs NME 17 end | SHA PHT PHE NME 17 | SHA PHT PHE NME 17 end | PCT CS NME 17 | PCT CS NME 17 end | PCT CCG NME 17 | PCT CCG NME 17 end | PCT DC NME 17 | PCT DC NME 17 end | PCT AQP NME 17 | PCT AQP NME 17 end | PCT HWB NME 17 | PCT HWB NME 17 end | PCT PHT LAs NME 17 | PCT PHT LAs NME 17 end | PCT PHT PHE NME 17 | PCT PHT PHE NME 17 end | QIPP LM 1.15 | QIPP LM 1.15 end | QIPP LM 2.15 | QIPP LM 2.15 end | QIPP LM 3.15 | QIPP LM 3.15 end | QIPP LM 4.15 | QIPP LM 4.15 end | QIPP LM 5.15 | QIPP LM 5.15 end | QIPP LM 6.15 | QIPP LM 6.15 end | QIPP LM 7.15 | QIPP LM 7.15 end | QIPP LM 8.15 | QIPP LM 8.15 end | QIPP LM 9.15 | QIPP LM 9.15 end | FTs NME 17 | FTs NME 17 end | 2013-05-31 |  |  |  |  | Staffing |  |  |  | West Mercia |  | 17
SHA CS NME 18 | SHA CS NME 18 end | SHA CCG NME 18 | SHA CCG NME 18 end | SHA DC NME 18 | SHA DC NME 18 end | SHA AQP NME 18 | SHA AQP NME 18 end | SHA HWB NME 18 | SHA HWB NME 18 end | SHA PHT LAs NME 18 | SHA PHT LAs NME 18 end | SHA PHT PHE NME 18 | SHA PHT PHE NME 18 end | PCT CS NME 18 | PCT CS NME 18 end | PCT CCG NME 18 | PCT CCG NME 18 end | PCT DC NME 18 | PCT DC NME 18 end | PCT AQP NME 18 | PCT AQP NME 18 end | PCT HWB NME 18 | PCT HWB NME 18 end | PCT PHT LAs NME 18 | PCT PHT LAs NME 18 end | PCT PHT PHE NME 18 | PCT PHT PHE NME 18 end | QIPP LM 1.16 | QIPP LM 1.16 end | QIPP LM 2.16 | QIPP LM 2.16 end | QIPP LM 3.16 | QIPP LM 3.16 end | QIPP LM 4.16 | QIPP LM 4.16 end | QIPP LM 5.16 | QIPP LM 5.16 end | QIPP LM 6.16 | QIPP LM 6.16 end | QIPP LM 7.16 | QIPP LM 7.16 end | QIPP LM 8.16 | QIPP LM 8.16 end | QIPP LM 9.16 | QIPP LM 9.16 end | FTs NME 18 | FTs NME 18 end | 2013-06-30 |  |  |  |  | Clinical support rationalisation |  |  |  | Arden |  | 18
SHA CS NME 19 | SHA CS NME 19 end | SHA CCG NME 19 | SHA CCG NME 19 end | SHA DC NME 19 | SHA DC NME 19 end | SHA AQP NME 19 | SHA AQP NME 19 end | SHA HWB NME 19 | SHA HWB NME 19 end | SHA PHT LAs NME 19 | SHA PHT LAs NME 19 end | SHA PHT PHE NME 19 | SHA PHT PHE NME 19 end | PCT CS NME 19 | PCT CS NME 19 end | PCT CCG NME 19 | PCT CCG NME 19 end | PCT DC NME 19 | PCT DC NME 19 end | PCT AQP NME 19 | PCT AQP NME 19 end | PCT HWB NME 19 | PCT HWB NME 19 end | PCT PHT LAs NME 19 | PCT PHT LAs NME 19 end | PCT PHT PHE NME 19 | PCT PHT PHE NME 19 end | QIPP LM 1.17 | QIPP LM 1.17 end | QIPP LM 2.17 | QIPP LM 2.17 end | QIPP LM 3.17 | QIPP LM 3.17 end | QIPP LM 4.17 | QIPP LM 4.17 end | QIPP LM 5.17 | QIPP LM 5.17 end | QIPP LM 6.17 | QIPP LM 6.17 end | QIPP LM 7.17 | QIPP LM 7.17 end | QIPP LM 8.17 | QIPP LM 8.17 end | QIPP LM 9.17 | QIPP LM 9.17 end | FTs NME 19 | FTs NME 19 end | 2013-07-31 |  |  |  |  | Diagnostics |  |  |  | Birmingham and Solihull |  | 19
SHA CS NME 20 | SHA CS NME 20 end | SHA CCG NME 20 | SHA CCG NME 20 end | SHA DC NME 20 | SHA DC NME 20 end | SHA AQP NME 20 | SHA AQP NME 20 end | SHA HWB NME 20 | SHA HWB NME 20 end | SHA PHT LAs NME 20 | SHA PHT LAs NME 20 end | SHA PHT PHE NME 20 | SHA PHT PHE NME 20 end | PCT CS NME 20 | PCT CS NME 20 end | PCT CCG NME 20 | PCT CCG NME 20 end | PCT DC NME 20 | PCT DC NME 20 end | PCT AQP NME 20 | PCT AQP NME 20 end | PCT HWB NME 20 | PCT HWB NME 20 end | PCT PHT LAs NME 20 | PCT PHT LAs NME 20 end | PCT PHT PHE NME 20 | PCT PHT PHE NME 20 end | QIPP LM 1.18 | QIPP LM 1.18 end | QIPP LM 2.18 | QIPP LM 2.18 end | QIPP LM 3.18 | QIPP LM 3.18 end | QIPP LM 4.18 | QIPP LM 4.18 end | QIPP LM 5.18 | QIPP LM 5.18 end | QIPP LM 6.18 | QIPP LM 6.18 end | QIPP LM 7.18 | QIPP LM 7.18 end | QIPP LM 8.18 | QIPP LM 8.18 end | QIPP LM 9.18 | QIPP LM 9.18 end | FTs NME 20 | FTs NME 20 end | 2013-08-31 |  |  |  |  | Direct access |  |  |  | Northamptonshire and Milton Keynes |  | 20
SHA CS NME 21 | SHA CS NME 21 end | SHA CCG NME 21 | SHA CCG NME 21 end | SHA DC NME 21 | SHA DC NME 21 end | SHA AQP NME 21 | SHA AQP NME 21 end | SHA HWB NME 21 | SHA HWB NME 21 end | SHA PHT LAs NME 21 | SHA PHT LAs NME 21 end | SHA PHT PHE NME 21 | SHA PHT PHE NME 21 end | PCT CS NME 21 | PCT CS NME 21 end | PCT CCG NME 21 | PCT CCG NME 21 end | PCT DC NME 21 | PCT DC NME 21 end | PCT AQP NME 21 | PCT AQP NME 21 end | PCT HWB NME 21 | PCT HWB NME 21 end | PCT PHT LAs NME 21 | PCT PHT LAs NME 21 end | PCT PHT PHE NME 21 | PCT PHT PHE NME 21 end | QIPP LM 1.19 | QIPP LM 1.19 end | QIPP LM 2.19 | QIPP LM 2.19 end | QIPP LM 3.19 | QIPP LM 3.19 end | QIPP LM 4.19 | QIPP LM 4.19 end | QIPP LM 5.19 | QIPP LM 5.19 end | QIPP LM 6.19 | QIPP LM 6.19 end | QIPP LM 7.19 | QIPP LM 7.19 end | QIPP LM 8.19 | QIPP LM 8.19 end | QIPP LM 9.19 | QIPP LM 9.19 end | FTs NME 21 | FTs NME 21 end | 2013-09-30 |  |  |  |  | Medicines use |  |  |  | Nottinghamshire |  | 21
SHA CS NME 22 | SHA CS NME 22 end | SHA CCG NME 22 | SHA CCG NME 22 end | SHA DC NME 22 | SHA DC NME 22 end | SHA AQP NME 22 | SHA AQP NME 22 end | SHA HWB NME 22 | SHA HWB NME 22 end | SHA PHT LAs NME 22 | SHA PHT LAs NME 22 end | SHA PHT PHE NME 22 | SHA PHT PHE NME 22 end | PCT CS NME 22 | PCT CS NME 22 end | PCT CCG NME 22 | PCT CCG NME 22 end | PCT DC NME 22 | PCT DC NME 22 end | PCT AQP NME 22 | PCT AQP NME 22 end | PCT HWB NME 22 | PCT HWB NME 22 end | PCT PHT LAs NME 22 | PCT PHT LAs NME 22 end | PCT PHT PHE NME 22 | PCT PHT PHE NME 22 end | QIPP LM 1.20 | QIPP LM 1.20 end | QIPP LM 2.20 | QIPP LM 2.20 end | QIPP LM 3.20 | QIPP LM 3.20 end | QIPP LM 4.20 | QIPP LM 4.20 end | QIPP LM 5.20 | QIPP LM 5.20 end | QIPP LM 6.20 | QIPP LM 6.20 end | QIPP LM 7.20 | QIPP LM 7.20 end | QIPP LM 8.20 | QIPP LM 8.20 end | QIPP LM 9.20 | QIPP LM 9.20 end | FTs NME 22 | FTs NME 22 end | 2013-10-31 |  |  |  |  | Prescribing |  |  |  | Leicestershire |  | 22
SHA CS NME 23 | SHA CS NME 23 end | SHA CCG NME 23 | SHA CCG NME 23 end | SHA DC NME 23 | SHA DC NME 23 end | SHA AQP NME 23 | SHA AQP NME 23 end | SHA HWB NME 23 | SHA HWB NME 23 end | SHA PHT LAs NME 23 | SHA PHT LAs NME 23 end | SHA PHT PHE NME 23 | SHA PHT PHE NME 23 end | PCT CS NME 23 | PCT CS NME 23 end | PCT CCG NME 23 | PCT CCG NME 23 end | PCT DC NME 23 | PCT DC NME 23 end | PCT AQP NME 23 | PCT AQP NME 23 end | PCT HWB NME 23 | PCT HWB NME 23 end | PCT PHT LAs NME 23 | PCT PHT LAs NME 23 end | PCT PHT PHE NME 23 | PCT PHT PHE NME 23 end | QIPP LM 1.21 | QIPP LM 1.21 end | QIPP LM 2.21 | QIPP LM 2.21 end | QIPP LM 3.21 | QIPP LM 3.21 end | QIPP LM 4.21 | QIPP LM 4.21 end | QIPP LM 5.21 | QIPP LM 5.21 end | QIPP LM 6.21 | QIPP LM 6.21 end | QIPP LM 7.21 | QIPP LM 7.21 end | QIPP LM 8.21 | QIPP LM 8.21 end | QIPP LM 9.21 | QIPP LM 9.21 end | FTs NME 23 | FTs NME 23 end | 2013-11-30 |  |  |  |  | Unidentified |  |  |  | Derbyshire |  | 23
SHA CS NME 24 | SHA CS NME 24 end | SHA CCG NME 24 | SHA CCG NME 24 end | SHA DC NME 24 | SHA DC NME 24 end | SHA AQP NME 24 | SHA AQP NME 24 end | SHA HWB NME 24 | SHA HWB NME 24 end | SHA PHT LAs NME 24 | SHA PHT LAs NME 24 end | SHA PHT PHE NME 24 | SHA PHT PHE NME 24 end | PCT CS NME 24 | PCT CS NME 24 end | PCT CCG NME 24 | PCT CCG NME 24 end | PCT DC NME 24 | PCT DC NME 24 end | PCT AQP NME 24 | PCT AQP NME 24 end | PCT HWB NME 24 | PCT HWB NME 24 end | PCT PHT LAs NME 24 | PCT PHT LAs NME 24 end | PCT PHT PHE NME 24 | PCT PHT PHE NME 24 end | QIPP LM 1.22 | QIPP LM 1.22 end | QIPP LM 2.22 | QIPP LM 2.22 end | QIPP LM 3.22 | QIPP LM 3.22 end | QIPP LM 4.22 | QIPP LM 4.22 end | QIPP LM 5.22 | QIPP LM 5.22 end | QIPP LM 6.22 | QIPP LM 6.22 end | QIPP LM 7.22 | QIPP LM 7.22 end | QIPP LM 8.22 | QIPP LM 8.22 end | QIPP LM 9.22 | QIPP LM 9.22 end | FTs NME 24 | FTs NME 24 end | 2013-12-31 | [8 empty] | Lincolnshire |  | 24
SHA CS NME 25 | SHA CS NME 25 end | SHA CCG NME 25 | SHA CCG NME 25 end | SHA DC NME 25 | SHA DC NME 25 end | SHA AQP NME 25 | SHA AQP NME 25 end | SHA HWB NME 25 | SHA HWB NME 25 end | SHA PHT LAs NME 25 | SHA PHT LAs NME 25 end | SHA PHT PHE NME 25 | SHA PHT PHE NME 25 end | PCT CS NME 25 | PCT CS NME 25 end | PCT CCG NME 25 | PCT CCG NME 25 end | PCT DC NME 25 | PCT DC NME 25 end | PCT AQP NME 25 | PCT AQP NME 25 end | PCT HWB NME 25 | PCT HWB NME 25 end | PCT PHT LAs NME 25 | PCT PHT LAs NME 25 end | PCT PHT PHE NME 25 | PCT PHT PHE NME 25 end | QIPP LM 1.23 | QIPP LM 1.23 end | QIPP LM 2.23 | QIPP LM 2.23 end | QIPP LM 3.23 | QIPP LM 3.23 end | QIPP LM 4.23 | QIPP LM 4.23 end | QIPP LM 5.23 | QIPP LM 5.23 end | QIPP LM 6.23 | QIPP LM 6.23 end | QIPP LM 7.23 | QIPP LM 7.23 end | QIPP LM 8.23 | QIPP LM 8.23 end | QIPP LM 9.23 | QIPP LM 9.23 end | FTs NME 25 | FTs NME 25 end | 2014-01-31 | [8 empty] | North East Essex |  | 25
SHA CS LMS 1 | SHA CS LMS 1 end | SHA CCG LMS 1 | SHA CCG LMS 1 end | SHA DC LMS 1 | SHA DC LMS 1 end | SHA AQP LMS 1 | SHA AQP LMS 1 end | SHA HWB LMS 1 | SHA HWB LMS 1 end | SHA PHT LAs LMS 1 | SHA PHT LAs LMS 1 end | SHA PHT PHE LMS 1 | SHA PHT PHE LMS 1 end | PCT CS LMS 1 | PCT CS LMS 1 end | PCT CCG LMS 1 | PCT CCG LMS 1 end | PCT DC LMS 1 | PCT DC LMS 1 end | PCT AQP LMS 1 | PCT AQP LMS 1 end | PCT HWB LMS 1 | PCT HWB LMS 1 end | PCT PHT LAs LMS 1 | PCT PHT LAs LMS 1 end | PCT PHT PHE LMS 1 | PCT PHT PHE LMS 1 end | QIPP LM 1.24 | QIPP LM 1.24 end | QIPP LM 2.24 | QIPP LM 2.24 end | QIPP LM 3.24 | QIPP LM 3.24 end | QIPP LM 4.24 | QIPP LM 4.24 end | QIPP LM 5.24 | QIPP LM 5.24 end | QIPP LM 6.24 | QIPP LM 6.24 end | QIPP LM 7.24 | QIPP LM 7.24 end | QIPP LM 8.24 | QIPP LM 8.24 end | QIPP LM 9.24 | QIPP LM 9.24 end | FTs LMS 1 | FTs LMS 1 end | 2014-02-28 | [8 empty] | South Essex |  | 26
SHA CS LMS 2 | SHA CS LMS 2 end | SHA CCG LMS 2 | SHA CCG LMS 2 end | SHA DC LMS 2 | SHA DC LMS 2 end | SHA AQP LMS 2 | SHA AQP LMS 2 end | SHA HWB LMS 2 | SHA HWB LMS 2 end | SHA PHT LAs LMS 2 | SHA PHT LAs LMS 2 end | SHA PHT PHE LMS 2 | SHA PHT PHE LMS 2 end | PCT CS LMS 2 | PCT CS LMS 2 end | PCT CCG LMS 2 | PCT CCG LMS 2 end | PCT DC LMS 2 | PCT DC LMS 2 end | PCT AQP LMS 2 | PCT AQP LMS 2 end | PCT HWB LMS 2 | PCT HWB LMS 2 end | PCT PHT LAs LMS 2 | PCT PHT LAs LMS 2 end | PCT PHT PHE LMS 2 | PCT PHT PHE LMS 2 end | QIPP LM 1.25 | QIPP LM 1.25 end | QIPP LM 2.25 | QIPP LM 2.25 end | QIPP LM 3.25 | QIPP LM 3.25 end | QIPP LM 4.25 | QIPP LM 4.25 end | QIPP LM 5.25 | QIPP LM 5.25 end | QIPP LM 6.25 | QIPP LM 6.25 end | QIPP LM 7.25 | QIPP LM 7.25 end | QIPP LM 8.25 | QIPP LM 8.25 end | QIPP LM 9.25 | QIPP LM 9.25 end | FTs LMS 2 | FTs LMS 2 end | 2014-03-31 | [8 empty] | Bedfordshire and Luton |  | 27
SHA CS LMS 3 | SHA CS LMS 3 end | SHA CCG LMS 3 | SHA CCG LMS 3 end | SHA DC LMS 3 | SHA DC LMS 3 end | SHA AQP LMS 3 | SHA AQP LMS 3 end | SHA HWB LMS 3 | SHA HWB LMS 3 end | SHA PHT LAs LMS 3 | SHA PHT LAs LMS 3 end | SHA PHT PHE LMS 3 | SHA PHT PHE LMS 3 end | PCT CS LMS 3 | PCT CS LMS 3 end | PCT CCG LMS 3 | PCT CCG LMS 3 end | PCT DC LMS 3 | PCT DC LMS 3 end | PCT AQP LMS 3 | PCT AQP LMS 3 end | PCT HWB LMS 3 | PCT HWB LMS 3 end | PCT PHT LAs LMS 3 | PCT PHT LAs LMS 3 end | PCT PHT PHE LMS 3 | PCT PHT PHE LMS 3 end | QIPP LM 1.26 | QIPP LM 1.26 end | QIPP LM 2.26 | QIPP LM 2.26 end | QIPP LM 3.26 | QIPP LM 3.26 end | QIPP LM 4.26 | QIPP LM 4.26 end | QIPP LM 5.26 | QIPP LM 5.26 end | QIPP LM 6.26 | QIPP LM 6.26 end | QIPP LM 7.26 | QIPP LM 7.26 end | QIPP LM 8.26 | QIPP LM 8.26 end | QIPP LM 9.26 | QIPP LM 9.26 end | FTs LMS 3 | FTs LMS 3 end | 2014-04-30 | [8 empty] | Cambridgeshire & Peterborough |  | 28
SHA CS LMS 4 | SHA CS LMS 4 end | SHA CCG LMS 4 | SHA CCG LMS 4 end | SHA DC LMS 4 | SHA DC LMS 4 end | SHA AQP LMS 4 | SHA AQP LMS 4 end | SHA HWB LMS 4 | SHA HWB LMS 4 end | SHA PHT LAs LMS 4 | SHA PHT LAs LMS 4 end | SHA PHT PHE LMS 4 | SHA PHT PHE LMS 4 end | PCT CS LMS 4 | PCT CS LMS 4 end | PCT CCG LMS 4 | PCT CCG LMS 4 end | PCT DC LMS 4 | PCT DC LMS 4 end | PCT AQP LMS 4 | PCT AQP LMS 4 end | PCT HWB LMS 4 | PCT HWB LMS 4 end | PCT PHT LAs LMS 4 | PCT PHT LAs LMS 4 end | PCT PHT PHE LMS 4 | PCT PHT PHE LMS 4 end | QIPP LM 1.27 | QIPP LM 1.27 end | QIPP LM 2.27 | QIPP LM 2.27 end | QIPP LM 3.27 | QIPP LM 3.27 end | QIPP LM 4.27 | QIPP LM 4.27 end | QIPP LM 5.27 | QIPP LM 5.27 end | QIPP LM 6.27 | QIPP LM 6.27 end | QIPP LM 7.27 | QIPP LM 7.27 end | QIPP LM 8.27 | QIPP LM 8.27 end | QIPP LM 9.27 | QIPP LM 9.27 end | FTs LMS 4 | FTs LMS 4 end | 2014-05-31 | [8 empty] | Hertfordshire |  | 29
SHA CS LMS 5 | SHA CS LMS 5 end | SHA CCG LMS 5 | SHA CCG LMS 5 end | SHA DC LMS 5 | SHA DC LMS 5 end | SHA AQP LMS 5 | SHA AQP LMS 5 end | SHA HWB LMS 5 | SHA HWB LMS 5 end | SHA PHT LAs LMS 5 | SHA PHT LAs LMS 5 end | SHA PHT PHE LMS 5 | SHA PHT PHE LMS 5 end | PCT CS LMS 5 | PCT CS LMS 5 end | PCT CCG LMS 5 | PCT CCG LMS 5 end | PCT DC LMS 5 | PCT DC LMS 5 end | PCT AQP LMS 5 | PCT AQP LMS 5 end | PCT HWB LMS 5 | PCT HWB LMS 5 end | PCT PHT LAs LMS 5 | PCT PHT LAs LMS 5 end | PCT PHT PHE LMS 5 | PCT PHT PHE LMS 5 end | QIPP LM 1.28 | QIPP LM 1.28 end | QIPP LM 2.28 | QIPP LM 2.28 end | QIPP LM 3.28 | QIPP LM 3.28 end | QIPP LM 4.28 | QIPP LM 4.28 end | QIPP LM 5.28 | QIPP LM 5.28 end | QIPP LM 6.28 | QIPP LM 6.28 end | QIPP LM 7.28 | QIPP LM 7.28 end | QIPP LM 8.28 | QIPP LM 8.28 end | QIPP LM 9.28 | QIPP LM 9.28 end | FTs LMS 5 | FTs LMS 5 end | 2014-06-30 | [8 empty] | Suffolk |  | 30
SHA CS LMS 6 | SHA CS LMS 6 end | SHA CCG LMS 6 | SHA CCG LMS 6 end | SHA DC LMS 6 | SHA DC LMS 6 end | SHA AQP LMS 6 | SHA AQP LMS 6 end | SHA HWB LMS 6 | SHA HWB LMS 6 end | SHA PHT LAs LMS 6 | SHA PHT LAs LMS 6 end | SHA PHT PHE LMS 6 | SHA PHT PHE LMS 6 end | PCT CS LMS 6 | PCT CS LMS 6 end | PCT CCG LMS 6 | PCT CCG LMS 6 end | PCT DC LMS 6 | PCT DC LMS 6 end | PCT AQP LMS 6 | PCT AQP LMS 6 end | PCT HWB LMS 6 | PCT HWB LMS 6 end | PCT PHT LAs LMS 6 | PCT PHT LAs LMS 6 end | PCT PHT PHE LMS 6 | PCT PHT PHE LMS 6 end | QIPP LM 1.29 | QIPP LM 1.29 end | QIPP LM 2.29 | QIPP LM 2.29 end | QIPP LM 3.29 | QIPP LM 3.29 end | QIPP LM 4.29 | QIPP LM 4.29 end | QIPP LM 5.29 | QIPP LM 5.29 end | QIPP LM 6.29 | QIPP LM 6.29 end | QIPP LM 7.29 | QIPP LM 7.29 end | QIPP LM 8.29 | QIPP LM 8.29 end | QIPP LM 9.29 | QIPP LM 9.29 end | FTs LMS 6 | FTs LMS 6 end | 2014-07-31 | [8 empty] | Norfolk, Greater Yarmouth & Waveney |  | 31
SHA CS LMS 7 | SHA CS LMS 7 end | SHA CCG LMS 7 | SHA CCG LMS 7 end | SHA DC LMS 7 | SHA DC LMS 7 end | SHA AQP LMS 7 | SHA AQP LMS 7 end | SHA HWB LMS 7 | SHA HWB LMS 7 end | SHA PHT LAs LMS 7 | SHA PHT LAs LMS 7 end | SHA PHT PHE LMS 7 | SHA PHT PHE LMS 7 end | PCT CS LMS 7 | PCT CS LMS 7 end | PCT CCG LMS 7 | PCT CCG LMS 7 end | PCT DC LMS 7 | PCT DC LMS 7 end | PCT AQP LMS 7 | PCT AQP LMS 7 end | PCT HWB LMS 7 | PCT HWB LMS 7 end | PCT PHT LAs LMS 7 | PCT PHT LAs LMS 7 end | PCT PHT PHE LMS 7 | PCT PHT PHE LMS 7 end | QIPP LM 1.30 | QIPP LM 1.30 end | QIPP LM 2.30 | QIPP LM 2.30 end | QIPP LM 3.30 | QIPP LM 3.30 end | QIPP LM 4.30 | QIPP LM 4.30 end | QIPP LM 5.30 | QIPP LM 5.30 end | QIPP LM 6.30 | QIPP LM 6.30 end | QIPP LM 7.30 | QIPP LM 7.30 end | QIPP LM 8.30 | QIPP LM 8.30 end | QIPP LM 9.30 | QIPP LM 9.30 end | FTs LMS 7 | FTs LMS 7 end | 2014-08-31 | [8 empty] | Inner North East London |  | 32
SHA CS LMS 8 | SHA CS LMS 8 end | SHA CCG LMS 8 | SHA CCG LMS 8 end | SHA DC LMS 8 | SHA DC LMS 8 end | SHA AQP LMS 8 | SHA AQP LMS 8 end | SHA HWB LMS 8 | SHA HWB LMS 8 end | SHA PHT LAs LMS 8 | SHA PHT LAs LMS 8 end | SHA PHT PHE LMS 8 | SHA PHT PHE LMS 8 end | PCT CS LMS 8 | PCT CS LMS 8 end | PCT CCG LMS 8 | PCT CCG LMS 8 end | PCT DC LMS 8 | PCT DC LMS 8 end | PCT AQP LMS 8 | PCT AQP LMS 8 end | PCT HWB LMS 8 | PCT HWB LMS 8 end | PCT PHT LAs LMS 8 | PCT PHT LAs LMS 8 end | PCT PHT PHE LMS 8 | PCT PHT PHE LMS 8 end | QIPP LM 1.31 | QIPP LM 1.31 end | QIPP LM 2.31 | QIPP LM 2.31 end | QIPP LM 3.31 | QIPP LM 3.31 end | QIPP LM 4.31 | QIPP LM 4.31 end | QIPP LM 5.31 | QIPP LM 5.31 end | QIPP LM 6.31 | QIPP LM 6.31 end | QIPP LM 7.31 | QIPP LM 7.31 end | QIPP LM 8.31 | QIPP LM 8.31 end | QIPP LM 9.31 | QIPP LM 9.31 end | FTs LMS 8 | FTs LMS 8 end | 2014-09-30 | [8 empty] | Outer North East London |  | 33
SHA CS LMS 9 | SHA CS LMS 9 end | SHA CCG LMS 9 | SHA CCG LMS 9 end | SHA DC LMS 9 | SHA DC LMS 9 end | SHA AQP LMS 9 | SHA AQP LMS 9 end | SHA HWB LMS 9 | SHA HWB LMS 9 end | SHA PHT LAs LMS 9 | SHA PHT LAs LMS 9 end | SHA PHT PHE LMS 9 | SHA PHT PHE LMS 9 end | PCT CS LMS 9 | PCT CS LMS 9 end | PCT CCG LMS 9 | PCT CCG LMS 9 end | PCT DC LMS 9 | PCT DC LMS 9 end | PCT AQP LMS 9 | PCT AQP LMS 9 end | PCT HWB LMS 9 | PCT HWB LMS 9 end | PCT PHT LAs LMS 9 | PCT PHT LAs LMS 9 end | PCT PHT PHE LMS 9 | PCT PHT PHE LMS 9 end | QIPP LM 1.32 | QIPP LM 1.32 end | QIPP LM 2.32 | QIPP LM 2.32 end | QIPP LM 3.32 | QIPP LM 3.32 end | QIPP LM 4.32 | QIPP LM 4.32 end | QIPP LM 5.32 | QIPP LM 5.32 end | QIPP LM 6.32 | QIPP LM 6.32 end | QIPP LM 7.32 | QIPP LM 7.32 end | QIPP LM 8.32 | QIPP LM 8.32 end | QIPP LM 9.32 | QIPP LM 9.32 end | FTs LMS 9 | FTs LMS 9 end | 2014-10-31 | [8 empty] | North Central London |  | 34
SHA CS LMS 10 | SHA CS LMS 10 end | SHA CCG LMS 10 | SHA CCG LMS 10 end | SHA DC LMS 10 | SHA DC LMS 10 end | SHA AQP LMS 10 | SHA AQP LMS 10 end | SHA HWB LMS 10 | SHA HWB LMS 10 end | SHA PHT LAs LMS 10 | SHA PHT LAs LMS 10 end | SHA PHT PHE LMS 10 | SHA PHT PHE LMS 10 end | PCT CS LMS 10 | PCT CS LMS 10 end | PCT CCG LMS 10 | PCT CCG LMS 10 end | PCT DC LMS 10 | PCT DC LMS 10 end | PCT AQP LMS 10 | PCT AQP LMS 10 end | PCT HWB LMS 10 | PCT HWB LMS 10 end | PCT PHT LAs LMS 10 | PCT PHT LAs LMS 10 end | PCT PHT PHE LMS 10 | PCT PHT PHE LMS 10 end | QIPP LM 1.33 | QIPP LM 1.33 end | QIPP LM 2.33 | QIPP LM 2.33 end | QIPP LM 3.33 | QIPP LM 3.33 end | QIPP LM 4.33 | QIPP LM 4.33 end | QIPP LM 5.33 | QIPP LM 5.33 end | QIPP LM 6.33 | QIPP LM 6.33 end | QIPP LM 7.33 | QIPP LM 7.33 end | QIPP LM 8.33 | QIPP LM 8.33 end | QIPP LM 9.33 | QIPP LM 9.33 end | FTs LMS 10 | FTs LMS 10 end | 2014-11-30 | [8 empty] | South East London |  | 35
SHA CS LMS 11 | SHA CS LMS 11 end | SHA CCG LMS 11 | SHA CCG LMS 11 end | SHA DC LMS 11 | SHA DC LMS 11 end | SHA AQP LMS 11 | SHA AQP LMS 11 end | SHA HWB LMS 11 | SHA HWB LMS 11 end | SHA PHT LAs LMS 11 | SHA PHT LAs LMS 11 end | SHA PHT PHE LMS 11 | SHA PHT PHE LMS 11 end | PCT CS LMS 11 | PCT CS LMS 11 end | PCT CCG LMS 11 | PCT CCG LMS 11 end | PCT DC LMS 11 | PCT DC LMS 11 end | PCT AQP LMS 11 | PCT AQP LMS 11 end | PCT HWB LMS 11 | PCT HWB LMS 11 end | PCT PHT LAs LMS 11 | PCT PHT LAs LMS 11 end | PCT PHT PHE LMS 11 | PCT PHT PHE LMS 11 end | QIPP LM 1.34 | QIPP LM 1.34 end | QIPP LM 2.34 | QIPP LM 2.34 end | QIPP LM 3.34 | QIPP LM 3.34 end | QIPP LM 4.34 | QIPP LM 4.34 end | QIPP LM 5.34 | QIPP LM 5.34 end | QIPP LM 6.34 | QIPP LM 6.34 end | QIPP LM 7.34 | QIPP LM 7.34 end | QIPP LM 8.34 | QIPP LM 8.34 end | QIPP LM 9.34 | QIPP LM 9.34 end | FTs LMS 11 | FTs LMS 11 end | 2014-12-31 | [8 empty] | South West London |  | 36
SHA CS LMS 12 | SHA CS LMS 12 end | SHA CCG LMS 12 | SHA CCG LMS 12 end | SHA DC LMS 12 | SHA DC LMS 12 end | SHA AQP LMS 12 | SHA AQP LMS 12 end | SHA HWB LMS 12 | SHA HWB LMS 12 end | SHA PHT LAs LMS 12 | SHA PHT LAs LMS 12 end | SHA PHT PHE LMS 12 | SHA PHT PHE LMS 12 end | PCT CS LMS 12 | PCT CS LMS 12 end | PCT CCG LMS 12 | PCT CCG LMS 12 end | PCT DC LMS 12 | PCT DC LMS 12 end | PCT AQP LMS 12 | PCT AQP LMS 12 end | PCT HWB LMS 12 | PCT HWB LMS 12 end | PCT PHT LAs LMS 12 | PCT PHT LAs LMS 12 end | PCT PHT PHE LMS 12 | PCT PHT PHE LMS 12 end | QIPP LM 1.35 | QIPP LM 1.35 end | QIPP LM 2.35 | QIPP LM 2.35 end | QIPP LM 3.35 | QIPP LM 3.35 end | QIPP LM 4.35 | QIPP LM 4.35 end | QIPP LM 5.35 | QIPP LM 5.35 end | QIPP LM 6.35 | QIPP LM 6.35 end | QIPP LM 7.35 | QIPP LM 7.35 end | QIPP LM 8.35 | QIPP LM 8.35 end | QIPP LM 9.35 | QIPP LM 9.35 end | FTs LMS 12 | FTs LMS 12 end | 2015-01-31 | [8 empty] | North West London |  | 37
SHA CS LMS 13 | SHA CS LMS 13 end | SHA CCG LMS 13 | SHA CCG LMS 13 end | SHA DC LMS 13 | SHA DC LMS 13 end | SHA AQP LMS 13 | SHA AQP LMS 13 end | SHA HWB LMS 13 | SHA HWB LMS 13 end | SHA PHT LAs LMS 13 | SHA PHT LAs LMS 13 end | SHA PHT PHE LMS 13 | SHA PHT PHE LMS 13 end | PCT CS LMS 13 | PCT CS LMS 13 end | PCT CCG LMS 13 | PCT CCG LMS 13 end | PCT DC LMS 13 | PCT DC LMS 13 end | PCT AQP LMS 13 | PCT AQP LMS 13 end | PCT HWB LMS 13 | PCT HWB LMS 13 end | PCT PHT LAs LMS 13 | PCT PHT LAs LMS 13 end | PCT PHT PHE LMS 13 | PCT PHT PHE LMS 13 end | QIPP LM 1.36 | QIPP LM 1.36 end | QIPP LM 2.36 | QIPP LM 2.36 end | QIPP LM 3.36 | QIPP LM 3.36 end | QIPP LM 4.36 | QIPP LM 4.36 end | QIPP LM 5.36 | QIPP LM 5.36 end | QIPP LM 6.36 | QIPP LM 6.36 end | QIPP LM 7.36 | QIPP LM 7.36 end | QIPP LM 8.36 | QIPP LM 8.36 end | QIPP LM 9.36 | QIPP LM 9.36 end | FTs LMS 13 | FTs LMS 13 end | 2015-02-28 | [8 empty] | Cumbria |  | 38
SHA CS LMS 14 | SHA CS LMS 14 end | SHA CCG LMS 14 | SHA CCG LMS 14 end | SHA DC LMS 14 | SHA DC LMS 14 end | SHA AQP LMS 14 | SHA AQP LMS 14 end | SHA HWB LMS 14 | SHA HWB LMS 14 end | SHA PHT LAs LMS 14 | SHA PHT LAs LMS 14 end | SHA PHT PHE LMS 14 | SHA PHT PHE LMS 14 end | PCT CS LMS 14 | PCT CS LMS 14 end | PCT CCG LMS 14 | PCT CCG LMS 14 end | PCT DC LMS 14 | PCT DC LMS 14 end | PCT AQP LMS 14 | PCT AQP LMS 14 end | PCT HWB LMS 14 | PCT HWB LMS 14 end | PCT PHT LAs LMS 14 | PCT PHT LAs LMS 14 end | PCT PHT PHE LMS 14 | PCT PHT PHE LMS 14 end | QIPP LM 1.37 | QIPP LM 1.37 end | QIPP LM 2.37 | QIPP LM 2.37 end | QIPP LM 3.37 | QIPP LM 3.37 end | QIPP LM 4.37 | QIPP LM 4.37 end | QIPP LM 5.37 | QIPP LM 5.37 end | QIPP LM 6.37 | QIPP LM 6.37 end | QIPP LM 7.37 | QIPP LM 7.37 end | QIPP LM 8.37 | QIPP LM 8.37 end | QIPP LM 9.37 | QIPP LM 9.37 end | FTs LMS 14 | FTs LMS 14 end | 2015-03-31 | [8 empty] | Lancashire |  | 39
SHA CS LMS 15 | SHA CS LMS 15 end | SHA CCG LMS 15 | SHA CCG LMS 15 end | SHA DC LMS 15 | SHA DC LMS 15 end | SHA AQP LMS 15 | SHA AQP LMS 15 end | SHA HWB LMS 15 | SHA HWB LMS 15 end | SHA PHT LAs LMS 15 | SHA PHT LAs LMS 15 end | SHA PHT PHE LMS 15 | SHA PHT PHE LMS 15 end | PCT CS LMS 15 | PCT CS LMS 15 end | PCT CCG LMS 15 | PCT CCG LMS 15 end | PCT DC LMS 15 | PCT DC LMS 15 end | PCT AQP LMS 15 | PCT AQP LMS 15 end | PCT HWB LMS 15 | PCT HWB LMS 15 end | PCT PHT LAs LMS 15 | PCT PHT LAs LMS 15 end | PCT PHT PHE LMS 15 | PCT PHT PHE LMS 15 end | QIPP LM 1.38 | QIPP LM 1.38 end | QIPP LM 2.38 | QIPP LM 2.38 end | QIPP LM 3.38 | QIPP LM 3.38 end | QIPP LM 4.38 | QIPP LM 4.38 end | QIPP LM 5.38 | QIPP LM 5.38 end | QIPP LM 6.38 | QIPP LM 6.38 end | QIPP LM 7.38 | QIPP LM 7.38 end | QIPP LM 8.38 | QIPP LM 8.38 end | QIPP LM 9.38 | QIPP LM 9.38 end | FTs LMS 15 | FTs LMS 15 end | 2015-04-30 | [8 empty] | Merseyside |  | 40
SHA CS LMS 16 | SHA CS LMS 16 end | SHA CCG LMS 16 | SHA CCG LMS 16 end | SHA DC LMS 16 | SHA DC LMS 16 end | SHA AQP LMS 16 | SHA AQP LMS 16 end | SHA HWB LMS 16 | SHA HWB LMS 16 end | SHA PHT LAs LMS 16 | SHA PHT LAs LMS 16 end | SHA PHT PHE LMS 16 | SHA PHT PHE LMS 16 end | PCT CS LMS 16 | PCT CS LMS 16 end | PCT CCG LMS 16 | PCT CCG LMS 16 end | PCT DC LMS 16 | PCT DC LMS 16 end | PCT AQP LMS 16 | PCT AQP LMS 16 end | PCT HWB LMS 16 | PCT HWB LMS 16 end | PCT PHT LAs LMS 16 | PCT PHT LAs LMS 16 end | PCT PHT PHE LMS 16 | PCT PHT PHE LMS 16 end | QIPP LM 1.39 | QIPP LM 1.39 end | QIPP LM 2.39 | QIPP LM 2.39 end | QIPP LM 3.39 | QIPP LM 3.39 end | QIPP LM 4.39 | QIPP LM 4.39 end | QIPP LM 5.39 | QIPP LM 5.39 end | QIPP LM 6.39 | QIPP LM 6.39 end | QIPP LM 7.39 | QIPP LM 7.39 end | QIPP LM 8.39 | QIPP LM 8.39 end | QIPP LM 9.39 | QIPP LM 9.39 end | FTs LMS 16 | FTs LMS 16 end | 2015-05-31 | [8 empty] | Greater Manchester |  | 41
SHA CS LMS 17 | SHA CS LMS 17 end | SHA CCG LMS 17 | SHA CCG LMS 17 end | SHA DC LMS 17 | SHA DC LMS 17 end | SHA AQP LMS 17 | SHA AQP LMS 17 end | SHA HWB LMS 17 | SHA HWB LMS 17 end | SHA PHT LAs LMS 17 | SHA PHT LAs LMS 17 end | SHA PHT PHE LMS 17 | SHA PHT PHE LMS 17 end | PCT CS LMS 17 | PCT CS LMS 17 end | PCT CCG LMS 17 | PCT CCG LMS 17 end | PCT DC LMS 17 | PCT DC LMS 17 end | PCT AQP LMS 17 | PCT AQP LMS 17 end | PCT HWB LMS 17 | PCT HWB LMS 17 end | PCT PHT LAs LMS 17 | PCT PHT LAs LMS 17 end | PCT PHT PHE LMS 17 | PCT PHT PHE LMS 17 end | QIPP LM 1.40 | QIPP LM 1.40 end | QIPP LM 2.40 | QIPP LM 2.40 end | QIPP LM 3.40 | QIPP LM 3.40 end | QIPP LM 4.40 | QIPP LM 4.40 end | QIPP LM 5.40 | QIPP LM 5.40 end | QIPP LM 6.40 | QIPP LM 6.40 end | QIPP LM 7.40 | QIPP LM 7.40 end | QIPP LM 8.40 | QIPP LM 8.40 end | QIPP LM 9.40 | QIPP LM 9.40 end | FTs LMS 17 | FTs LMS 17 end | 2015-06-30 | [8 empty] | Cheshire |  | 42
SHA CS LMS 18 | SHA CS LMS 18 end | SHA CCG LMS 18 | SHA CCG LMS 18 end | SHA DC LMS 18 | SHA DC LMS 18 end | SHA AQP LMS 18 | SHA AQP LMS 18 end | SHA HWB LMS 18 | SHA HWB LMS 18 end | SHA PHT LAs LMS 18 | SHA PHT LAs LMS 18 end | SHA PHT PHE LMS 18 | SHA PHT PHE LMS 18 end | PCT CS LMS 18 | PCT CS LMS 18 end | PCT CCG LMS 18 | PCT CCG LMS 18 end | PCT DC LMS 18 | PCT DC LMS 18 end | PCT AQP LMS 18 | PCT AQP LMS 18 end | PCT HWB LMS 18 | PCT HWB LMS 18 end | PCT PHT LAs LMS 18 | PCT PHT LAs LMS 18 end | PCT PHT PHE LMS 18 | PCT PHT PHE LMS 18 end | QIPP LM 1.41 | QIPP LM 1.41 end | QIPP LM 2.41 | QIPP LM 2.41 end | QIPP LM 3.41 | QIPP LM 3.41 end | QIPP LM 4.41 | QIPP LM 4.41 end | QIPP LM 5.41 | QIPP LM 5.41 end | QIPP LM 6.41 | QIPP LM 6.41 end | QIPP LM 7.41 | QIPP LM 7.41 end | QIPP LM 8.41 | QIPP LM 8.41 end | QIPP LM 9.41 | QIPP LM 9.41 end | FTs LMS 18 | FTs LMS 18 end | 2015-07-31 | [8 empty] | County Durham & Darlington |  | 43
SHA CS LMS 19 | SHA CS LMS 19 end | SHA CCG LMS 19 | SHA CCG LMS 19 end | SHA DC LMS 19 | SHA DC LMS 19 end | SHA AQP LMS 19 | SHA AQP LMS 19 end | SHA HWB LMS 19 | SHA HWB LMS 19 end | SHA PHT LAs LMS 19 | SHA PHT LAs LMS 19 end | SHA PHT PHE LMS 19 | SHA PHT PHE LMS 19 end | PCT CS LMS 19 | PCT CS LMS 19 end | PCT CCG LMS 19 | PCT CCG LMS 19 end | PCT DC LMS 19 | PCT DC LMS 19 end | PCT AQP LMS 19 | PCT AQP LMS 19 end | PCT HWB LMS 19 | PCT HWB LMS 19 end | PCT PHT LAs LMS 19 | PCT PHT LAs LMS 19 end | PCT PHT PHE LMS 19 | PCT PHT PHE LMS 19 end | QIPP LM 1.42 | QIPP LM 1.42 end | QIPP LM 2.42 | QIPP LM 2.42 end | QIPP LM 3.42 | QIPP LM 3.42 end | QIPP LM 4.42 | QIPP LM 4.42 end | QIPP LM 5.42 | QIPP LM 5.42 end | QIPP LM 6.42 | QIPP LM 6.42 end | QIPP LM 7.42 | QIPP LM 7.42 end | QIPP LM 8.42 | QIPP LM 8.42 end | QIPP LM 9.42 | QIPP LM 9.42 end | FTs LMS 19 | FTs LMS 19 end | [9 empty] | North of Tyne |  | 44
SHA CS LMS 20 | SHA CS LMS 20 end | SHA CCG LMS 20 | SHA CCG LMS 20 end | SHA DC LMS 20 | SHA DC LMS 20 end | SHA AQP LMS 20 | SHA AQP LMS 20 end | SHA HWB LMS 20 | SHA HWB LMS 20 end | SHA PHT LAs LMS 20 | SHA PHT LAs LMS 20 end | SHA PHT PHE LMS 20 | SHA PHT PHE LMS 20 end | PCT CS LMS 20 | PCT CS LMS 20 end | PCT CCG LMS 20 | PCT CCG LMS 20 end | PCT DC LMS 20 | PCT DC LMS 20 end | PCT AQP LMS 20 | PCT AQP LMS 20 end | PCT HWB LMS 20 | PCT HWB LMS 20 end | PCT PHT LAs LMS 20 | PCT PHT LAs LMS 20 end | PCT PHT PHE LMS 20 | PCT PHT PHE LMS 20 end | QIPP LM 1.43 | QIPP LM 1.43 end | QIPP LM 2.43 | QIPP LM 2.43 end | QIPP LM 3.43 | QIPP LM 3.43 end | QIPP LM 4.43 | QIPP LM 4.43 end | QIPP LM 5.43 | QIPP LM 5.43 end | QIPP LM 6.43 | QIPP LM 6.43 end | QIPP LM 7.43 | QIPP LM 7.43 end | QIPP LM 8.43 | QIPP LM 8.43 end | QIPP LM 9.43 | QIPP LM 9.43 end | FTs LMS 20 | FTs LMS 20 end | [9 empty] | South of Tyne & Wear |  | 45
SHA CS LMS 21 | SHA CS LMS 21 end | SHA CCG LMS 21 | SHA CCG LMS 21 end | SHA DC LMS 21 | SHA DC LMS 21 end | SHA AQP LMS 21 | SHA AQP LMS 21 end | SHA HWB LMS 21 | SHA HWB LMS 21 end | SHA PHT LAs LMS 21 | SHA PHT LAs LMS 21 end | SHA PHT PHE LMS 21 | SHA PHT PHE LMS 21 end | PCT CS LMS 21 | PCT CS LMS 21 end | PCT CCG LMS 21 | PCT CCG LMS 21 end | PCT DC LMS 21 | PCT DC LMS 21 end | PCT AQP LMS 21 | PCT AQP LMS 21 end | PCT HWB LMS 21 | PCT HWB LMS 21 end | PCT PHT LAs LMS 21 | PCT PHT LAs LMS 21 end | PCT PHT PHE LMS 21 | PCT PHT PHE LMS 21 end | QIPP LM 1.44 | QIPP LM 1.44 end | QIPP LM 2.44 | QIPP LM 2.44 end | QIPP LM 3.44 | QIPP LM 3.44 end | QIPP LM 4.44 | QIPP LM 4.44 end | QIPP LM 5.44 | QIPP LM 5.44 end | QIPP LM 6.44 | QIPP LM 6.44 end | QIPP LM 7.44 | QIPP LM 7.44 end | QIPP LM 8.44 | QIPP LM 8.44 end | QIPP LM 9.44 | QIPP LM 9.44 end | FTs LMS 21 | FTs LMS 21 end | [9 empty] | Tees |  | 46
SHA CS LMS 22 | SHA CS LMS 22 end | SHA CCG LMS 22 | SHA CCG LMS 22 end | SHA DC LMS 22 | SHA DC LMS 22 end | SHA AQP LMS 22 | SHA AQP LMS 22 end | SHA HWB LMS 22 | SHA HWB LMS 22 end | SHA PHT LAs LMS 22 | SHA PHT LAs LMS 22 end | SHA PHT PHE LMS 22 | SHA PHT PHE LMS 22 end | PCT CS LMS 22 | PCT CS LMS 22 end | PCT CCG LMS 22 | PCT CCG LMS 22 end | PCT DC LMS 22 | PCT DC LMS 22 end | PCT AQP LMS 22 | PCT AQP LMS 22 end | PCT HWB LMS 22 | PCT HWB LMS 22 end | PCT PHT LAs LMS 22 | PCT PHT LAs LMS 22 end | PCT PHT PHE LMS 22 | PCT PHT PHE LMS 22 end | QIPP LM 1.45 | QIPP LM 1.45 end | QIPP LM 2.45 | QIPP LM 2.45 end | QIPP LM 3.45 | QIPP LM 3.45 end | QIPP LM 4.45 | QIPP LM 4.45 end | QIPP LM 5.45 | QIPP LM 5.45 end | QIPP LM 6.45 | QIPP LM 6.45 end | QIPP LM 7.45 | QIPP LM 7.45 end | QIPP LM 8.45 | QIPP LM 8.45 end | QIPP LM 9.45 | QIPP LM 9.45 end | FTs LMS 22 | FTs LMS 22 end | [9 empty] | South Yorkshire & Bassetlaw |  | 47
SHA CS LMS 23 | SHA CS LMS 23 end | SHA CCG LMS 23 | SHA CCG LMS 23 end | SHA DC LMS 23 | SHA DC LMS 23 end | SHA AQP LMS 23 | SHA AQP LMS 23 end | SHA HWB LMS 23 | SHA HWB LMS 23 end | SHA PHT LAs LMS 23 | SHA PHT LAs LMS 23 end | SHA PHT PHE LMS 23 | SHA PHT PHE LMS 23 end | PCT CS LMS 23 | PCT CS LMS 23 end | PCT CCG LMS 23 | PCT CCG LMS 23 end | PCT DC LMS 23 | PCT DC LMS 23 end | PCT AQP LMS 23 | PCT AQP LMS 23 end | PCT HWB LMS 23 | PCT HWB LMS 23 end | PCT PHT LAs LMS 23 | PCT PHT LAs LMS 23 end | PCT PHT PHE LMS 23 | PCT PHT PHE LMS 23 end | QIPP LM 1.46 | QIPP LM 1.46 end | QIPP LM 2.46 | QIPP LM 2.46 end | QIPP LM 3.46 | QIPP LM 3.46 end | QIPP LM 4.46 | QIPP LM 4.46 end | QIPP LM 5.46 | QIPP LM 5.46 end | QIPP LM 6.46 | QIPP LM 6.46 end | QIPP LM 7.46 | QIPP LM 7.46 end | QIPP LM 8.46 | QIPP LM 8.46 end | QIPP LM 9.46 | QIPP LM 9.46 end | FTs LMS 23 | FTs LMS 23 end | [9 empty] | Calderdale, Kirklees & Wakefield |  | 48
SHA CS LMS 24 | SHA CS LMS 24 end | SHA CCG LMS 24 | SHA CCG LMS 24 end | SHA DC LMS 24 | SHA DC LMS 24 end | SHA AQP LMS 24 | SHA AQP LMS 24 end | SHA HWB LMS 24 | SHA HWB LMS 24 end | SHA PHT LAs LMS 24 | SHA PHT LAs LMS 24 end | SHA PHT PHE LMS 24 | SHA PHT PHE LMS 24 end | PCT CS LMS 24 | PCT CS LMS 24 end | PCT CCG LMS 24 | PCT CCG LMS 24 end | PCT DC LMS 24 | PCT DC LMS 24 end | PCT AQP LMS 24 | PCT AQP LMS 24 end | PCT HWB LMS 24 | PCT HWB LMS 24 end | PCT PHT LAs LMS 24 | PCT PHT LAs LMS 24 end | PCT PHT PHE LMS 24 | PCT PHT PHE LMS 24 end | QIPP LM 1.47 | QIPP LM 1.47 end | QIPP LM 2.47 | QIPP LM 2.47 end | QIPP LM 3.47 | QIPP LM 3.47 end | QIPP LM 4.47 | QIPP LM 4.47 end | QIPP LM 5.47 | QIPP LM 5.47 end | QIPP LM 6.47 | QIPP LM 6.47 end | QIPP LM 7.47 | QIPP LM 7.47 end | QIPP LM 8.47 | QIPP LM 8.47 end | QIPP LM 9.47 | QIPP LM 9.47 end | FTs LMS 24 | FTs LMS 24 end | [9 empty] | The Humber |  | 49
SHA CS LMS 25 | SHA CS LMS 25 end | SHA CCG LMS 25 | SHA CCG LMS 25 end | SHA DC LMS 25 | SHA DC LMS 25 end | SHA AQP LMS 25 | SHA AQP LMS 25 end | SHA HWB LMS 25 | SHA HWB LMS 25 end | SHA PHT LAs LMS 25 | SHA PHT LAs LMS 25 end | SHA PHT PHE LMS 25 | SHA PHT PHE LMS 25 end | PCT CS LMS 25 | PCT CS LMS 25 end | PCT CCG LMS 25 | PCT CCG LMS 25 end | PCT DC LMS 25 | PCT DC LMS 25 end | PCT AQP LMS 25 | PCT AQP LMS 25 end | PCT HWB LMS 25 | PCT HWB LMS 25 end | PCT PHT LAs LMS 25 | PCT PHT LAs LMS 25 end | PCT PHT PHE LMS 25 | PCT PHT PHE LMS 25 end | QIPP LM 1.48 | QIPP LM 1.48 end | QIPP LM 2.48 | QIPP LM 2.48 end | QIPP LM 3.48 | QIPP LM 3.48 end | QIPP LM 4.48 | QIPP LM 4.48 end | QIPP LM 5.48 | QIPP LM 5.48 end | QIPP LM 6.48 | QIPP LM 6.48 end | QIPP LM 7.48 | QIPP LM 7.48 end | QIPP LM 8.48 | QIPP LM 8.48 end | QIPP LM 9.48 | QIPP LM 9.48 end | FTs LMS 25 | FTs LMS 25 end | [9 empty] | Leedsand Bradford |  | 50
SHA CS LMS 26 | SHA CS LMS 26 end | SHA CCG LMS 26 | SHA CCG LMS 26 end | SHA DC LMS 26 | SHA DC LMS 26 end | SHA AQP LMS 26 | SHA AQP LMS 26 end | SHA HWB LMS 26 | SHA HWB LMS 26 end | SHA PHT LAs LMS 26 | SHA PHT LAs LMS 26 end | SHA PHT PHE LMS 26 | SHA PHT PHE LMS 26 end | PCT CS LMS 26 | PCT CS LMS 26 end | PCT CCG LMS 26 | PCT CCG LMS 26 end | PCT DC LMS 26 | PCT DC LMS 26 end | PCT AQP LMS 26 | PCT AQP LMS 26 end | PCT HWB LMS 26 | PCT HWB LMS 26 end | PCT PHT LAs LMS 26 | PCT PHT LAs LMS 26 end | PCT PHT PHE LMS 26 | PCT PHT PHE LMS 26 end | QIPP LM 1.49 | QIPP LM 1.49 end | QIPP LM 2.49 | QIPP LM 2.49 end | QIPP LM 3.49 | QIPP LM 3.49 end | QIPP LM 4.49 | QIPP LM 4.49 end | QIPP LM 5.49 | QIPP LM 5.49 end | QIPP LM 6.49 | QIPP LM 6.49 end | QIPP LM 7.49 | QIPP LM 7.49 end | QIPP LM 8.49 | QIPP LM 8.49 end | QIPP LM 9.49 | QIPP LM 9.49 end | FTs LMS 26 | FTs LMS 26 end | [9 empty] | North Yorkshire & York
SHA CS LMS 27 | SHA CS LMS 27 end | SHA CCG LMS 27 | SHA CCG LMS 27 end | SHA DC LMS 27 | SHA DC LMS 27 end | SHA AQP LMS 27 | SHA AQP LMS 27 end | SHA HWB LMS 27 | SHA HWB LMS 27 end | SHA PHT LAs LMS 27 | SHA PHT LAs LMS 27 end | SHA PHT PHE LMS 27 | SHA PHT PHE LMS 27 end | PCT CS LMS 27 | PCT CS LMS 27 end | PCT CCG LMS 27 | PCT CCG LMS 27 end | PCT DC LMS 27 | PCT DC LMS 27 end | PCT AQP LMS 27 | PCT AQP LMS 27 end | PCT HWB LMS 27 | PCT HWB LMS 27 end | PCT PHT LAs LMS 27 | PCT PHT LAs LMS 27 end | PCT PHT PHE LMS 27 | PCT PHT PHE LMS 27 end | QIPP LM 1.50 | QIPP LM 1.50 end | QIPP LM 2.50 | QIPP LM 2.50 end | QIPP LM 3.50 | QIPP LM 3.50 end | QIPP LM 4.50 | QIPP LM 4.50 end | QIPP LM 5.50 | QIPP LM 5.50 end | QIPP LM 6.50 | QIPP LM 6.50 end | QIPP LM 7.50 | QIPP LM 7.50 end | QIPP LM 8.50 | QIPP LM 8.50 end | QIPP LM 9.50 | QIPP LM 9.50 end | FTs LMS 27 | FTs LMS 27 end
SHA CS LMS 28 | SHA CS LMS 28 end | SHA CCG LMS 28 | SHA CCG LMS 28 end | SHA DC LMS 28 | SHA DC LMS 28 end | SHA AQP LMS 28 | SHA AQP LMS 28 end | SHA HWB LMS 28 | SHA HWB LMS 28 end | SHA PHT LAs LMS 28 | SHA PHT LAs LMS 28 end | SHA PHT PHE LMS 28 | SHA PHT PHE LMS 28 end | PCT CS LMS 28 | PCT CS LMS 28 end | PCT CCG LMS 28 | PCT CCG LMS 28 end | PCT DC LMS 28 | PCT DC LMS 28 end | PCT AQP LMS 28 | PCT AQP LMS 28 end | PCT HWB LMS 28 | PCT HWB LMS 28 end | PCT PHT LAs LMS 28 | PCT PHT LAs LMS 28 end | PCT PHT PHE LMS 28 | PCT PHT PHE LMS 28 end | QIPP LM 1.51 | QIPP LM 1.51 end | QIPP LM 2.51 | QIPP LM 2.51 end | QIPP LM 3.51 | QIPP LM 3.51 end | QIPP LM 4.51 | QIPP LM 4.51 end | QIPP LM 5.51 | QIPP LM 5.51 end | QIPP LM 6.51 | QIPP LM 6.51 end | QIPP LM 7.51 | QIPP LM 7.51 end | QIPP LM 8.51 | QIPP LM 8.51 end | QIPP LM 9.51 | QIPP LM 9.51 end | FTs LMS 28 | FTs LMS 28 end
SHA CS LMS 29 | SHA CS LMS 29 end | SHA CCG LMS 29 | SHA CCG LMS 29 end | SHA DC LMS 29 | SHA DC LMS 29 end | SHA AQP LMS 29 | SHA AQP LMS 29 end | SHA HWB LMS 29 | SHA HWB LMS 29 end | SHA PHT LAs LMS 29 | SHA PHT LAs LMS 29 end | SHA PHT PHE LMS 29 | SHA PHT PHE LMS 29 end | PCT CS LMS 29 | PCT CS LMS 29 end | PCT CCG LMS 29 | PCT CCG LMS 29 end | PCT DC LMS 29 | PCT DC LMS 29 end | PCT AQP LMS 29 | PCT AQP LMS 29 end | PCT HWB LMS 29 | PCT HWB LMS 29 end | PCT PHT LAs LMS 29 | PCT PHT LAs LMS 29 end | PCT PHT PHE LMS 29 | PCT PHT PHE LMS 29 end | QIPP LM 1.52 | QIPP LM 1.52 end | QIPP LM 2.52 | QIPP LM 2.52 end | QIPP LM 3.52 | QIPP LM 3.52 end | QIPP LM 4.52 | QIPP LM 4.52 end | QIPP LM 5.52 | QIPP LM 5.52 end | QIPP LM 6.52 | QIPP LM 6.52 end | QIPP LM 7.52 | QIPP LM 7.52 end | QIPP LM 8.52 | QIPP LM 8.52 end | QIPP LM 9.52 | QIPP LM 9.52 end | FTs LMS 29 | FTs LMS 29 end
SHA CS LMS 30 | SHA CS LMS 30 end | SHA CCG LMS 30 | SHA CCG LMS 30 end | SHA DC LMS 30 | SHA DC LMS 30 end | SHA AQP LMS 30 | SHA AQP LMS 30 end | SHA HWB LMS 30 | SHA HWB LMS 30 end | SHA PHT LAs LMS 30 | SHA PHT LAs LMS 30 end | SHA PHT PHE LMS 30 | SHA PHT PHE LMS 30 end | PCT CS LMS 30 | PCT CS LMS 30 end | PCT CCG LMS 30 | PCT CCG LMS 30 end | PCT DC LMS 30 | PCT DC LMS 30 end | PCT AQP LMS 30 | PCT AQP LMS 30 end | PCT HWB LMS 30 | PCT HWB LMS 30 end | PCT PHT LAs LMS 30 | PCT PHT LAs LMS 30 end | PCT PHT PHE LMS 30 | PCT PHT PHE LMS 30 end | QIPP LM 1.53 | QIPP LM 1.53 end | QIPP LM 2.53 | QIPP LM 2.53 end | QIPP LM 3.53 | QIPP LM 3.53 end | QIPP LM 4.53 | QIPP LM 4.53 end | QIPP LM 5.53 | QIPP LM 5.53 end | QIPP LM 6.53 | QIPP LM 6.53 end | QIPP LM 7.53 | QIPP LM 7.53 end | QIPP LM 8.53 | QIPP LM 8.53 end | QIPP LM 9.53 | QIPP LM 9.53 end | FTs LMS 30 | FTs LMS 30 end