## SummaryReformMilestonesM&E EM
NHS Midlands and East: - East Midlands Area PCT cluster RAG ratings for progress against QIPP initiatives - 2012-13
For SHA USE Summary commentry on PCT clusters Summary commentry for SHA cluster
Report for the month of: | Date |  |  | PCT Clusters
Domains | Totals for RAG Rating |  |  | Derbyshire | Leicestershire | Lincolnshire | Northhamptonshire | Nottinghamshire | PCT cluster 6 | PCT cluster 7
| Red | Amber | Green
Initiative 1 | 0 | 1 | 4 | Green | Green | Amber | Green | Green | RAG Rating | RAG Rating
| Narrative |  |  | Programme & initiatives are progressing in line with schedule. There are some delays with specific elements as CCGs adapt / refine approach. M4 financials indicate no significant issues with full QIPP delivery expected for City and County. M4 MAR (UNIFY) indicates the following cumulative trend: - All elective activity at or below plan (and 2011/12) for County PCT - GP and other referrals above plan (and 2011/12) for City PCT. This is reflected in contract activity with Derby Hospitals NHS FT (DHFT). NHS Southern Derbyshire, supported by the cluster PMO, are investigating this referral pattern to understand the trend and plan mitigating actions. - Elective activity is above plan (although equivalent to 2011/12) for the City PCT. This is due to additional daycase activity at DHFT in May to ensure waiting lists/times remain within the RTT standards. Activity and waiting times will continue to be monitored to ensure performance is achieved within affordable limits. | There are a number of schemes that will impact on elective activity later in the year once new pathways are embedded locally. For instance, CCGs have demand management schemes in place, with new pathways being introduced in Q2. Activity Triagulation: QIPP savings were reduced in the contract negotitations compared to the UNIFY plan. Therefore the UNIFY plan would be higher. | Trajectory to end state overall on track., Improving activity. Rephasing of ULHT activity complete and agreed - still awaiting backdating of impact and coding issues - 3.4% fye beneficial impact. Peterborogh recovery plan in place for RTT | The Healthier Together Consultation has been set for October 12. The Strategic Health Authority have issued a KPMG report that potentially impacts on the Healthier Together programme. The CCGs are currently discussing the impact of the SHA initiative with key providers. This will not be concluded until early Octoberber 12. The LAT is involved. | Milestones are on track in accordance with the new IHSC delivery programme. Financial QIPP delivery is above plan for both City & County. | 0 | 0
Initiative 2 | 0 | 4 | 1 | Amber | Amber | Amber | Amber | Green | RAG Rating | RAG Rating
| Narrative |  |  | Programme & initiatives are progressing in line with schedule. M4 financials indicate no significant issues with full QIPP delivery expected for City and County. M4 MAR (UNIFY) indicates the following cumulative trend: - Non elective activity is below plan (and 2011/12) for City PCT. - Non elective activity is above plan (and 2011/12) for County PCT. Some providers have understated activity in their 2012/13 plans which has contributed to a small understatement of the County PCT level plan. This only has marginal contribution to the over performance being experienced. The over performance is most noticable at Nottingham (NUH), Chesterfield (CRHFT), Sherwood Forest Hospitals and Derbyshire Community Health Services (DCHS). In most cases the impact of QIPP schemes was not phased until month 6 so non delivery of QIPP is not considered to be the issue. The four CCGs, supported by the cluster PMO, are investigating this over performance to understand the underlying causes and plan mitigating actions. | The current status of this programme is Amber. The Transformational Fund schemes in place will impact on non-elective activity. Confirm and Challenge Meetings in September/October have provided assurance to PCT. Work continues with regard to activity pressures & an update will be available in October return. Activity Triangulation: Performance is as a result of an increase in demand. | Milestones - overall on track. Activity - off plan. Collectively the Lincolnshire CCG’s have experienced an increase in both value and complexity in non-elective acute activity. This has impacted on a key component of the PCT QIPP programme. Since August the CCG’s have commissioned the services of an external consultant (commencing in October) to review the activity counting and coding in the context of changes negotiated with ULHT. All CCG’s have ongoing projects to support reduction of admissions and are reviewing all QIPP initiatives in respect of non-elective acute activity. Second quarter data is expected to better inform impact of mitigating actions | Monthly performance meetings with CCGs suggest real progress in reducing outpatient referrals and follow ups. We have more accurately phased the impact of demand management schemes and this is starting to show particularly in Northants. Each of the CCGs has begun a series of contractual challenges with their respective Acute Providers to seek clarification. All are forecasting to be on target by the end of the year, with their QIPP savings. | Milestones are largely on track for the Mental Health QIPP Programme. Financial delivery for County is on track with a slight under delivery for City | 0 | 0
Initiative 3 | 0 | 2 | 3 | Green | Green | Green | Amber | Amber | RAG Rating | RAG Rating
| Narrative |  |  | Programme & initiatives are progressing in line with schedule. M4 financials indicate no significant issues with full QIPP delivery expected for City and County. M4 MAR (UNIFY) indicates the following cumulative trend: - Elective outpatient activity is cumulatively above plan for the City although below 2011/12 levels). There has been a particular increase in outpatients in July which is understood to relate to the increase in GP and other referrals seen in earlier months. This will continue to be monitored closely particularly in relation to it resulting in increased elective activity later in the year.Activity and waiting times will continue to be monitored to ensure performance is achieved within affordable limits. | The current status of this programme is Green as progressing to schedule. There are currently no foreseen issues relating to work which has commenced. Activity triagulation: QIPP savings are based on all new outpatients with a small number of exclusions. UNIFY only states GP referred or Consultant led. There is an under-performance in the "Other new outpatients" and QIPP savings were reduced in the contract negotitations compared to the UNIFY plan. Therefore the UNIFY plan would be higher. | Overall milestones, activity and finance on track. New to follow up reduced by 11846 attendances across 4 key specialties | Northants trusts (KGH & NGH) on track with A&E. QIPP non-elective actions not a large percentage and are not impacting (+ 6-7 %). Concern remains about the acuity of patients presenting to A&E and the growth in admissions. A number of additional redesign and change management processes are in place and / or being developed, including additional investments. | Milestones are largely on track for all schemes. Financial delivery is slightly under for City and County. There is an over performance in non elective activity for both County & City for surgical & medical specialties with Respiratory being the main issue at both acute trusts. Further investigation is being undertaken by CCG's and the Information teams. | 0 | 0
Initiative 4 | 0 | 2 | 3 | Green | Green | Green | Amber | Amber | RAG Rating | RAG Rating
| Narrative |  |  | Programme/initiative progressing in line with schedule. | The current status of this programme is Green as progressing to schedule. There are currently no foreseen issues relating to work which has commenced. | All milestones and activity on track. Work is ongoing around the Publiuc Health Allocationand its impact on business plan for 13/14. Plan targetted for December 2012 completion. | There are a number of QIPP Schemes working around management of electives, in particular Right Care and other Planned Care programmes. However phasing is an issue and the CCG concerns with regard to Trust activity are being challenged through the contracts. We expect that to reduce Acute Elective activity in line with plan by the end of the year. This is begining to show a positive trend. | Milestones are largely on track. Financial QIPP delivery is above plan at County and slightly under at City. With regards to activity, elective ordinarys are under plan whilst elective day case are above plan partly as a result of Bowel Cancer Awareness Screening | 0 | 0
Initiative 5 | 0 | 2 | 3 | Green | Green | Amber | Green | Amber | RAG Rating | RAG Rating
| Narrative |  |  | QIPP Programme/initiative progressing in line with schedule. 2% non recurrent has been deployed to support medicines management programmes within CCGs. Prescribing performance is monitored at CCG level on a monthly basis and shared with CCG Governing Body and individual practices via the locality GP prescribing leads. Monthly reports (produced by the Eclipse system) are provided at practice level giving a further breakdown of financial and quality prescribing indicators, highlighting clinical variation and monitoring success of specific prescribing projects. | The current status of this programme is Green as progressing to schedule. There are currently no foreseen issues relating to work which has commenced. | As August: All milestones met. More accurate forecasts will develop over the coming months as it becomes clearer what effect the transition will have on Running Costs. Latest calculations indicate Running costs are within the target ceiling. QIPP: FMR continues to report all QIPP savings will be delivered in 2012/13. Performance information that informed the Q1 monitoring information was incomplete and contradictory. Year to date performance was evaluated on the basis of limited information suggesting over performance of acute activity relative to plan. | The Mental Health and Learning Disabilities schemes in the tracker are progressing well. There are a significant number of additional schemes and actions in this domain that are either progressing well or are on an accelerated development path. For both Milton Keynes and Northamptonshire, we are confident that they will meet their QIPP requirement by year end. Savings have already been recovered through contracts with providers. | Milestones are largely on track. Financial delivery is under delivering at both City & County. With regards to activity, first OP appts are above plan with with a high backlog of patients to be seen at SFH relating to diagnostic waiting times and challenges with C&B slots availability | 0 | 0
Initiative 6 | 0 | 1 | 2 | Green | RAG Rating | Amber | RAG Rating | Green | RAG Rating | RAG Rating
| Narrative |  |  | Programme/initiative progressing in line with schedule. Individual patient programme progressing in line with plan and planned savings to date have been achieved. | 0 | Our Prescribing QIPP Information Pack 2012/13 detailing all QIPP opportunities and productivity savings by practice and CCG was issued in early May 2012. Since then the Prescribing and Medicines Optimisation Team have been working with CCGs, locality GP groups and individual practices to secure agreements around prescribing changes for this year. This work is on track for completion in October 2012. To date, £1.9M savings have now been agreed with our practices. So far £291,000 have been realised through technician implementation of agreed changes. Most of the technician led switches implemented during the last few months have been rosuvastatin switches designed to maximise efficiencies resulting from the atorvastatin patent expiry. Further work quantifying the in-year savings related to additional patent expiries in 2012 has been completed and quantified as £2.7M. However, prescribing expenditure remains a key risk area and trends will continue to be closely monitored. | 0 | Milestones are all on track. Financial delivery is over plan for both County & City | 0 | 0
Initiative 7 | 0 | 1 | 1 | Amber | RAG Rating | Green | RAG Rating | RAG Rating | RAG Rating | RAG Rating
| Narrative |  |  | Due to the complexity of the overall integrated care programme, delays are now expected in the detailed design, formal public consultation and development or robust implementation plans in 2012/13 to 2013/14. This is expected to have a knock on delay to implementation in 2013/14. | 0 | 75% of the LD multi-disciplinary team are in post within a single provider, including Physiotherapy, Occupational Therapy, Psychology and Psychiatry. Nursing staff will transfer in the coming months. The Lincolnshire transformation of mental health services programme is developing its proposals and option appraisal methods to engage with all stakeholders. Public consultation is planned and gateway process will be applied to ensure the plans are robust enough to proceed. | 0 | 0 | 0
PCT narrative on cluster progress |  |  |  | The cluster/CCGs are making strong progress delivering QIPP milestones. M4 financials indicate no significant issues with full QIPP delivery expected for City and County. Where UNIFY activity is above plan (elective activity for the City PCT and non elective activity for the County PCT) this is being explored with the lead commissioning CCGs to determine whether it signals an issue, and if so how this is being addressed / mitigated. There is some slippage at milestone level associated with the development of strategies for implementation in 2013/14. This is not expected to impact significiantly on 2012/13 QIPP impact but may impact on 2013/14 QIPP impact. CCGs are already actively working to address any delay in expected savings for 2013/14 through other areas of CCG QIPP plans for 2013/14. CCGs remain committed to achieving the overall Derbyshire vision set out within the integrated plan. During 2012/13 and as part of authorisation they have necessarily developed their own clinically led visions and supporting QIPP delivery plans. These increasingly do not align with the original milestones set out within the integrated plan. This report therefore indicates missed milestones, when in many cases CCGs have just have adopted a different approach to delivery. Where milestones are behind schedule the cluster is actively challenging the CCG to improve progress. It is expected that CCGs will wish to review/refine detailed milestone plans as part of the 2013/14 planning round. | The SHA and PCT cluster are in agreement over an AMBER rating for September. Finance is on track and milestones are progressing, however, the overall situation is being affected by the non-elective activity position. Schemes are in place which will change pathways, however these will take time to embed in locally. Assurance has been obtained through Confirm & Challenge sessions with programme leads, and further work on activity pressures will be reported in October 2012, with CCG input. | Milestones are generally on track and good progress continues towards end states. However bothoth finance and activity are off plan predominantly due to acute contractual issues. The increase in value and complexity of non-elective acute activity impacts on a key component of the Cluster QIPP programme. All CCGs are reviewing all QIPP initiatives in respect of non-elective acute activity and have a consultant commencing in October to review the counting and coding of activity in the context of changes negotiated with ULHT. The latest financial position shows a £1.8m shortfall against QIPP target. However £1.6m of 'unspecified' projects is also identified and the CCGs are committed to identify those projects that can be brought forward from 13/14 and to a review of 12/13 projects to maximise impact. The PCT is confifdent that mitigations offered will start to impact in second quarter figures and re-profiliing off activity will ensure achievement of theoverall QIPP financial target. | The majority of milestones are on target, and those that are delayed have had no serious impact on the overall plans. There is some impact on financial performance year to date, however this is being mitigated by financial contingency. CCGs are actively working to put in place schemes for the latter part of the year and expect to still hit target by year end. Remedial QIPP plans all signed-off and implementation began in August 12. | Overall milestones are on track across the whole QIPP Programme. QIPP financial delivery is above plan at County PCT although there is variance in overall delivery across workstreams. City PCT are under performing against their QIPP plan as a result of planned care follow up targets and an increase in emergency admissions. CCGs have a clinical review underway as a mitigating action. Elective Inpatient activity is under performing whilst Day Case activity is over performing. Non Elective activity continues to overperform against plan with mitigating actions including clinical reviews in specialties of over performance.
Overall RAG rating for PCT cluster QIPP programme PCT cluster to complete |  |  |  | Amber | Amber | Red | Red | Amber | RAG Rating | RAG Rating
SHA narrative on PCT RAG rating |  |  |  | The SHA and cluster have agreed an amber rating. Finance is on track at month 5 for City and County and for full year expectation. Activity for the cluster is also under plan for all indicators with the exception of NEL and work is underway to investigate and address performance issues via CCGs. Milestones continue to show steady postive progress. | The cluster continues with an amber rating. M5 finance figures remain on track and there has been minimal change in the overall position of milestones. Activity is red-rated but showing some overall improvement in Aug ytd figures. Confirm and challenge sessions have been held with programme leads to gain assurance around QIPP delivery. | The cluster originally rated itself as amber. This has been moderated to red based on QIPP finance month 5 figures showing red and activity for both non-electives and electives also red. Milestones continue to progess steadily and there remains confidence that mitigation around counting and coding and revised clinical thresholds will make a significant impact in terms of recovery by year end combined with bringing projects forward and maximising existing successful schemes. Correction of activity phasing may also impact positively on current performance levels. | The cluster initially rated itself as amber. This has now been revised to red. The M5 financial position is red due to MK. Activity is showing a possible improvement in Aug ytd provisional data for NEL but electives remain amber and referrals red. Milestones are progressing steadily but the impact on activity changes is unclear. 100% QIPP delivery is still forecast for year end and CCGs are putting plans in place to achieve this. | The SHA and PCT have agreed an overall amber rating. Finance at M5 is green for the cluster and milestones are progressing steadily. Activity remains red-rated due to over-performance in key indicators. The cluster is working jointly with CCGs to analyse the link between activity and QIPP schemes.
SHA Quarterly assurance of QIPP delivery |  |  |  | Comments
i. Confirmation that all elements of assurance as set out in the planning round have been transposed into the QIPP milestone tracker
ii. Quarterly assessment of progress in delivering transactional change completed. Supported by evidence of impact demonstrated through finance, activity, performance and workforce change whilst maintaining or improving quality
iii. Quarterly assessment of progress in delivering transformational change completed. Supported by evidence that in-year milestones which are required ensure delivery in 2013-14 and 2014-15, (e.g. those associated with building the case for reconfiguration or invest to save schemes), are on track.
Q1 - Quarterly Overall RAG rating for QIPP programme To be completed by SHA cluster |  |  |  | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating
Q2 - Quarterly Overall RAG rating for QIPP programme To be completed by SHA cluster |  |  |  | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating
Q3- Quarterly Overall RAG rating for QIPP programme To be completed by SHA cluster |  |  |  | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating
Q4- Quarterly Overall RAG rating for QIPP programme To be completed by SHA cluster |  |  |  | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating | RAG Rating

## Derbyshire_QIPPmilestones
2012- 2013 Milestone Tracker |  |  | Acute Contracts (Elective) | [32 empty] | Acute Contracts (Non Elective) | [32 empty] | Acute Contracts (Outpatients) | [32 empty] | Acute contracts (other) | [32 empty] | Primary Care Prescribing | [32 empty] | Mental Health & Learning Disabilities Contracts | [32 empty] | Community Contracts
QIPP Overview and finances
SHA cluster: |  | NHS Midlands and East
PCT Cluster : |  | Derbyshire
Number of CCGs in cluster: |  | 4
Report for the month of:
QIPP Challenge (£000s) |  | 101300
FIMS Plan: Savings for CSR period (£000s) |  | 293466
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s) |  | 94805
Yr 2 Plan FIMS savings for 2012-13 (£000s) |  | 84511
Yr 3 Plan FIMS savings for 2013-14 (£000s) |  | 58075
Yr 4 Plan FIMS savings for 2014-15 (£000s) |  | 56075
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 293466
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be <50% of years 2-4 (Cells C11:C13)) |  | 139380
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale | PCT cluster |  | Title | Tackling unwarranted variation for elective care and reforming primary care | [28 empty] | Scale | PCT cluster |  | Title | Tackling unwarranted variation for non elective care and improving urgent care | [28 empty] | Scale | PCT cluster |  | Title | Tackling unwarranted variation for elective care (outpatients) | [28 empty] | Scale | PCT cluster |  | Title | Tackling unwarranted variation for elective care (other) | [28 empty] | Scale | PCT cluster |  | Title | Tackling unwarranted variation for primary care prescribing | [28 empty] | Scale | PCT cluster |  | Title | Improving mental health and learning disabilities | [28 empty] | Scale | PCT cluster |  | Title | Integrated Care
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings | Acute Contracts (Elective) | Estimated savings 2012-13 (£000's) | 15437 | Estimated savings 2013-14 (£000's) | 9223 | Estimated savings 2014-15 (£000's) | 8587 | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings | Acute Contracts (Non Elective) | Estimated savings 2012-13 (£000's) | 13540 | Estimated savings 2013-14 (£000's) | 8949 | Estimated savings 2014-15 (£000's) | 8560 | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings | Acute Contracts (Outpatients) | Estimated savings 2012-13 (£000's) | 8151 | Estimated savings 2013-14 (£000's) | 6171 | Estimated savings 2014-15 (£000's) | 6091 | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings | Acute Contracts (Other) | Estimated savings 2012-13 (£000's) | 6055 | Estimated savings 2013-14 (£000's) | 4330 | Estimated savings 2014-15 (£000's) | 4221 | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings | Primary Care Prescribing | Estimated savings 2012-13 (£000's) | 4706 | Estimated savings 2013-14 (£000's) | 2786 | Estimated savings 2014-15 (£000's) | 2587 | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings | Mental Health & Learning Disabilities Contracts | Estimated savings 2012-13 (£000's) | 5411 | Estimated savings 2013-14 (£000's) | 3465 | Estimated savings 2014-15 (£000's) | 3288 | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings | Community Contracts | Estimated savings 2012-13 (£000's) | 7048 | Estimated savings 2013-14 (£000's) | 5414 | Estimated savings 2014-15 (£000's) | 5360 | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 | 15437 | FIMS savings 2013-14 | 9223 | FIMS savings 2014-15 | 8587 | Total for CSR period | 33247 | [25 empty] | FIMS savings 2012-13 | 13540 | FIMS savings 2013-14 | 8949 | FIMS savings 2014-15 | 8560 | Total for CSR period | 31049 | [25 empty] | FIMS savings 2012-13 | 8151 | FIMS savings 2013-14 | 6171 | FIMS savings 2014-15 | 6091 | Total for CSR period | 20413 | [25 empty] | FIMS savings 2012-13 | 6055 | FIMS savings 2013-14 | 4330 | FIMS savings 2014-15 | 4221 | Total for CSR period | 14606 | [25 empty] | FIMS savings 2012-13 | 4706 | FIMS savings 2013-14 | 2786 | FIMS savings 2014-15 | 2587 | Total for CSR period | 10079 | [25 empty] | FIMS savings 2012-13 | 5411 | FIMS savings 2013-14 | 3465 | FIMS savings 2014-15 | 3288 | Total for CSR period | 12164 | [25 empty] | FIMS savings 2012-13 | 7048 | FIMS savings 2013-14 | 5414 | FIMS savings 2014-15 | 5360 | Total for CSR period | 17822
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative. |  |  |  |  | Total number of FFCEs increase by 1268 / 0.9% over 3 year period, well below antcipated growth levels. | CCGs agree practice 2012/13 targets that support achievement of annual CCG target to reduce variation in elective care. Achievement of targets to be reviewed on a quarterly basis and recovery plans agreed with practices not achieving targets. | Each CCG to use local spend / outcome analysis (and/or NHS Atlas) to identify 4 programme areas in which to reduce variation in 2013/14. | Engagement with primary care stakeholders to commence development of future models of primary care that improve all aspects of care | Primary and seconday care clinicians (e.g. clinical improvement groups) hold event to agree 2013/14 pathway changes, based on best clinical evidence, to reduce variation identified through outcomes / spend analysis and the NHS Atlas. | CCGs, practices and cluster direct commissioning team agree model for high quality, consistent and proactive primary care improve all aspects of care | Detailed plans in place to deliver 2013/14 pathway improvements to support reduced variation. | Productive practice programme commenced in 60% of practices within North Derbyshire CCG. | Detailed 2013/14 implementation plan in place to achieve agreed model for high quality, consistent and proactive primary care to improve all aspects of care | CCGs achieve 2012/13 annual target to reduce variation in elective care. | CCGs agree practice 2013/14 targets that support achievement of annual CCG target to reduce variation in elective care. Achievement of targets to be reviewed on a quarterly basis and recovery plans agreed with practices not achieving targets. | Commence implementation of detailed 2013/14 implementation plan to reform primary care. To include productive practice dependent on favourable evaluation from North Derbyshire 2012/13 programme. | Each CCG to use local spend / outcome analysis (and/or NHS Atlas) to identify 4 programme areas in which to reduce variation in 2014/15. | Primary and seconday care clinicians (e.g. clinical improvement groups) hold event to agree 2014/15 pathway changes, based on best clinical evidence, to reduce variation identified through outcomes / spend analysis and the NHS Atlas. | Detailed plans in place to deliver 2014/15 pathway improvements to support reduced variation. | Detailed 2014/15 implementation plan in place to achieve agreed model for high quality, consistent and proactive primary care | CCGs achieve 2013/14 annual target to reduce variation in elective care. | CCGs agree practice 2014/15 targets that support achievement of annual CCG target to reduce variation in elective care. Achievement of targets to be reviewed on a quarterly basis and recovery plans agreed with practices not achieving targets. | Commence implementation of detailed 2014/15 implementation plan to reform primary care. To include productive practice dependent on favourable evaluation from North Derbyshire 2012/13 programme. | Each CCG to use local spend / outcome analysis (and/or NHS Atlas) to identify 4 programme areas in which to reduce variation in 2015/16. | Primary and seconday care clinicians (e.g. clinical improvement groups) hold event to agree 2015/16 pathway changes, based on best clinical evidence, to reduce variation identified through outcomes / spend analysis and the NHS Atlas. | Detailed plans in place to deliver 2015/16 pathway improvements to support reduced variation. | Detailed 2015/16 implementation plan in place to achieve agreed model for high quality, consistent and proactive primary care | CCGs achieve 2014/15 annual target to reduce variation in elective care. | [6 empty] | Early indications of activity vs plan in the City is an issue which is being addressed as described below. Engagement of primary care stakeholders to commence development of future models of primary care has not been completed in July. Each CCG has a local approach to achieving high quality primary care e.g. CCG practice visits, productive practice. It is likely that there will be a more systematic approach through the NHS CB and CCGs in response to ‘Securing excellence in commissioning primary care’. All milestones related to this are therefore under review. There are some delays with specific elements as CCGs adapt / refine approach. CCGs are still considering their approach to addressing variation identified in the commissioning for value packs and clearly this is delaying implementation. This is not expected to impact on 2012/13 achievement of QIPP therefore the overall RAG rating is considered GREEN. |  |  | Non-Elective FFCEs only increase by 2329 over 3 years, which is 2.2% of total, and below antcipated growth levels. | CCGs agree practice 2012/13 targets that support achievement of annual CCG target to reduce variation in non elective care. Achievement of targets to be reviewed on a quarterly basis and recovery plans agreed with practices not achieving targets. | SD CCG / DHFT implemented fast track to CDU for 6 clinical pathways. | Roll out D-Dimer complete | Finalise single Derbyshire detailed proposal for urgent care. | Single point of access in place in North Derbyshire and South Derbyshire | Proactive case management in place in Erewash CCG for patients living with LTC | CCGs to agree model for proactive case management underpinned by reform of primary care | Detailed 2013/14 implementation plan for urgent care in place based on outcome of consultation. | Complete full roll out of 111 | CCGs agree practice 2013/14 targets that support achievement of annual CCG target to reduce variation in non elective care. | Commence implementation of detailed plan for urgent care in 2013/14. | Detailed 2014/15 implementation plan for urgent care in place | CCGs achieve 2013/14 annual target to reduce variation in non elective care. | CCGs agree practice 2014/15 targets that support achievement of annual CCG target to reduce variation in non elective care. | Commence implementation of detailed plan for urgent care in 2014/15. | Detailed 2015/16 implementation plan for urgent care in place | CCGs achieve 2014/15 annual target to reduce variation in non elective care. | [12 empty] | Early indications of activity vs plan in the County is an issue which is being addressed as described below. CCGs are leading a number of initiatives in this area to address performance (e.g. A&E) and streamline access (e.g. 111, single point of access). Development of a broader strategy to streamline urgent access needs to progress in line with the outcomes of the 21st Century consultation and other system transformations (e.g. integrated care, reform of primary care). The delays in producing and overall urgent care strategy should not impact on QIPP delivery in 2012/13 or 2013/14. Activity above plan for the County in M4 indicates this should be raised to AMBER. |  |  | First outpatients will only increase by 0.7% / 1641 over 3 years to 247,229, generating savings due to savings below anticipated growth levels. | CCGs agree practice 2012/13 targets that support achievement of annual CCG target to reduce variation in outpatients. Achievement of targets to be reviewed on a quarterly basis and recovery plans agreed with practices not achieving targets. | Each CCG to use local spend / outcome analysis (and/or NHS Atlas) to identify 4 programme areas in which to reduce variation in 2013/14. | Primary and seconday care clinicians (e.g. clinical improvement groups) hold event to agree 2013/14 pathway changes, based on best clinical evidence, to reduce variation identified through outcomes / spend analysis and the NHS Atlas. | Detailed plans in place to deliver 2013/14 pathway improvements to support reduced variation. | CCGs achieve 2012/13 annual target to reduce variation in elective care. | CCGs agree practice 2013/14 targets that support achievement of annual CCG target to reduce variation in other acute contracts care. Achievement of targets to be reviewed on a quarterly basis and recovery plans agreed with practices not achieving targets. | Each CCG to use local spend / outcome analysis (and/or NHS Atlas) to identify 4 programme areas in which to reduce variation in 2014/15. | Primary and seconday care clinicians (e.g. clinical improvement groups) hold event to agree 2014/15 pathway changes, based on best clinical evidence, to reduce variation identified through outcomes / spend analysis and the NHS Atlas. | Detailed plans in place to deliver 2014/15 pathway improvements to support reduced variation. | CCGs achieve 2013/14 annual target to reduce variation in elective care. | CCGs agree practice 2014/15 targets that support achievement of annual CCG target to reduce variation in other acute contracts care. Achievement of targets to be reviewed on a quarterly basis and recovery plans agreed with practices not achieving targets. | Each CCG to use local spend / outcome analysis (and/or NHS Atlas) to identify 4 programme areas in which to reduce variation in 2015/16. | Primary and seconday care clinicians (e.g. clinical improvement groups) hold event to agree 2015/16 pathway changes, based on best clinical evidence, to reduce variation identified through outcomes / spend analysis and the NHS Atlas. | Detailed plans in place to deliver 2015/16 pathway improvements to support reduced variation. | CCGs achieve 2014/15 annual target to reduce variation in elective care. | [14 empty] | Early indications of activity vs plan in the City is an issue which is being addressed as described below. |  |  | Total number of FFCEs increase by 1268 / 0.9% over 3 year period, well below antcipated growth levels. | CCGs agree practice 2012/13 targets that support achievement of annual CCG target to reduce variation in other acute contracts care. Achievement of targets to be reviewed on a quarterly basis and recovery plans agreed with practices not achieving targets. | Each CCG to use local spend / outcome analysis (and/or NHS Atlas) to identify 4 programme areas in which to reduce variation in 2013/14. | Primary and seconday care clinicians (e.g. clinical improvement groups) hold event to agree 2013/14 pathway changes, based on best clinical evidence, to reduce variation identified through outcomes / spend analysis and the NHS Atlas. | Detailed plans in place to deliver 2013/14 pathway improvements to support reduced variation. | CCGs achieve 2012/13 annual target to reduce variation in other acute care. | CCGs agree practice 2013/14 targets that support achievement of annual CCG target to reduce variation in other acute contract spend. Achievement of targets to be reviewed on a quarterly basis and recovery plans agreed with practices not achieving targets. | Each CCG to use local spend / outcome analysis (and/or NHS Atlas) to identify 4 programme areas in which to reduce variation in 2014/15. | Primary and seconday care clinicians (e.g. clinical improvement groups) hold event to agree 2014/15 pathway changes, based on best clinical evidence, to reduce variation identified through outcomes / spend analysis and the NHS Atlas. | Detailed plans in place to deliver 2013/14 pathway improvements to support reduced variation. | CCGs achieve 2013/14 annual target to reduce variation in other acute contract spend. | CCGs agree practice 2014/15 targets that support achievement of annual CCG target to reduce variation in other acute contract spend. Achievement of targets to be reviewed on a quarterly basis and recovery plans agreed with practices not achieving targets. | Each CCG to use local spend / outcome analysis (and/or NHS Atlas) to identify 4 programme areas in which to reduce variation in 2015/16. | Primary and seconday care clinicians (e.g. clinical improvement groups) hold event to agree 2015/16 pathway changes, based on best clinical evidence, to reduce variation identified through outcomes / spend analysis and the NHS Atlas. | Detailed plans in place to deliver 2015/16 pathway improvements to support reduced variation. | CCGs achieve 2014/15 annual target to reduce variation in other acute contract spend. | [14 empty] | Issues and risks associated with activity as described for elective, non elective and outpatient programmes. |  |  | Reduction in GP Prescribing costs by £5,982,000 over 3 year period (excluding growth) | CCGs agree practice 2012/13 targets that support achievement of annual CCG target to reduce variation in prescribing. Achievement of targets to be reviewed on a quarterly basis and recovery plans agreed with practices not achieving targets. | CCG review secondary care prescribing performance and agree action plans where above agreed / affordable plans. | CCGs to idenitfy practice targets for reducing variation in prescribing in 2013/14. | CCGs achieve 2012/13 annual target to reduce variation in prescribing. | CCGs agree practice 2013/14 targets that support achievement of annual CCG target to reduce variation in prescribing. Achievement of targets to be reviewed on a quarterly basis and recovery plans agreed with practices not achieving targets. | CCG review secondary care precribing performance and agree action plans where above agreed / affordable plans. | CCGs to idenitfy practice targets for reducing variation in prescribing in 2014/15. | CCGs achieve 2013/14 annual target to reduce variation in prescribing. | CCGs agree practice 2014/15 targets that support achievement of annual CCG target to reduce variation in prescribing. Achievement of targets to be reviewed on a quarterly basis and recovery plans agreed with practices not achieving targets. | CCG review secondary care prescribing performance and agree action plans where above agreed / affordable plans. | CCGs to idenitfy practice targets for reducing variation in prescribing in 2015/16. | CCGs achieve 2014/15 annual target to reduce variation in prescribing. | [17 empty] | None to report. |  |  | Reduction of MH independent contracts by £3,644,000 over 3 year period | Complete snapshot exercise to forecast expected date of discharge for current patient caseload and produce quarterly plan for 2012/13. Commence implementation of 2012/13 individual patient placement programme | Achieve forecast number of patients repatriated to Derbyshire by the end of quarter 1 2012/13 | System wide strategy agreed which responds to 'no health without mental health' and programme budgetting intelligence | Achieve forecast number of patients repatriated to Derbyshire by the end of quarter 2 2012/13 | Detailed implementation plans in place to improve quality and value in MH priority areas during 2013/14. | Achieve forecast number of patients repatriated to Derbyshire by the end of quarter 3 2012/13 | Achieve forecast number of patients repatriated to Derbyshire by the end of quarter 4 2012/13 | Commence implementation of 2013/14 plan to improve quality and value in mental health Complete snapshot exercise to forecast expected date of discharge for current patient caseload and produce quarterly plan for 2013/14. | Achieve forecast number of patients repatriated to Derbyshire by the end of quarter 1 2013/14 | Achieve forecast number of patients repatriated to Derbyshire by the end of quarter 2 2013/14 | Achieve forecast number of patients repatriated to Derbyshire by the end of quarter 3 2013/14 | Detailed implementation plans in place to improve quality and value in MH priority areas during 2014/15. | Achieve forecast number of patients repatriated to Derbyshire by the end of quarter 4 2013/14 | Commence implementation of 2014/15 plan to improve quality and value in mental health Complete snapshot exercise to forecast expected date of discharge for current patient caseload and produce quarterly plan for 2014/15 | Achieve forecast number of patients repatriated to Derbyshire by the end of quarter 1 2014/15 | Achieve forecast number of patients repatriated to Derbyshire by the end of quarter 2 2014/15 | Achieve forecast number of patients repatriated to Derbyshire by the end of quarter 3 2014/15 | Detailed implementation plans in place to improve quality and value in MH priority areas during 2015/16 | Achieve forecast number of patients repatriated to Derbyshire by the end of quarter 4 2014/15 | [10 empty] | The main risk is that achievement of plans for individual patients is delayed resulting in a smaller part year effect of the quality and financial benefits. This is being mitgated through close management of implementation against individual patient plans. Further opportunities are also being explored e.g. rapid assessment, interface and discharge (RAID) and acute liaison. The joint commissioning board plan to develop a system wide strategy in response 'no health without mental health' has been revised with events planned in the September the City and County. Whilst the overall strategy is therefore not expected until November this is not considered a risk to delivery of the plan in 2013/14. |  |  | Financial savings of £7,024,000 over a 3 year period. | Complete '21st Century Healthcare' consultation to agree system wide principles/values underpinning service transformation. | Agreed high level strategy for integrated care for the North and South of the County | Completed first iteration of detailed proposals for Integrated Care in the North and South | Derbyshire strategic workforce group (DSWG) complete 5 year workforce plan | Finalised detailed proposals for integrated care transformation in the North and South of the County | Improved case management for frail elderly in place in North Derbyshire | Mobile working in place with district nursing staff for Southern Derbyshire / Erewash CCG population | Detailed 2013/14 implementation plan for integrated care in place based on outcome of consultation. | 2013/14 implementation of integrated care reflected in CCG contracts with providers | Commence implementation of detailed plan for integrated care in 2013/14. | Complete integrated care implementation actions for first quarter of 2013/14. | Derbyshire strategic workforce group (DSWG) complete 5 year workforce plan | Complete integrated care implementation actions for second quarter of 2013/14. | Complete integrated care implementation actions for third quarter of 2013/14. | Complete integrated care implementation actions for fourth quarter of 2013/14. | Commence implementation of detailed plan for integrated care in 2014/15. | Complete integrated care implementation actions for first quarter of 2014/15. | Derbyshire strategic workforce group (DSWG) complete 5 year workforce plan | Complete integrated care implementation actions for second quarter of 2014/15. | Complete integrated care implementation actions for third quarter of 2014/15. | Complete integrated care implementation actions for fourth quarter of 2014/15. | [8 empty] | The approach in the North and South has been reviewed with the result that there will be a more modular approach to implementation (in managable chunks) in 2012/13. Due to the complexity of the overall integrated care programme, delays are now expected in the detailed design, formal public consultation and development or robust implementation plans in 2012/13 to 2013/14. This is expected to have a knock on delay to implementation in 2013/14. The cluster is supporting CCG leaders to redefine the programme plan for integrated care and reset milestones. The AMBER rag rating is based on the significant delay in the overall programme.
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones |  |  | Total number of FFCEs in the period | [32 empty] | Number of G&A non-elective FFCEs in the period | [32 empty] | All first outpatient attendances (consultant-led) in general and acute specialties
(UNIFY indicators) Anticipated performance at period end |  |  | 145548 | 147250 | 147014 | [30 empty] | 107242 | 108684 | 109474 | [30 empty] | 243466 | 245785 | 247229
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s))) |  |  | Number of elective FFCEs - ordinary admissions | [65 empty] | Number of 1st outpatient attendances (consultant-led) following GP referral in general and acute specialties
(Other KPIs) Anticipated performance at period end |  |  | 27594 | 28337 | 29004 | [63 empty] | 148292 | 150043 | 151915
QIPP Initiative Reporting
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-02-28 | 2015-03-31 | [7 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | 2015-03-31 | [13 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [15 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [15 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-09-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-09-30 | 2015-01-31 | 2015-03-31 | [18 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-07-31 | 2012-08-31 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-01-31 | 2015-03-31 | [11 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-08-31 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-03-31
Progress reporting against milestones and Initiative 1 |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall progress of the initiative along with risks, issues and mitigating actions where relevant ▪ Quarterly (required) Report overall progress of the initiative and supporting workstreams including an assessment of progress against performance indicators and finance. Include narrative on risks, issues and mitigating actions where relevant |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (optional) to report overall progress of the initiative along with risks, issues and mitigating actions ▪ Quarterly (required) and should give narrative on overall progress of the initiative and supporting workstreams. It should include an assessment of progress against performance indicators, and finance along with risks and mitigating actions |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (optional) to report overall progress of the initiative along with risks, issues and mitigating actions ▪ Quarterly (required) and should give narrative on overall progress of the initiative and supporting workstreams. It should include an assessment of progress against performance indicators, and finance along with risks and mitigating actions |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (optional) to report overall progress of the initiative along with risks, issues and mitigating actions ▪ Quarterly (required) and should give narrative on overall progress of the initiative and supporting workstreams. It should include an assessment of progress against performance indicators, and finance along with risks and mitigating actions |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (optional) to report overall progress of the initiative along with risks, issues and mitigating actions ▪ Quarterly (required) and should give narrative on overall progress of the initiative and supporting workstreams. It should include an assessment of progress against performance indicators, and finance along with risks and mitigating actions |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (optional) to report overall progress of the initiative along with risks, issues and mitigating actions ▪ Quarterly (required) and should give narrative on overall progress of the initiative and supporting workstreams. It should include an assessment of progress against performance indicators, and finance along with risks and mitigating actions |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (optional) to report overall progress of the initiative along with risks, issues and mitigating actions ▪ Quarterly (required) and should give narrative on overall progress of the initiative and supporting workstreams. It should include an assessment of progress against performance indicators, and finance along with risks and mitigating actions |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber
[8 empty] | Each CCG has a local approach to working with member practices to achieve high quality and consistent primary care e.g. CCG practice visits, productive practice. This has not yet been developed into a single vision as it is likely that there will be a more systematic approach once the NHS CB is established and working under a single model and has an effective interface with CCGs. All milestones related to this are therefore under review. | CCGs are still considering how to respond to the commissioning for value packs and hence have not yet held these events with secondary care clinicians and other stakeholders. There are however clinical improvement groups in place with primary and secondary care clinicians working together to address specific areas of variation. CCGs to identify approach and potential dates as part of 13/14 planning. No forecast date can be reliably provided at this stage. | As LM1.3 | As LM1.4 |  | As LM1.3 |  |  | As LM1.3 |  |  |  | Superceded by LM1.8 |  |  | Superseded by LM1.12 | [11 empty] | Programme & initiatives are progressing in line with schedule. There are some delays with specific elements as CCGs adapt / refine approach. M4 financials indicate no significant issues with full QIPP delivery expected for City and County. M4 MAR (UNIFY) indicates the following cumulative trend: - All elective activity at or below plan (and 2011/12) for County PCT - GP and other referrals above plan (and 2011/12) for City PCT. This is reflected in contract activity with Derby Hospitals NHS FT (DHFT). NHS Southern Derbyshire, supported by the cluster PMO, are investigating this referral pattern to understand the trend and plan mitigating actions. - Elective activity is above plan (although equivalent to 2011/12) for the City PCT. This is due to additional daycase activity at DHFT in May to ensure waiting lists/times remain within the RTT standards. Activity and waiting times will continue to be monitored to ensure performance is achieved within affordable limits. | [6 empty] | CCGs are leading a number of initiatives in this area to address performance (e.g. A&E) and streamline access (e.g. 111, single point of access). Development of a broader strategy to streamline urgent access needs to progress in line with the outcomes of the 21st Century consultation and other system transformations(e.g. integrated care, reform of primary care). CCGs are reviewing this and will consider this as part of their planning for 2013/14 and beyond. This is not likely to impact on 2012/13 delivery as individual urgent care initiatives are being progressed by CCGs. | Implementation and roll out slightly behind schedule but will be in place by November as part of the winter plan. |  |  | As LM2.4 | [21 empty] | Programme & initiatives are progressing in line with schedule. M4 financials indicate no significant issues with full QIPP delivery expected for City and County. M4 MAR (UNIFY) indicates the following cumulative trend: - Non elective activity is below plan (and 2011/12) for City PCT. - Non elective activity is above plan (and 2011/12) for County PCT. Some providers have understated activity in their 2012/13 plans which has contributed to a small understatement of the County PCT level plan. This only has marginal contribution to the over performance being experienced. The over performance is most noticable at Nottingham (NUH), Chesterfield (CRHFT), Sherwood Forest Hospitals and Derbyshire Community Health Services (DCHS). In most cases the impact of QIPP schemes was not phased until month 6 so non delivery of QIPP is not considered to be the issue. The four CCGs, supported by the cluster PMO, are investigating this over performance to understand the underlying causes and plan mitigating actions. | [5 empty] | CCGs are still considering how to respond to the commissioning for value packs and hence have not yet held these events with secondary care clinicians and other stakeholders. There are however clinical improvement groups in place with primary and secondary care clinicians working together to address specific areas of variation. CCGs to identify approach and potential dates as part of 13/14 planning. No forecast date can be reliably provided at this stage. | [26 empty] | Programme & initiatives are progressing in line with schedule. M4 financials indicate no significant issues with full QIPP delivery expected for City and County. M4 MAR (UNIFY) indicates the following cumulative trend: - Elective outpatient activity is cumulatively above plan for the City although below 2011/12 levels). There has been a particular increase in outpatients in July which is understood to relate to the increase in GP and other referrals seen in earlier months. This will continue to be monitored closely particularly in relation to it resulting in increased elective activity later in the year.Activity and waiting times will continue to be monitored to ensure performance is achieved within affordable limits. | [5 empty] | CCGs are still considering how to respond to the commissioning for value packs and hence have not yet held these events with secondary care clinicians and other stakeholders. There are however clinical improvement groups in place with primary and secondary care clinicians working together to address specific areas of variation. CCGs to identify approach and potential dates as part of 13/14 planning. No forecast date can be reliably provided at this stage. | [26 empty] | Programme/initiative progressing in line with schedule. | [32 empty] | QIPP Programme/initiative progressing in line with schedule. 2% non recurrent has been deployed to support medicines management programmes within CCGs. Prescribing performance is monitored at CCG level on a monthly basis and shared with CCG Governing Body and individual practices via the locality GP prescribing leads. Monthly reports (produced by the Eclipse system) are provided at practice level giving a further breakdown of financial and quality prescribing indicators, highlighting clinical variation and monitoring success of specific prescribing projects. | [5 empty] | The joint commissioning board plan to develop a system wide strategy in response 'no health without mental health' has been revised with events planned in the September the City and County. Whilst the overall strategy is therefore not expected until November this is not considered a risk to delivery of the plan in 2013/14. |  | See LM6.3 | [24 empty] | Programme/initiative progressing in line with schedule. Individual patient programme progressing in line with plan and planned savings to date have been achieved. | [6 empty] | A 2012/13 workforce plan has been produced by the end of July and this milestone is therefore considered complete. | Due to the complexity of the overall integrated care programme, delays are now expected in the detailed design, formal public consultation and development or robust implementation plans in 2012/13 to 2013/14. This is expected to have a knock on delay to implementation in 2013/14. The cluster is supporting CCG leaders to redefine the programme plan for integrated care and reset milestones. |  |  | See LM7.9 | See LM7.9 | See LM7.9 | [19 empty] | Due to the complexity of the overall integrated care programme, delays are now expected in the detailed design, formal public consultation and development or robust implementation plans in 2012/13 to 2013/14. This is expected to have a knock on delay to implementation in 2013/14.
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Delayed - amber | Delayed - amber | Delayed - amber | Delayed - amber | In progress | Delayed - amber | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | [7 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Delayed - amber | Delayed - amber | In progress | In progress | Delayed - amber | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | [13 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Delayed - amber | Delayed - amber | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | [15 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Delayed - amber | Delayed - amber | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | [14 empty] | As comments for elective / non elective activity. | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | [18 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Delayed - amber | In progress | Delayed - amber | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | [11 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | Delayed - amber | In progress | In progress | In progress | Delayed - amber | Delayed - amber | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 |  |  |  | 2012-04-30 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-02-28 | 2015-03-31 | [6 empty] | 0 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | 2015-03-31 | [12 empty] | 0 |  |  |  | 2012-04-30 | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [14 empty] | 0 |  |  |  | 2012-04-30 | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [14 empty] | 0 |  |  |  | 2012-04-30 | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-09-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-09-30 | 2015-01-31 | 2015-03-31 | [17 empty] | 0 |  |  |  | 2012-04-30 | 2012-07-31 | 2012-08-31 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-01-31 | 2015-03-31 | [10 empty] | 0 |  |  |  | 2012-05-31 | 2012-05-31 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-08-31 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [8 empty] | 1.0333
| Month 2 | 2012-05-31 |  |  |  | 2012-04-30 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-02-28 | 2015-03-31 | [6 empty] | 0 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | 2015-03-31 | [12 empty] | 0 |  |  |  | 2012-04-30 | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [14 empty] | 0 |  |  |  | 2012-04-30 | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [14 empty] | 0 |  |  |  | 2012-04-30 | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-09-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-09-30 | 2015-01-31 | 2015-03-31 | [17 empty] | 0 |  |  |  | 2012-04-30 | 2012-07-31 | 2012-08-31 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-01-31 | 2015-03-31 | [10 empty] | 0 |  |  |  | 2012-06-30 | 2012-05-31 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-08-31 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [8 empty] | 2.0333
| Month 3 | 2012-06-30 |  |  |  |  | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-02-28 | 2015-03-31 | [6 empty] | 0 | [5 empty] | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | 2015-03-31 | [12 empty] | 0 |  |  |  |  | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [14 empty] | 0 |  |  |  |  | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [14 empty] | 0 |  |  |  |  | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-09-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-09-30 | 2015-01-31 | 2015-03-31 | [17 empty] | 0 |  |  |  |  | 2012-07-31 | 2012-08-31 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-01-31 | 2015-03-31 | [10 empty] | 0 |  |  |  | 2012-06-30 |  | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-08-31 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [8 empty] | 2.0333
| Month 4 | 2012-07-31 | [5 empty] | 2013-07-31 | 2012-09-30 | 2013-10-31 | 2012-12-31 | 2013-01-31 | 2014-02-28 | 2013-03-31 | 2013-04-30 | 2014-05-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-02-28 | 2015-03-31 | [6 empty] | 48.6667 | [5 empty] | 2012-08-31 | 2013-03-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | 2015-03-31 | [12 empty] | 7.1 | [5 empty] | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [14 empty] | 0 | [5 empty] | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [14 empty] | 0 |  |  |  |  | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-09-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-09-30 | 2015-01-31 | 2015-03-31 | [17 empty] | 0 |  |  |  |  | 2012-07-31 | 2013-11-30 | 2012-10-31 | 2013-02-28 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-01-31 | 2015-03-31 | [10 empty] | 17.1667 | [6 empty] | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-08-31 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [8 empty] | 0
| Month 5 | 2012-08-31 | [5 empty] | 2013-07-31 | 2012-09-30 | 2013-10-31 | 2012-12-31 | 2013-01-31 | 2014-02-28 | 2013-03-31 | 2013-04-30 | 2014-05-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-02-28 | 2015-03-31 | [6 empty] | 48.6667 | [5 empty] | 2012-08-31 | 2013-03-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | 2015-03-31 | [12 empty] | 7.1 | [5 empty] | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [14 empty] | 0 | [5 empty] | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [14 empty] | 0 |  |  |  |  | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-09-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-09-30 | 2015-01-31 | 2015-03-31 | [17 empty] | 0 | [5 empty] | 2013-11-30 | 2012-10-31 | 2013-02-28 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-01-31 | 2015-03-31 | [10 empty] | 17.1667 | [6 empty] | 2012-08-31 | 2013-06-30 | 2012-10-31 | 2012-12-31 | 2013-09-30 | 2014-03-31 | 2014-04-30 | 2013-06-30 | 2013-08-31 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [8 empty] | 41.5
| Month 6 | 2012-09-30 | [5 empty] | 2013-07-31 | 2013-09-30 | 2013-10-31 | 2013-12-31 | 2013-01-31 | 2014-02-28 | 2013-03-31 | 2013-04-30 | 2014-05-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-02-28 | 2015-03-31 | [6 empty] | 73 | [6 empty] | 2013-03-31 | 2012-11-30 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2015-02-28 | 2015-03-31 | [12 empty] | 8.1 | [5 empty] | 2013-09-30 | 2013-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [14 empty] | 24.3333 | [5 empty] | 2013-09-30 | 2013-12-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [14 empty] | 24.3333 |  |  |  |  | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-09-30 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-09-30 | 2015-01-31 | 2015-03-31 | [17 empty] | 0 | [5 empty] | 2013-11-30 | 2012-10-31 | 2013-02-28 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-01-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-01-31 | 2015-03-31 | [10 empty] | 17.1667 | [6 empty] | 2012-08-31 | 2013-06-30 | 2012-10-31 | 2012-12-31 | 2013-09-30 | 2014-03-31 | 2014-04-30 | 2013-06-30 | 2013-08-31 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | 2014-09-30 | 2014-12-31 | 2015-03-31 | [8 empty] | 41.5
| Month 7 | 2012-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [10 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [16 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [18 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [18 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [21 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [14 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Number of CCGs who have completed this milestone | [5 empty] | 4 | 2012-06-30: 4 | [10 empty] | 4 | 4 | 4 | [30 empty] | 4 | 4 | [31 empty] | 4 | 4 | [31 empty] | 4 | 4 | [31 empty] | 4 | 4 | [31 empty] | 4 | 4 | 4 | 4
Percentage of PCTs completing this milestone |  |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Leicestershire_QIPPmilestones
2012- 2013 Milestone Tracker |  |  | Acute Contracts (Elective) | [32 empty] | Acute Contracts (Non Elective) | [32 empty] | Acute Contracts (Outpatients) | [32 empty] | Primary Care Prescribing | [32 empty] | Mental Health & Learning Disabilities Contracts
QIPP Overview and finances
SHA cluster: |  | NHS Midlands and East
PCT Cluster : |  | Leicestershire
Number of CCGs in cluster: |  | 3
Report for the month of: |  | 2012-09-30
QIPP Challenge (£000s) |  | 69200
FIMS Plan: Savings for CSR period (£000s) |  | 252177
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s) |  | 65668
Yr 2 Plan FIMS savings for 2012-13 (£000s) |  | 58649
Yr 3 Plan FIMS savings for 2013-14 (£000s) |  | 58980
Yr 4 Plan FIMS savings for 2014-15 (£000s) |  | 68880
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 252177
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be >50% of years 2-4 (Cells C10:C12)) |  | 125650
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 | 1313 | FIMS savings 2013-14 | 1847 | FIMS savings 2014-15 | 3076 | Total for CSR period | 6236 | [25 empty] | FIMS savings 2012-13 | 5571 | FIMS savings 2013-14 | 7835 | FIMS savings 2014-15 | 13052 | Total for CSR period | 26458 | [25 empty] | FIMS savings 2012-13 | 1490 | FIMS savings 2013-14 | 2096 | FIMS savings 2014-15 | 3491 | Total for CSR period | 7077 | [25 empty] | FIMS savings 2012-13 | 6076 | FIMS savings 2013-14 | 5000 | FIMS savings 2014-15 | 5000 | Total for CSR period | 16076 | [25 empty] | FIMS savings 2012-13 | 14750 | FIMS savings 2013-14 | 20650 | FIMS savings 2014-15 | 34403 | Total for CSR period | 69803 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 13-14 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative. |  |  |  |  | f | Commence agreement process for Individual Practice Targets for Delivery (clinical variation) | Provide SPACE manuals to COPD patients being discharged form an acute setting and to primary care clinicians. | Individual Practice Targets agreed for Delivery (clinical variation). Implement COPD discharge bundle for all discharged patients. | Commence clinical review of patient records within primary care to determine the accuracy of COPD patient list using OPC reporting. Completion by Q4 | All GP Practices to review patients discharged from hospital within 2 weeks of discharge where the cause for admission was COPD. | Agree COPD telehealth and telecare opportunities | Completion of patient record review to determine accuracy of COPD patient list. Part of normal working practice moving forward | Commence rollout to all GP Practices of new 13/14 surgical thresholds and new outpatient referral protocols. | Commence PQQ stage for West Leicestershire community care bundle | Undertake clinical audit (if required) to check impact upon quality and adherence to agreed thresholds and protocols | Commence ITT stage for West Leicester community care bundle | Contract award for West Leicestershire community care bundle | Commence rollout to all GP Practices of new 14/15 surgical thresholds and new outpatient referral protocols. | Commence Mobilisation stage for West Leicestershire community care bundle. | Complete mobilisation for West Leicestershire Community Care bundle | [17 empty] | An integrated, efficient, high quality emergency care system that spans across the LLR health economy Reduction of 8390 spells to 14/15 Reduction of 2870 spells in 12/13 | Commence agreement process for Individual Practice Targets for Delivery (clinical variation) | Individual Practice Targets agreed for Delivery (clinical variation) | OPAT pathway live | Local Authority to commission Dementia advisors to support shared care memory assessment pathway | Full evaluation of 'discharge to assess' model | Commence Phase 4 Risk stratification roll out | Commence Phase 1 implementation of telehealth model across LLR description | Commence Phase 3 implementation of proactive care model in LCR | Commence reconfiguration of ED footprint | Commence Final phase of risk stratification project (140 practices in total) | Mobilisation of LLR telecare/telehealth model | Initial evaluation of telecare/telehealth model | Further roll-out and development of telehealth/telecare model | Extention of FOPAL's service to cover all wards in UHL | Complete ED footprint reconfiguration | [17 empty] | Left shift of activity, aimed to improve productivity, patient experience, reduce provider cost base and clinical variation 2015 Reduction of 49832 New / FU In year Reduction of 13,265 New / FU | Provide SPACE manuals to COPD patients being discharged form an acute setting and to primary care clinicians. | Individual Practice Targets agreed for Delivery (clinical variation). Implement COPD discharge bundle for all discharged patients. | Commence clinical review of patient records within primary care to determine the accuracy of COPD patient list using OPC reporting. Completion by Q4 | All GP Practices to review patients discharged from hospital within 2 weeks of discharge where the cause for admission was COPD. | Agree COPD telehealth and telecare opportunities | Completion of patient record review to determine accuracy of COPD patient list. Part of normal working practice moving forward | Commence rollout to all GP Practices of new 13/14 surgical thresholds and new outpatient referral protocols. | Commence PQQ stage for West Leicestershire community care bundle | Undertake clinical audit (if required) to check impact upon quality and adherence to agreed thresholds and protocols | Commence ITT stage for West Leicester community care bundle | Contract award for West Leicestershire community care bundle | Commence rollout to all GP Practices of new 14/15 surgical thresholds and new outpatient referral protocols. | Commence Mobilisation stage for West Leicestershire community care bundle. | Complete mobilisation for West Leicestershire Community Care bundle | [18 empty] | There will be a reduced level of prescribing between 'like' practices. Peer review will help deliver improved quality and sustained improvement in prescribing behaviour. Budget will be set net of saving with an incentive scheme linked to delivery. Total reduction £16.075 million | Commence GP practices signing off scheme. | 100 % of GP practices have signed off scheme. | Achieve £6.075m savings | Commence GP practices signing off scheme. | 100 % of GP practices have signed off scheme. | Achieve £5.0m savings | Commence GP practices signing off scheme. | 100 % of GP practices have signed off scheme. | Achieve £5.0m savings | [23 empty] | Delivery of LLR Vision exemplified by a transformational left shift in care where safe and appropriate to do so. Reconfigured acute work undertaken on 2 Acute sites | Estates & Facilities contract tender Preferred bidder selection | Estates & Facilities contract award. Mobilisation to commence. | Estates & Facilities new contract mobilisation complete | Commence reconfiguration of ED footprint | PQQ stage for West Leicester community care bundle | ITT stage for West Leicester community care bundle | Contract award for West Leicester community care bundle | PID prepared and considered by LLR Trust Boards. Priority pathways agreed | Complete the transfer of services from the Leicester General Hospital site to other settings | Reconfiguration of Leicester General Hospital complete and now focusses upon health and well being for City CCG and outpatients and elective.
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones |  |  | Total number of FFCEs in the period | [32 empty] | Number of G&A non-elective FFCEs in the period | [32 empty] | All first outpatient attendances (consultant-led) in general and acute specialties
(UNIFY indicators) Anticipated performance at period end |  |  | 119579 | 120979 | 122063 | [30 empty] | 85170 | 83265 | 81215 | [30 empty] | 229697 | 231224 | 232309
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s))) |  |  | Number of elective FFCEs - ordinary admissions | [65 empty] | Number of 1st outpatient attendances (consultant-led) following GP referral in general and acute specialties
(Other KPIs) Anticipated performance at period end |  |  | 24301 | 24565 | 24783 | [63 empty] | 138943 | 140748 | 142296
QIPP Initiative Reporting
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-04-30 | 2014-09-30 | [15 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-07-31 | 2014-12-31 | [15 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-04-30 | 2014-09-30 | [16 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-06-30 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2015-03-31 | [21 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-06-30 | 2012-11-30 | 2013-03-31 | 2013-07-31 | 2013-10-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [20 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31
Progress reporting against milestones and Initiative 1 |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall prog |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly ( |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating
[10 empty] | A way forward regarding the identification of COPD patients has now been agreed with UH A comprehensive information pack is being developed for general medical practice whereby the implementation of this aspect of the COPD pathway is outlined | [24 empty] | There are a number of schemes that will impact on elective activity later in the year once new pathways are embedded locally. For instance, CCGs have demand management schemes in place, with new pathways being introduced in Q2. Activity Triagulation: QIPP savings were reduced in the contract negotitations compared to the UNIFY plan. Therefore the UNIFY plan would be higher. | [5 empty] | Delayed by one month while firming up governance arrangements. | [26 empty] | The current status of this programme is Amber. The Transformational Fund schemes in place will impact on non-elective activity. Confirm and Challenge Meetings in September/October have provided assurance to PCT. Work continues with regard to activity pressures & an update will be available in October return. Activity Triangulation: Performance is as a result of an increase in demand. | [6 empty] | A way forward regarding the identification of COPD patients has now been agreed with UH A comprehensive information pack is being developed for general medical practice whereby the implementation of this aspect of the COPD pathway is outlined | [25 empty] | The current status of this programme is Green as progressing to schedule. There are currently no foreseen issues relating to work which has commenced. Activity triagulation: QIPP savings are based on all new outpatients with a small number of exclusions. UNIFY only states GP referred or Consultant led. There is an under-performance in the "Other new outpatients" and QIPP savings were reduced in the contract negotitations compared to the UNIFY plan. Therefore the UNIFY plan would be higher. | [32 empty] | The current status of this programme is Green as progressing to schedule. There are currently no foreseen issues relating to work which has commenced. | [32 empty] | The current status of this programme is Green as progressing to schedule. There are currently no foreseen issues relating to work which has commenced.
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | Completed | [25 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Delayed - amber | [27 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | [26 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | [28 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | [29 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-04-30 | 2014-09-30 | [14 empty] | 0 |  |  |  | 2012-04-30 | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-07-31 | 2014-12-31 | [14 empty] | 0 |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-04-30 | 2014-09-30 | [15 empty] | 0 |  |  |  | 2012-04-30 | 2012-06-30 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2015-03-31 | [20 empty] | 0 |  |  |  | 2012-06-30 | 2012-11-30 | 2013-03-31 | 2013-07-31 | 2013-10-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [19 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2012-05-31 |  |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-04-30 | 2014-09-30 | [14 empty] | 0 |  |  |  |  | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-07-31 | 2014-12-31 | [14 empty] | 0 |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-04-30 | 2014-09-30 | [15 empty] | 0 |  |  |  |  | 2012-06-30 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2015-03-31 | [20 empty] | 0 |  |  |  | 2012-06-30 | 2012-11-30 | 2013-03-31 | 2013-07-31 | 2013-10-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [19 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2012-06-30 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-04-30 | 2014-09-30 | [14 empty] | 0 |  |  |  |  | 2012-06-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-07-31 | 2014-12-31 | [14 empty] | 0 |  |  |  |  | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-04-30 | 2014-09-30 | [15 empty] | 1.0333 |  |  |  |  | 2012-06-30 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2015-03-31 | [20 empty] | 0 |  |  |  | 2012-06-30 | 2012-11-30 | 2013-03-31 | 2013-07-31 | 2013-10-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [19 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2012-07-31 | [6 empty] | 2012-07-31 | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-04-30 | 2014-09-30 | [14 empty] | 0 | [5 empty] | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-07-31 | 2014-12-31 | [14 empty] | 0 | [5 empty] | 2012-07-31 | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-04-30 | 2014-09-30 | [15 empty] | 0 | [5 empty] | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2015-03-31 | [20 empty] | 0 |  |  |  |  | 2012-11-30 | 2013-03-31 | 2013-07-31 | 2013-10-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [19 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2012-08-31 | [7 empty] | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-04-30 | 2014-09-30 | [14 empty] | 0 | [5 empty] | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-07-31 | 2014-12-31 | [14 empty] | 0 | [6 empty] | 2012-09-30 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-04-30 | 2014-09-30 | [15 empty] | 0 | [5 empty] | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2015-03-31 | [20 empty] | 0 |  |  |  |  | 2012-11-30 | 2013-03-31 | 2013-07-31 | 2013-10-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [19 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2012-09-30 | [8 empty] | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-03-31 | 2014-04-30 | 2014-09-30 | [14 empty] | -1 | [5 empty] | 2012-10-31 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-03-31 | 2013-06-30 | 2013-07-31 | 2013-09-30 | 2013-10-31 | 2014-01-31 | 2014-04-30 | 2014-07-31 | 2014-12-31 | [14 empty] | -1 | [7 empty] | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2013-11-30 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-04-30 | 2014-09-30 | [15 empty] | 0 | [5 empty] | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-06-30 | 2015-03-31 | [20 empty] | 0 |  |  |  |  | 2012-11-30 | 2013-03-31 | 2013-07-31 | 2013-10-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [19 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2012-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | [17 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [17 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [23 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [23 empty] | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 2
Number of CCGs who have completed this milestone | [5 empty] | 3 | 3 | 3 | 3 | 3 | [28 empty] | 3 | 3 | [31 empty] | 3 | 3 | 3 | 3 | [29 empty] | 3 | 3
Percentage of PCTs completing this milestone |  |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | 0% | 100% | 100% | [13 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | bar: 2012-09-30 to 2014-12-31

## Lincolnshire_QIPPmilestones
2012- 2013 Milestone Tracker |  |  | Acute Contracts (Elective) | [32 empty] | Acute Contracts (Non Elective) | [32 empty] | Acute Contracts (Outpatients) | [32 empty] | Other | [32 empty] | PCT Running Costs | [32 empty] | Primary Care Prescribing | [32 empty] | Mental Health & Learning Disabilities Contracts
QIPP Overview and finances
SHA cluster: |  | NHS Midlands and East
PCT Cluster : |  | Lincolnshire
Number of CCGs in cluster: |  | 4
Report for the month of: |  | 2012-09-30
QIPP Challenge (£000s) |  | 75917
FIMS Plan: Savings for CSR period (£000s) |  | 161708
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s) |  | 49003
Yr 2 Plan FIMS savings for 2012-13 (£000s) |  | 45948
Yr 3 Plan FIMS savings for 2013-14 (£000s) |  | 34642
Yr 4 Plan FIMS savings for 2014-15 (£000s) |  | 32115
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 161708
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be <50% of years 2-4 (Cells C11:C13)) |  | 76608
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 | 7664 | FIMS savings 2013-14 | 5473 | FIMS savings 2014-15 | 4806 | Total for CSR period | 17943 | [25 empty] | FIMS savings 2012-13 | 11938 | FIMS savings 2013-14 | 8009 | FIMS savings 2014-15 | 6993 | Total for CSR period | 26940 | [25 empty] | FIMS savings 2012-13 | 6046 | FIMS savings 2013-14 | 3983 | FIMS savings 2014-15 | 3717 | Total for CSR period | 13746 | [25 empty] | FIMS savings 2012-13 | 535 | FIMS savings 2013-14 | 174 | FIMS savings 2014-15 | 134 | Total for CSR period | 843 | [25 empty] | FIMS savings 2012-13 | 6 | FIMS savings 2013-14 | 6 | FIMS savings 2014-15 | 6 | Total for CSR period | 18 | [25 empty] | FIMS savings 2012-13 | 1794 | FIMS savings 2013-14 | 1000 | FIMS savings 2014-15 | 750 | Total for CSR period | 3544 | [25 empty] | FIMS savings 2012-13 | 5233 | FIMS savings 2013-14 | 4201 | FIMS savings 2014-15 | 4140 | Total for CSR period | 13574
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 13-14 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative. |  |  |  |  | As a result of improved pathways, there will be a 5% reduction in elective activity in secondary care, despite 0.5% growth in the local population, aging population, increasing and other underlying increases in demand. | ULHT contract signed incorporating Right care eg Ophthalmology pathways for ARMD and other areas. | ULHT contract signed incorporating strict application of Low priority procedure criteria | Implementation of PCSS pathway and thresholds for hip and knee (LE and Sth Holland) | LW- additonal GPwSI recruited to support expansion of triage & treat | (LW) 90% of practices signed up to PCSS pathway | New Spinal Pathway fully implemented | ARMD pathway in place, 90% move from daycase to OP procedure ( -270 daycases PA) | Review of changing thresholds with providers to compensate against activity performance and build intoi contract negotiations. | (LW)5% reduction in secondary care minor surgical procedures | Review status of FT applications with providers and impact on QIPP (across all relevant domains) | Review of progress against benchmarks with providers and review of financial pressures and impact against QIPP. Agreed adjustments across all relevant domains. | Notice of significant contract changes to providers for 14/15 for all domains | Review of changing thresholds with providers to compensate against activity performance and build intoi contract negotiations across all relevant domains. | Review of progress against benchmarks with providers and review of financial pressures and impact against QIPP. Agreed adjustments across all relevant domains. | Notice of significant contract changes to providers for 15/16 for all domains | Review of changing thresholds with providers to compensate against activity performance and build into contract negotiations across all relevant domains | [13 empty] | Potential risk of delay to Spinal services at ULHT until December 2012. Service provision from ULHT dependant on outcome of business case to ULHT Board (deferred in Sept to October Board). No aniticipated risk to maintenance of existing services through One Health. Regarding activity rephasing and coding, ULHT only able to change system at end of first quarter as numbers locked into UNIFY therefore activity may remain unchanged for that period but payments will be adjusted. 52 week waits: In relation to the Community Paediatric long waiters NHSL are working with ULHT to provide either additional capacity or diversion into other services for this cohort, we are awaiting the details of the clinical or other care needs of the group. Triage arrangements have been operating across children’s services for over a year , the build-up of this backlog is unexplained, we are investigating the underlying cause. Review the list of over 52 week waiters will commence in September and will continue on a regular basis to manage this cohort. |  |  | As a result of improved pathways and reduced variation, there will be a 1.5% reduction in non elective admissions to secondary care and a 3% reduction in A&E attendances | Implement Urgent Care Centre in Skegness (LE) | Care Homes Housebound Project implemented in Lincolnshire East to improve LTC management at home and advanced care planning to reduce admissions and A&E attendances | Implement nursing home ward rounds (LE) | Phase 1 capacity management system in place (CMS) | CCG practice visits to targetted practices | Phase 2 CMS, implementation of winter plans | Review impact of nursing home ward rounds (LE) | 30% of practices completing NHSI Productive Practice programme and 2nd tranche sign-up | Frailty service model finalised and negotiated into acute and community contracts for implementation 13/14 | SPA implementation in all sectors and Implement integrated A&E in Grantham | Phase 1 Skegness UCC completed | Integrated MSK/ Pain service in place | Implement Louth day assessment unit - review Sept 2013 (LE) | Shared care arrangements in place for further 5 pathways | variation in referral rates reduced by 15% | 60% of practices completed NHSI Productive Practice programme and 3rd tranche sign up | variation in referral rates reduced by 20% | CQUINs in place for top 25% new to follow up ration performamnce in at least 85% of all specialities | Phase 2 Skegness UCC completed (LE) | Shared care arrangements in place for further 5 pathways | 90% of practices completed NHSI Productive Practice programme | Variation in referral rate reduced by 25% | [7 empty] | A&E 95% standard: Boston site has improved over the last 3 weeks and is now over 96%. There appear to be a number of factors that are affecting performance and causing “troughs” in performance. The urgent care lead is working with the trust, CCG’s and the LA to address the problems. It appears 111 triaging continues to create increased ambulance call out and A&E attendances. It appears this issue is not just pertinent to Lincolnshire as this has been discussed at length at the regional handover delays meeting; as well as locally at the Lincs handover delays meeting, Out Of Hours Group and Urgent Care Programme Board. The review of zero LOS patients is ongoing. Early indications are that patients are being admitted for conditions that could be managed more appropriately in other settings. Lincolnshire East CCG is working with the new Urgent Care lead to target practices with specific issues. ULHT are now coding MDS with a 111 referral source so once September data has been submitted to SUS, we can assess the impact of 111 on increased short stay admissions by matching A&E MDS to Inpatient MDS. Review of increase ion paediatric activity is ongoing. |  |  | As a result of improved pathways there will be a 7% reduction in follow up appointments, despite 0.5% growth in the local population, aging population. | SH- implementation of revised model for MSK (-1110 first orthopaedic appts.) and LIMS triage in place for East coast and Sth Holland | ULHT & PSHFT CQUINs in place incentivising best practice follow up ratios in further 5 specialities | Welland implementation of regular peer review of practices (-506 referrals) | Quality Premium pre-consent implemented tp give patients early info about joint replacement surgery and reduce referral into secondary care (SL) | LSW, SL and LE (Boston) Pathfinder referrals- support software fully installed and monitoring & reporting in place | LW-RMC in place for orthopaedics, gynaecology, urology, dermatology and ENT, diverting 5% of referrals | SWL & Welland- full implementation of orthopaedic pathway (-2,789, & 1,579) referrals) | 2% reduction in Outpatient appointmnets cancelled by hospital | The first 50 referral pathways managed using Pathfinder software. | New to follow up ratios in diabetes,Paediatrics,Urology, Cardiology, General surgery in top 25% performance and 5% reduction in Outpatient appointmnets cancelled by hospital. | CQUINs in place for top 25% new to follow up ratio performamnce in at least 75% of all specialties | New Glaucoma pathway in place, reducing secondary care Ophthalmology follow ups by (LW=600 PA) | Evaluation of Pathfinder referral software with view to roll out | Pthfinder referral software applied by all Lincolnshire CCGs across all pathways | CQUINs in place for top 25% new to follow up ration performamnce in at least 85% of all specialities | Variation in referral rates reduced by further 5% | Shared care arrangements in place for further 5 pathways | 7%reduction in Follow up appointments from 12/13 baseline. | [11 empty] | Movement from day case to OP procedures e.g. Wet AMD and maternity, not added into OP procedures plan, Will be corected for 13/14 plan. |  |  | Health inequalities driven down and quality of life improved through integrated healthcare delivery that promotes enhanced access, choice, experience, influence and safety - evidence based, cost effective and patient centred | Commission an additional 4000 weight management places | Implementation of virtual Ward (reablement) in Lincolnshire East - to enable patients to remain at home | Alcohol lead in post to ensure multi-agency approach across the county with focus on prevention and early detection | Making Every Contact Count programme developed with main providers and use CQUIN to support activity | 15% of dependant drinkers are in treatment service | 20% of obese children are offered access to healthy lives intervention utilising the Childhood Obesity Pathway | Impementation of 5 year alcohol plan for Lincolnshire | Simple telehealth implemented in SWL CCG and East Lindsey Locality of LE CCG: supporting self-care and community case management, working in partnership with County Council as part of reablement work stream. | Effective model for community health champions in place and ensured to reach Hard to Reach People. | Tele=health implementation plans for remaining localities and CCG agreed, and integrated with County Council Telecare plans | Making Every Contact count expanded across all front line staff and equitable delivery assured | 40% of obese children are offered access to healthy lives intervention utilising the Childhood Obesity Pathway | 100% of obese children are offered access to healthy lives intervention utilising the Childhood Obesity Pathway | [16 empty] | No significant, additional issues or risks |  |  | Organisational running costs are within respective envelopes (eg. CCG running costs per head of population) | CCG and PCT Cluster budgets amended to reflect the reduction in management costs realised recurrently by 31 March 2012. (The Cluster running cost ceiling for 12/13 is set at 11/12 outturn, as the Cluster has delivered the recurrent savings required to achieve the end state.) | Reaffirm that audited accounts confirm the delivery of targetrecurrent savings. | CCG and PCT Cluster budgets amended to reflect the reduction in management costs realised recurrently by 31 March 2012. (The Cluster running cost ceiling for 12/13 is set at 11/12 outturn, as the Cluster has delivered the recurrent savings required to achieve the end sate.) | Confirm no additional savings required for 13/14 | CCG and PCT Cluster budgets amended to reflect the reduction in management costs realised recurrently by 31 March 2012. (The Cluster running cost ceiling for 12/13 is set at 11/12 outturn, as the Cluster has delivered the recurrent savings required to achieve the end state.) | Confirm no additional savings required for 14/15 | [23 empty] | No additional issues since August report. The additional work associated with the 111 national procurement, AQP programme, contract stocktake and the establishment of LATs, CCGs and CSU have resulted in additional costs being incurred. There is a danger that if additional resources are not allowed to be put into these areas that staff absence will increase markedly due to work related stress. The PCT recognises that there are many risks associated with transition and that the running costs associated with these transition risks will not become clear until later in the financial year; the PCT is therefore continuing tight control over existing running costs. |  |  | Eliminate clinical variation in prescribing through the application of known best practice, thereby improving quality, safety, efficiency and effectiveness. Total planned savings achieved in line with published priorities | CCG prescribing information pack issued detailing productivity opportunity for all practices and all practices asked to agree 3 areas of change linked to Meds 6 and 10 from QOF | MONTHLY: 3 new drug assessments; 1 new trial assessment | All practices signed up to Med 6 and 10 plan involving their 3 actions | Rosuvastatin switching agreed in all relevant practices | All practice agreed actions implemented in accordance with QOF. | Additional actions linked to CCGs preferred ways of working agreed and developed foir 13/14 implementation. | MONTHLY: 3 new drug assessments; 1 new trial assessment | CCG prescribing information pack issued detailing poroductivity opportunity for all practices and all practices asked to agree 3 areas of change linked to Meds 6 and 10 from QOF | Review of managing variation with practices with view to corrective CCG action plans | CCG prescribing information pack issued detailing oroductivity opportunity for all practices and all practices asked to agree 3 areas of change linked to Meds 6 and 10 from QOF | MONTHLY: 3 new drug assessments; 1 new trial assessment | Review of managing variation with practices with view to corrective CCG action plans | [17 empty] | The NHS Business Services Authority (NHSBSA) have published prescribing forecast out-turn (FOT) figures based on prescribing expenditure for the first four months of 2012/13. Acknowledging the inherent unreliability of such early forecasts, current figures predict a forecast overspend of £439,952 for Lincolnshire PCT. The NHSBSA have announced their intention to change the forecasting profile again next month to take into account the dramatic fall in the price of generic atorvastatin. Hence the current FOT does not take into account the £2.9M in year fortuitous saving predicted for atorvastatin nor does it accommodate the £2.7M in year saving linked to other key patent expiries in 2012/13. Overall, FOT prescribing expenditure looks set to fall within budget from next month onwards. |  |  | Multi-Disciplinary LD teams fully in place and efficinecies realised by new model | First Cohort of & Low secure patients transfer complete | Recruitment of 6 additIonal LD Nurses | Transfer of CHC function to CSS for LD team | 15 low secure patients transferred into new service | Multi-Disciplinary LD team 50% in place | Phase 2 of LD team restructuring TUPE transfer of remaining posts and decomissioning of surplus posts | Transfer of LD complete | Multi-Disciplinary LD teams fully in place and efficinecies realised by new model | [21 empty] | No significant risks or issues at this time
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones |  |  | Total number of FFCEs in the period | [32 empty] | Number of G&A non-elective FFCEs in the period | [32 empty] | All first outpatient attendances (consultant-led) in general and acute specialties
(UNIFY indicators) Anticipated performance at period end |  |  | 115972 | 117711 | 119477 | [30 empty] | 73429 | 74530 | 75648 | [30 empty] | 222318 | 225653 | 229038
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s))) |  |  | Number of elective FFCEs - ordinary admissions | [65 empty] | Number of 1st outpatient attendances (consultant-led) following GP referral in general and acute specialties
(Other KPIs) Anticipated performance at period end |  |  | 24548 | 24916 | 25290 | [63 empty] | 148757 | 150988 | 153253
QIPP Initiative Reporting | [100 empty] | On-going development of integrated pathways with ULHT and CCGs
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-07-31 | 2014-09-30 | 2014-12-31 | [14 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-10-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-02-28 | 2015-03-31 | [8 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-03-31 | [12 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-09-30 | 2012-10-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2014-02-28 | 2014-03-31 | 2015-03-31 | [17 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-06-30 | 2012-04-30 | 2013-05-31 | 2014-04-30 | 2014-05-31 | [24 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-09-30 | 2014-04-30 | 2014-05-31 | 2014-09-30 | [18 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2014-03-31
Progress reporting against milestones and Initiative 1 |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall prog |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly ( |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green
[10 empty] | 0n coursev for 90% by October | Potential risk of delay to December 2012. Service provision from ULHT dependant on outcome of business case to ULHT Board (deferred in Sept to October Board). No aniticipated risk to maintenance of existing services through One Health.. | [23 empty] | Trajectory to end state overall on track., Improving activity. Rephasing of ULHT activity complete and agreed - still awaiting backdating of impact and coding issues - 3.4% fye beneficial impact. Peterborogh recovery plan in place for RTT |  |  |  | Lincolnshire East CCG only | Lincolnshire East CCG only | Lincolnshire East CCG only | New software available through Connecting for Health from October 2012. Therefore decision made to implement only once as inappropriate to implement July and agin in October |  | New software available through Connecting for Health from October 2012. Therefore decision made to implement only once as inappropriate to implement July and agin in October | [23 empty] | Milestones - overall on track. Activity - off plan. Collectively the Lincolnshire CCG’s have experienced an increase in both value and complexity in non-elective acute activity. This has impacted on a key component of the PCT QIPP programme. Since August the CCG’s have commissioned the services of an external consultant (commencing in October) to review the activity counting and coding in the context of changes negotiated with ULHT. All CCG’s have ongoing projects to support reduction of admissions and are reviewing all QIPP initiatives in respect of non-elective acute activity. Second quarter data is expected to better inform impact of mitigating actions |  |  |  | Lincolnshire East and South Lincolnshire CCGs only |  |  |  | Milestone erroneously described as 3 CCG participants. Actually only ever 2 - South West Lincolnshire and South Lincolnshire. No detrimental effect on impact. | orthopaedics, gynaecology and urology in place with work started on dermatology and ENT which may slip to December 2012 |  | Total reduction to date of 11,846 across Gen Surgery, Cardiology, Respiratory and Oncology | South West Lincolnshire CCG and South Lincolnshire CCG only (iriginally specified as 3 CCGs prior to the merging of Welland and South Holland) | [20 empty] | Overall milestones, activity and finance on track. New to follow up reduced by 11846 attendances across 4 key specialties |  |  |  |  | Lincolnshire East CCG only | [27 empty] | All milestones and activity on track. Work is ongoing around the Publiuc Health Allocationand its impact on business plan for 13/14. Plan targetted for December 2012 completion. | [32 empty] | As August: All milestones met. More accurate forecasts will develop over the coming months as it becomes clearer what effect the transition will have on Running Costs. Latest calculations indicate Running costs are within the target ceiling. QIPP: FMR continues to report all QIPP savings will be delivered in 2012/13. Performance information that informed the Q1 monitoring information was incomplete and contradictory. Year to date performance was evaluated on the basis of limited information suggesting over performance of acute activity relative to plan. | [32 empty] | Our Prescribing QIPP Information Pack 2012/13 detailing all QIPP opportunities and productivity savings by practice and CCG was issued in early May 2012. Since then the Prescribing and Medicines Optimisation Team have been working with CCGs, locality GP groups and individual practices to secure agreements around prescribing changes for this year. This work is on track for completion in October 2012. To date, £1.9M savings have now been agreed with our practices. So far £291,000 have been realised through technician implementation of agreed changes. Most of the technician led switches implemented during the last few months have been rosuvastatin switches designed to maximise efficiencies resulting from the atorvastatin patent expiry. Further work quantifying the in-year savings related to additional patent expiries in 2012 has been completed and quantified as £2.7M. However, prescribing expenditure remains a key risk area and trends will continue to be closely monitored. | [5 empty] | Further discussion of structures. CHC for LD now with South West Lincolnshire CCG as federal lead for MH and LD services | [26 empty] | 75% of the LD multi-disciplinary team are in post within a single provider, including Physiotherapy, Occupational Therapy, Psychology and Psychiatry. Nursing staff will transfer in the coming months. The Lincolnshire transformation of mental health services programme is developing its proposals and option appraisal methods to engage with all stakeholders. Public consultation is planned and gateway process will be applied to ensure the plans are robust enough to proceed.
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | Delayed - amber | Delayed - amber | In progress | Work not yet commenced | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [14 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Delayed - amber | Completed | Delayed - amber | Work not yet commenced | In progress | In progress | In progress | In progress | In progress | Work not yet commenced | In progress | In progress | In progress | In progress | Work not yet commenced | In progress | Work not yet commenced | In progress | In progress | [8 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | Completed | Delayed - amber | Completed | Completed | In progress | In progress | In progress | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | In progress | [12 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | In progress | In progress | Completed | In progress | In progress | In progress | Work not yet commenced | In progress | In progress | [17 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Work not yet commenced | Work not yet commenced | Work not yet commenced | [24 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | In progress | Completed | In progress | In progress | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [18 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | In progress | Completed | In progress | In progress | In progress
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Discussions have begun around the move to full Board status and in preparation for the publication of secondary legislation governing future constitution and operation. As part of these discussions, the establishment of a Commissioning Alliance has been agreed, to take forward the agreed arrangements for integrated working. | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 |  |  |  | 2012-03-31 | 2012-03-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-07-31 | 2014-09-30 | 2014-12-31 | [13 empty] | -3.0333 |  |  |  | 2012-04-30 | 2012-04-30 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-10-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-02-28 | 2015-03-31 | [7 empty] | -1.0333 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-03-31 | [11 empty] | 0 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-09-30 | 2012-10-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2014-02-28 | 2014-03-31 | 2015-03-31 | [16 empty] | 0 |  |  |  | 2012-04-30 | 2012-06-30 | 2012-04-30 | 2013-05-31 | 2014-04-30 | 2014-05-31 | [23 empty] | 0 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-09-30 | 2014-04-30 | 2014-05-31 | 2014-09-30 | [17 empty] | 0 |  |  |  | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2014-03-31 | [21 empty] | 0
| Month 2 | 2012-05-31 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-07-31 | 2014-09-30 | 2014-12-31 | [13 empty] | 0 | [5 empty] | 2012-05-31 | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-10-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-02-28 | 2015-03-31 | [7 empty] | -1 |  |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-03-31 | [11 empty] | 0 |  |  |  |  | 2012-05-31 | 2012-09-30 | 2012-10-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2014-02-28 | 2014-03-31 | 2015-03-31 | [16 empty] | 0 |  |  |  |  | 2012-06-30 |  | 2013-05-31 | 2014-04-30 | 2014-05-31 | [23 empty] | 0 |  |  |  |  | 2012-05-31 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-09-30 | 2014-04-30 | 2014-05-31 | 2014-09-30 | [17 empty] | 0 |  |  |  | 2012-05-31 | 2012-10-31 | 2012-11-30 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2014-03-31 | [21 empty] | -2.0333
| Month 3 | 2012-06-30 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-07-31 | 2014-09-30 | 2014-12-31 | [13 empty] | 0 | [6 empty] | 2012-07-31 | 2012-09-30 | 2012-10-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-10-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-02-28 | 2015-03-31 | [7 empty] | 0 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-03-31 | [11 empty] | 0 | [5 empty] | 2012-09-30 | 2012-10-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2014-02-28 | 2014-03-31 | 2015-03-31 | [16 empty] | 0 |  |  |  |  | 2012-06-30 |  | 2013-05-31 | 2014-04-30 | 2014-05-31 | [23 empty] | 0 | [5 empty] | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-09-30 | 2014-04-30 | 2014-05-31 | 2014-09-30 | [17 empty] | 0 |  |  |  |  | 2012-10-31 | 2012-11-30 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2014-03-31 | [21 empty] | 0
| Month 4 | 2012-07-31 | [6 empty] | 2012-07-31 | 2012-10-31 | 2012-12-31 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-07-31 | 2014-09-30 | 2014-12-31 | [13 empty] | 5.1 | [6 empty] | 2012-10-31 | 2012-09-30 | 2013-01-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-10-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-02-28 | 2015-03-31 | [7 empty] | 6.1333 | [6 empty] | 2012-07-31 | 2012-08-31 | 2012-12-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-03-31 | [11 empty] | 3.0667 | [5 empty] | 2012-09-30 | 2012-10-31 | 2013-02-28 | 2013-03-31 | 2012-07-31 | 2013-05-31 | 2013-01-31 | 2013-07-31 | 2014-02-28 | 2014-03-31 | 2015-03-31 | [16 empty] | -14.1 | [6 empty] | 2013-05-31 | 2014-04-30 | 2014-05-31 | [23 empty] | 0 | [5 empty] | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-01-31 | 2013-09-30 | 2014-04-30 | 2014-05-31 | 2014-09-30 | [17 empty] | -5 |  |  |  |  | 2012-10-31 | 2012-11-30 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2014-03-31 | [21 empty] | 0
| Month 5 | 2012-08-31 | [7 empty] | 2012-10-31 | 2012-12-31 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-07-31 | 2014-09-30 | 2014-12-31 | [13 empty] | 5.1 | [6 empty] | 2012-10-31 | 2012-09-30 | 2013-01-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-10-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-02-28 | 2015-03-31 | [7 empty] | 6.1333 | [7 empty] | 2012-08-31 | 2012-12-31 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-03-31 | [11 empty] | 3.0667 | [5 empty] | 2012-09-30 | 2012-10-31 | 2013-02-28 | 2013-03-31 | 2012-07-31 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2014-02-28 | 2014-03-31 | 2015-03-31 | [16 empty] | -9.1 | [6 empty] | 2013-05-31 | 2014-04-30 | 2014-05-31 | [23 empty] | 0 | [5 empty] | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-01-31 | 2013-09-30 | 2014-04-30 | 2014-05-31 | 2014-09-30 | [17 empty] | -5 |  |  |  |  | 2012-10-31 | 2012-11-30 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-10-31 | 2014-03-31 | [21 empty] | 0
| Month 6 | 2012-09-30 | [7 empty] | 2012-10-31 | 2012-12-31 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-07-31 | 2014-09-30 | 2014-12-31 | [13 empty] | 5.1 | [6 empty] | 2012-10-31 | 2012-09-30 | 2013-01-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-10-31 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-02-28 | 2015-03-31 | [7 empty] | 6.1333 | [7 empty] | 2012-08-31 | 2012-12-31 | 2012-09-30 | 2012-09-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-06-30 | 2015-03-31 | [11 empty] | 0 | [5 empty] | 2012-09-30 | 2012-09-30 | 2013-02-28 | 2013-03-31 | 2012-07-31 | 2013-05-31 | 2013-06-30 | 2013-07-31 | 2014-02-28 | 2014-03-31 | 2015-03-31 | [16 empty] | -10.1333 | [6 empty] | 2013-05-31 | 2014-04-30 | 2014-05-31 | [23 empty] | 0 | [5 empty] | 2012-10-31 | 2012-09-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-01-31 | 2013-09-30 | 2014-04-30 | 2014-05-31 | 2014-09-30 | [17 empty] | -7.0333 |  |  |  |  | 2012-09-30 | 2012-09-30 | 2013-02-28 | 2012-09-30 | 2013-04-30 | 2013-10-31 | 2014-03-31 | [21 empty] | -9.1333
| Month 7 | 2012-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone | [5 empty] | 4 | 4 | 2 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [17 empty] | 1 | 1 | 1 | 4 | 4 | 4 | 1 | 4 | 4 | 1 | 1 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | [11 empty] | 2 | 4 | 1 | 1 | 2 | 1 | 2 | 4 | 3 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | [15 empty] | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 4 | [20 empty] | 4 | 4 | 4 | 4 | 4 | 4 | [27 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [21 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Number of CCGs who have completed this milestone | [5 empty] | 4 | 4 | 2 | 1 | N/A | Date | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [17 empty] | 1 | 1 | 1 | N/A | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 2 | 4 | 1 | 1 | 2 | N/A | 2 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [15 empty] | 4 | 1 | 4 | 4 | N/A | N/A | 4 | N/A | N/A | N/A | N/A | N/A | N/A | [20 empty] | 4 | 4 | 4 | N/A | N/A | N/A | [27 empty] | 4 | 4 | N/A | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [21 empty] | 4 | N/A | 4 | N/A | N/A | N/A | N/A | N/A
Percentage of PCTs completing this milestone |  |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | #VALUE! | 100% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 100% | 100% | #VALUE! | 100% | 100% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 100% | #VALUE! | #VALUE! | 100% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 1 | 1 | 1 | #VALUE! | #VALUE! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 1 | 1 | #VALUE! | 1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 1 | #VALUE! | 1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Northamptonshire_QIPPmilestones
2012- 2013 Milestone Tracker |  |  | Northamptonshire Strategic Change Programme | [32 empty] | Acute Contracts (Outpatients) | [32 empty] | Acute Contracts (Non Elective) | [32 empty] | Acute Contracts (Elective) | [32 empty] | Mental Health & Learning Disabilities Contracts | [32 empty] | QIPP Initiative 6 | [32 empty] | QIPP Initiative 7
QIPP Overview and finances
SHA cluster: |  | NHS Midlands and East
PCT Cluster : |  | Northamptonshire and Milton Keynes
Number of CCGs in cluster: |  | 3
Report for the month of: |  | 2012-09-30
QIPP Challenge (£000s) |  | 235037
FIMS Plan: Savings for CSR period (£000s) |  | 282658
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s) |  | 101995
Yr 2 Plan FIMS savings for 2012-13 (£000s) |  | 82001
Yr 3 Plan FIMS savings for 2013-14 (£000s) |  | 48302
Yr 4 Plan FIMS savings for 2014-15 (£000s) |  | 50360
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 282658
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be <50% of years 2-4 (Cells C11:C13)) |  | 115117
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale | PCT cluster |  | Title | Healthier Together Service Review | [28 empty] | Scale | PCT cluster |  | Title | Acute Contracts (Outpatients) | [28 empty] | Scale | PCT cluster |  | Title | Acute Contracts (Non Elective) | [28 empty] | Scale | PCT cluster |  | Title | Acute Contracts (Elective) | [28 empty] | Scale | PCT cluster |  | Title | Mental Health & Learning Disabilities Contracts | [28 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings | Acute Contracts (Outpatients) | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings | Acute Contracts (Non Elective) | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings | Acute Contracts (Non Elective) | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings | Acute Contracts (Elective) | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings | Mental Health & Learning Disabilities Contracts | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 | 12285 | FIMS savings 2013-14 | 5873 | FIMS savings 2014-15 | 6124 | Total for CSR period | 24282 | [25 empty] | FIMS savings 2012-13 | 26816 | FIMS savings 2013-14 | 12898 | FIMS savings 2014-15 | 13448 | Total for CSR period | 53162 | [25 empty] | FIMS savings 2012-13 | 8505 | FIMS savings 2013-14 | 7094 | FIMS savings 2014-15 | 7397 | Total for CSR period | 22996 | [25 empty] | FIMS savings 2012-13 | 6426 | FIMS savings 2013-14 | 4039 | FIMS savings 2014-15 | 4212 | Total for CSR period | 14677 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 13-14 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative. |  |  |  |  | Improved quality, safety and affordability in services provided. Bringing care closer to home and developing some specialist centres by combining expertise across five hospitals in Bedford, Kettering, Luton, Milton Keynes and Northampton. | HTSR: Commissioning intentions shared with clinical working groups | HTSR: Core clinically viable services identified for all 5 sites | HTSR: Recommended clinical models & service locations identified | HTSR: 1st Stage Implementation Plan Agreed | HTSR: Public consultation starts | HTSR: Public consultation complete | HTSR: Review of Public Consultation Outcomes | HTSR: 1st Stage Implementation Starts, plans for 2nd stage implementation agreed | Strategic Change Programme 1 ( primary care): 2 Practices/Localities Pilot Hub & Spoke Configuration Implemented | HTSR: 2nd Stage Implementation Commences | HTSR: Review commissioning intentions for 2014/15 | HTSR: 1st Stage Implementation Complete | HTSR: Review of 1st Stage Implementation Complete | Strategic Change Programme 1 ( primary care): 2 further localities to Implement Hub & Spoke reconfiguration | Review commissioning intentions for 2015/16 | Implementation of service reconfiguration complete | [16 empty] | Reduction of 29,850 Outpatient Attns Reduction of 825 1st Outpatients Appts | Right Care/LPTs: Lower GI and Knee Pain Pathways Redesigned | Follow-Up Transfer of Care: Final LES document internally agreed and sign-off by project team and contracts lead | Ophthalmology: If decision to have an consolidated intermediate model without formal tendering, finalising service specification while the interim service continues | OPFUP by Phone: Quaterly progress review complete. Decision on further rollout complete | Telehealth Pilot: Review to governing body complete. Proposal for extension of Pilot and / or future procurement options agreed | Heart Failure LES: Roll out complete | GP Referrals: Review and Follow-Up meeting of Q&P leads with practices | Corby LUTs: Review presented to governing body. Decision on future procurement route. | Corby LUTs: Commence procurement. Review impact on FY13/14 acute activity | Ophthalmology: Tendering and procurement starts | Telehealth Pilot: Contract award | Dermatology - Community based UVA /UVB service for Corby patients (subject to option appraisal approval) | GP Referrals: Continued with a stretch towards further reductions in clinical variation | Ophthalmology: Procured Service implemented | Ophthalmology: Starts Delivering Benefits | Defined project plans implemented for 13-14 | 14-15 Plans developed | [15 empty] | Provide appropriate alternative urgent care treatment and shift 3700 Acute (Non-elective) to a local tariff. Reduce Acute (Non-elective) by 22,186 | Integrated Alcohol and OD Pathway Goes Live | Corby Urgent Care Centre (UCC): Review submitted ITT for service provider | Paediatric Pathway Review: GP peer support | CCH Step Up by GP: Agree preferred provider (included in UCC tender) subject to review | Locality based Community Nursing Demand Management schemes Commenced | GP Resource Utilisation: 50% of GP Practices will be within 50% of standard variation | Corby UCC: Urgent Care Centre (Corby) Opens. Service live date. GP led walk in centre & MIU decommissioned | Rollout of doctor first in Corby practices: Roll out completed. All practices fully operational | Diabetes: Newly Procured Service Goes Live | Frail Elderly: Implementation Of Wave 1 Changes | Strategic Change programme 3 (Prevention): Launch Awareness Campaigns around Obesity, Smoking, Alcohol) | Integrated Alcohol Treatment: Post Project Review Completed | Strategic Change Programme 12( IC and Case Management): Roll out of System-wide CASE Management Modules complete | Frail Elderly: Prelaunch Of CEC Service | Strategic Change programme 3 (Prevention): Final Wave of CHD Programme complete. All localities with representation. | Strategic Change programme 3 (Prevention): Launch Prevention Investment | Frail Elderly: MSK Project Review/Business Case Completed | Strategic Change Programme 12( IC and Case Management): Review of Risk Stratification Tools and project Impact complete | Strategic Change Programme 1 ( primary care): Wellingboro UCC Opens | Corby UCC: Willowbrook Phase II Implementation Commences | Strategic Change programme 3 (Prevention): Full Review Of Health Checks Impact ( next Steps) complete | Frail Elderly: MSK Project GO Live | Diabetes: Post Project Review Completed | Strategic Change Programme 1 ( primary care): 3rd UCC in Northants Goes Live | Strategic Change programme 3 (Prevention): Agree Development of Health Checks Programme | Defined project plans implemented for 13-14 | Frail Elderly: Implementation Of Frail Elderly Wave 2 | Strategic Change Programme 12( IC and Case Management): personalised Budget agreed for 70% of target users/carers. | Strategic Change Programme 1 ( primary care): 4th UCC in Northants Goes Live. |  |  |  | Development and cost reduction of gynae service, reduction of 1072 1st Outpatient Appts | Community Gynae service: specification agreed | Community Gynae service: contract agreed | Community Gynae service: service start | Commissioning strategy for 13/14 complete and project concepts scoped | 13/14 Projects fully worked up and signed off | Defined project plans implemented for 12-13 | Commissioning strategy for 14/15 commenced | Commissioning strategy for 14/15 complete and project concepts scoped | 14/15 Projects fully worked up and signed off | Defined project plans implemented for 13-14 | [22 empty] | Improved MH and LD services through appropriate decommissioning. Linden unit closed and future provision expanded in terms of team capacity by 20%. 15% Increase in people with LD living in the community. | Decommission AOT, complex needs and EIT: New specification in place for extended teams | Decommission Linden Unit: Review feedback from consultation and agree next steps | Decommission Linden Unit: Notice period and decommissioning date agreed | Decommission AOT, complex needs and EIT: contract and performance review - pull in audit results | Decommission Linden Unit: Clinical assessments and transfer of patient/s completed | Decommission Linden Unit: Unit Decommissioned | Commissioning strategy for 13/14 complete and project concepts scoped | LD Services: More people with LD living independently in the Community | 13/14 Projects fully worked up and signed off | Defined project plans implemented for 12/13 | Commissioning strategy for 14/15 commenced | Commissioning strategy for 14/15 complete and project concepts scoped | 14/15 Projects fully worked up and signed off | Defined project plans implemented for 13/14
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones | [35 empty] | All first outpatient attendances (consultant-led) in general and acute specialties | [32 empty] | Number of G&A non-elective FFCEs in the period | [32 empty] | Total number of FFCEs in the period
(UNIFY indicators) Anticipated performance at period end | [35 empty] | 212596 | 216927 | 221368 | [30 empty] | 86957 | 88735 | 90559 | [30 empty] | 127556 | 129937 | 132351
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s))) | [35 empty] | Number of 1st outpatient attendances (consultant-led) following GP referral in general and acute specialties | [65 empty] | Number of elective FFCEs - ordinary admissions
(Other KPIs) Anticipated performance at period end | [35 empty] | 140408 | 143164 | 145978 | [63 empty] | 26285 | 26781 | 27282
QIPP Initiative Reporting
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-10-31 | 2014-03-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [14 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | [13 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 2013-05-31 | 2013-05-31 | 2013-06-30 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-02-28 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-08-31 |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-06-30 | 2012-07-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2015-04-30 | [20 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [16 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31
Progress reporting against milestones and Initiative 1 |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall prog |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly ( |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating
[8 empty] | GP Referral numbers by specialty by practice have been produced which will allow locality managers to address overperformance with practices on a specialty by specialty basis | [26 empty] | The Healthier Together Consultation has been set for October 12. The Strategic Health Authority have issued a KPMG report that potentially impacts on the Healthier Together programme. The CCGs are currently discussing the impact of the SHA initiative with key providers. This will not be concluded until early Octoberber 12. The LAT is involved. |  |  |  |  | Nene complete. (MK) Proposed business rule was developed and put forward for contract negotiations as per the original milestone due date. However, this was not agreed into the acute contract, therefore mitigating plan is being implemented to deliver the financial benefits assigned to this project. LES is being developed currently as a mitigating plan to achieve financial benefits assigned to project. The LES has been produced in draft format. Subject to approvals and agreement it is anticipated that this should be able to be rolled out to General Practices from September/October. |  | KGH Follow-ups moved to block contract so savings in plan will not be seen. Corby is still progressing as it meets the 'Q' agenda and will establish the baseline for FY13/14 contracting round, but focus has been on other schemes to mitigate the loss of £500k from our QIPP followup reduction schemes. GP Home visiting running ahead of plan on savings, Diabetes prescribing savings now added to QIPP plan (for reasons unknown this was not included in the baseline), some PH (pure cost) schemes we had predicted would start April, not now starting until Q2/Q3. | The current Nene Telehealth project plan has this scheduled for action during November. | This was not due for completion in September. Rather a Gateway Clinical Evaluation and Data analysis was scheduled. The results of which are due in early October after which a recommendation will be submitted to NCDE scheduled for the end of October. | MK - Initial meetings have taken place with high referring practices to discuss clinical variation in referrals. Q&P Leads are in post and are meeting with practices on a monthly basis. Meetings have now been booked from October onwards. | Delay caused by contract issues for Consultant and long term illness of prime GP | [21 empty] | Monthly performance meetings with CCGs suggest real progress in reducing outpatient referrals and follow ups. We have more accurately phased the impact of demand management schemes and this is starting to show particularly in Northants. Each of the CCGs has begun a series of contractual challenges with their respective Acute Providers to seek clarification. All are forecasting to be on target by the end of the year, with their QIPP savings. | [6 empty] | Bids reviewed and recommended supplier approved by CCG board. Waiting for CCP approval in the next couple of days before supplier can be notified. | First PM who accepted the role consequently withdrew. A subsequent PM has accepted and commenced work on the project on 18 September. | This is an ongoing activity in and by localities and continues to review referral activity on a regular basis. | [23 empty] | Northants trusts (KGH & NGH) on track with A&E. QIPP non-elective actions not a large percentage and are not impacting (+ 6-7 %). Concern remains about the acuity of patients presenting to A&E and the growth in admissions. A number of additional redesign and change management processes are in place and / or being developed, including additional investments. |  |  |  |  | Service commenced in Jul-12 and patients are being seen & treated. Services are provided under the main acute contract, but a contact varaiation is needed. | [27 empty] | There are a number of QIPP Schemes working around management of electives, in particular Right Care and other Planned Care programmes. However phasing is an issue and the CCG concerns with regard to Trust activity are being challenged through the contracts. We expect that to reduce Acute Elective activity in line with plan by the end of the year. This is begining to show a positive trend. | [32 empty] | The Mental Health and Learning Disabilities schemes in the tracker are progressing well. There are a significant number of additional schemes and actions in this domain that are either progressing well or are on an accelerated development path. For both Milton Keynes and Northamptonshire, we are confident that they will meet their QIPP requirement by year end. Savings have already been recovered through contracts with providers.
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [14 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Delayed - amber | Completed | Delayed - amber | Delayed - amber | Delayed - amber | Completed | Delayed - amber | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [13 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | Delayed - amber | In progress | In progress | In progress | In progress | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Delayed - amber | Completed | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [20 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Delayed - amber | Delayed - amber | In progress | Work not yet commenced | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [16 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 |  |  | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-10-31 | 2014-03-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [13 empty] | 0 |  |  | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | [12 empty] | 0 |  |  | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 2013-05-31 | 2013-05-31 | 2013-06-30 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-02-28 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-08-31 | 0 |  |  | 2015-03-31 | 2012-04-30 | 2012-06-30 | 2012-07-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [19 empty] | -12.1667 |  |  | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [15 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2012-05-31 |  |  | 2015-03-31 |  | 2012-05-31 | 2012-06-30 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-10-31 | 2014-03-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [13 empty] | 0 |  |  | 2015-03-31 |  | 2012-04-30 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | [12 empty] | -1.0333 |  |  | 2015-03-31 |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 2013-05-31 | 2013-05-31 | 2013-06-30 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-02-28 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-08-31 | 0 |  |  | 2015-03-31 |  | 2012-06-30 | 2012-07-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [19 empty] | -12.1667 |  |  | 2015-03-31 |  | 2012-05-31 | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [15 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2012-06-30 |  |  | 2015-03-31 |  |  | 2012-06-30 | 2012-06-30 | 2012-10-31 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-10-31 | 2014-03-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [13 empty] | -3.0667 |  |  | 2015-03-31 |  |  | 2012-06-30 | 2012-09-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | [12 empty] | 2.0333 |  |  | 2015-03-31 |  |  | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 2013-05-31 | 2013-05-31 | 2013-06-30 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-02-28 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-08-31 | 0 |  |  | 2015-03-31 |  | 2012-07-31 | 2012-07-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [19 empty] | -11.1333 |  |  | 2015-03-31 |  |  | 2012-06-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [15 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2012-07-31 |  |  | 2015-03-31 |  |  |  |  | 2012-10-31 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-10-31 | 2014-03-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [13 empty] | 0 |  |  | 2015-03-31 |  | 2012-08-31 |  | 2012-09-30 | 2012-11-30 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | [12 empty] | 8.1333 |  |  | 2015-03-31 |  |  |  | 2012-08-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 2013-05-31 | 2013-05-31 | 2013-06-30 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-02-28 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-08-31 | 1.0333 |  |  | 2015-03-31 |  | 2012-08-31 | 2012-07-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [19 empty] | -10.1 |  |  | 2015-03-31 |  |  |  | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [15 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2012-08-31 |  |  | 2015-03-31 |  |  |  |  | 2012-10-31 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-10-31 | 2014-03-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [13 empty] | 0 |  |  | 2015-03-31 |  | 2012-09-30 |  | 2012-09-30 | 2012-11-30 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | [12 empty] | 10.1667 |  |  | 2015-03-31 |  |  |  | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 2013-05-31 | 2013-05-31 | 2013-06-30 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-02-28 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-08-31 | 3.0333 |  |  | 2015-03-31 |  | 2012-09-30 |  | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [19 empty] | -9.1 |  |  | 2015-03-31 |  |  |  | 2012-09-30 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [15 empty] | 1 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2012-09-30 |  |  | 2015-03-31 |  |  |  |  | 2012-10-31 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-06-30 | 2013-09-30 | 2013-10-31 | 2014-03-31 | 2014-03-31 | 2014-04-30 | 2014-10-31 | 2015-03-31 | [13 empty] | 0 |  |  | 2015-03-31 |  | 2012-10-31 |  | 2012-09-30 | 2012-11-30 | 2012-10-31 | 2012-10-31 | 2012-12-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-08-31 | 2013-12-31 | 2014-03-31 | 2014-04-30 | [12 empty] | 12.2333 |  |  | 2015-03-31 |  |  |  | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-10-31 | 2013-03-31 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 2013-05-31 | 2013-05-31 | 2013-06-30 | 2013-06-30 | 2013-07-31 | 2013-08-31 | 2013-08-31 | 2013-09-30 | 2013-10-31 | 2013-10-31 | 2013-11-30 | 2014-01-31 | 2014-02-28 | 2014-02-28 | 2014-03-31 | 2014-04-30 | 2014-05-31 | 2014-08-31 | 3.0333 |  |  | 2015-03-31 |  | 2012-10-31 |  | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [19 empty] | -8.0667 |  |  | 2015-03-31 |  |  |  | 2012-09-30 | 2012-11-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2013-10-31 | 2014-03-31 | 2014-04-30 | [15 empty] | 3.0333 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2012-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [19 empty] | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | [17 empty] | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [23 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 3 | 3 | 3 | 3 | 3
Number of CCGs who have completed this milestone | [38 empty] | 1 | 1 | 2 |  |  |  | 2 | [26 empty] | 2 | 1 | 1 | 1 | [29 empty] | 1 |  | 1 | [30 empty] | 1 | 1 | 1
Percentage of PCTs completing this milestone |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 50% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Nottinghamshire_QIPPmilestones
2012- 2013 Milestone Tracker |  |  | Community Contracts | [32 empty] | Mental Health and LD Contracts | [32 empty] | Acute - non elective | [32 empty] | Acute- elective | [32 empty] | Acute - outpatients | [32 empty] | Primary Care Prescibing | [32 empty] | QIPP Initiative 7
QIPP Overview and finances
SHA cluster: |  | NHS Midlands and East
PCT Cluster : |  | Nottinghamshire
Number of CCGs in cluster: |  | 6
Report for the month of:
QIPP Challenge (£000s) |  | 162300
FIMS Plan: Savings for CSR period (£000s) |  | 315979
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s) |  | 76595
Yr 2 Plan FIMS savings for 2012-13 (£000s) |  | 84508
Yr 3 Plan FIMS savings for 2013-14 (£000s) |  | 79253
Yr 4 Plan FIMS savings for 2014-15 (£000s) |  | 75623
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 315979
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be <50% of years 2-4 (Cells C11:C13)) |  | 127693
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 | 8015 |  | 4458 | FIMS savings 2014-15 | 4072 | Total for CSR period | 16545 | [25 empty] | FIMS savings 2012-13 | 8548 | FIMS savings 2013-14 | 3763 | FIMS savings 2014-15 | 3613 | Total for CSR period | 15924 | [25 empty] | FIMS savings 2012-13 | 15365 | FIMS savings 2013-14 | 20109 | FIMS savings 2014-15 | 18201 | Total for CSR period | 53675 | [25 empty] | FIMS savings 2012-13 | 6619 | FIMS savings 2013-14 | 2316 | FIMS savings 2014-15 | 1992 | Total for CSR period | 10927 | [25 empty] | FIMS savings 2012-13 | 11028 | FIMS savings 2013-14 | 5732 | FIMS savings 2014-15 | 4966 | Total for CSR period | 21726 | [25 empty] | FIMS savings 2012-13 | 1534 | FIMS savings 2013-14 | 3648 | FIMS savings 2014-15 | 3714 | Total for CSR period | 8896 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative. |  |  |  |  | 5% reducation in excess bed days and reduce community bed stock (24 beds 12/13 - 13/14 and 14/15 further potential reduction to be confirmed through clinical pathway | NEEDS MILESTONE DESCRIPTOR ENTERING | IHSC programme Roll out of County in-reach pilot to NNE and NW | IHSC Programme - Training and induction for phase 1 | IHSC - Phase 1 implementation | IHSC Programme - Workforce reconfiguration consultation planning process commences | Community Hospitals - Presentation to Joint City/County overview and Scrutiny Committee | Community Hospitals - Public Consultation if required | IHSC - Accountable Bodies sign off proposals | IHSC - Consultation on health and social care integration | Community Hospitals -Planned Closure of second Ward | Community Hospitals - pilot services evaluation report completed | Community Utilisation review completed and findings used to inform changes to patient pathways during 13/14 | IHSC - decision point for roll out to other CCGs | Community Utilisation review completed and findings included in 14/15 contract negotiations | Community Utilisation review findings including in 14/15 contract | Bed capacity review to determine potential of further community bed reductions during 14/15 | [16 empty] | 10% reduction in activity in OATs activity - 25% reduction in occupied bed days / Reduction in IP rehabilitation bed capacity (tbc)/ 30% reduction in medium secure - in line with other providers | OATs - Review of all locked rehabilitation patients commences | Rehab - Programme Board established to oversee the implementation of the review | Low secure services commission step down unit (8 beds) | OATs - Review of all placements completed and revised care pathways confirmed and implemented | DTOC - Commissioner and Mental Health Trust agree DTOC patient identification process | Rehab - Local authority commission an assessment post - to determine patients ready for discharge and facilitate move into community accommodation or residential | Rehab - Local authority commission 'intensive floating support packages' to facilitate resettlement into the community | Medium secure - risk sharing agreement and service change commened | DTOC - 13/14 target agreed | Rehab - revised patient pathway implemented | RAID service model evaluated to determine patient and service benefits | OATs - Locked rehab capacity review to assess impact of revised pathway and need for step down capcacity | Mental Health service utilisation reivew - agree methodology and carry out review of provider and primary/community care provision | RAID service model agreed and to be included in 14/15 contract | Rehabilitation review - bed capacity reduction agreed and implemented | Mental Health Utilisation reivew - recommendations and service change plan agreed and developed | Mental Health - service change plan agreed | [13 empty] | Financial |  | 4,680 non elective admissions reduction - includes - 20% reducation in ED attendances relating to falls - 5% reduction in admission from care homes | One Care Home One Practice - pilot commences in 2 practices | Eye casualty review commences | Practice validation of regular ED attenders - all CCGs | CDU - Nursing rotas and training programme agreed | Capital Works begin for Observational unit | Review of community geriatrician service spec and outcomes | One Care Home One Practice - pilot report delivered and decision on future roll out agreed | Eye casualty review completed and recommendations implemented | Observations Unit Opens | Crisis reponse falls service commences | Stroke rehabilitation review - bed reconfiguration completed and revised patient pathway agreed | Review of community geriatrician service spec and outcomes | One Care Home One Practice - further roll of service to agreed numnber of practices | Evaluation of Community Navigator pilot completed | Frail Elderly - development of medium / long term plans developed and agreed | Assisted technologies - implementation of system wide benefits and performance and quality monitoring process | Frail Elderly - service changes agreed in-year to inform 14/15 contract specifications with providers | End of Life - rapid response service spread agreed | Frail Elderly - implementation of patient pathways for health and social care | Re-fresh of the system wide utilisation reviews across all providers to inform areas for further efficiency | Review of emergency care delivery and capacity across the heatlh community | Futher opportunities to be identified in the use of assissted technologies to suport patient management | Assisted Technologies - impact assessment of telehealth/telecare and option appraisal for other conditions | [9 empty] | 500 elective admission reduction | CCG practice referral variation identified and support/training packages developed - E-healthscope / peer review support | Referral Gateway service specification agreed - ICATS | Shared referral decision making practice begins | Evaluation of referral gateway process completed | Elective care patient management reivew completed to agree shifts in the management of inpatient, daycase and outpatient procedures in the most appropriate setting | Elective care capacity review - review across all providers (NHS and IS) to inform capacity required for 13/14 &14/15 | ICAT sevice impact assessment completed | PLV - compliance performance report presented to CCG boards and agreement on additional procdures to be categorised as PLV | Patients being managed in most appropriate setting review completed - benchmarked against BADS/BADS+ | Primary care demand managemnent - assess further opportunities to reduce secondary care demand | Primary care demand management - agreed specialty expansion to reduce secondary care demand | [21 empty] | All specialty follow-up ratios in line with national average 20,500 reduction new and follow-up attendances | Urology PSA - Ensure sign up of the LES and undertake x 2 launch events for City & County CCGs | Opthalmology - Supply 2 Health advert published | Primary Care follow up and Secondary Care follow up agreed across SRGs | Opthalmology - Supply to Health - provider selection process | Community diabetes Community Nursing service to start | Opthalmology - service commencement | Community diabetes service commences | Better Care Better Value benchmark report re-freshed to inform 13/14 contract negotiations | Patient pathway changes included in the 14/15 contracts informed via the BCBC benchmarking information | Additional specialty follow-up reductions agreed | Review of primary care/community care follow-up services completed | Primary Care Demand Management - review of demand management schemes to assess the effectiveness and quality of services delivered | Review of service provision to determine further reduction in follow-up care being provided in secondary care | Secondary care follow-up reduction plan agreed and implementation timeline agreed | Primary and community demand management implementation plan to be agreed | [17 empty] | Top quartile performance on national QIPP indicators | Patent expiry will need to occur as forecast, dependent on DoH time line for Drug Tariff inclusion of drug. | Prescribing practice visits to agree action plans where practices not achieving top quartile national QIPP indicators, particularly antidepressants and laxatives. | Prescribing actions plans implemented | Update scriptswitch prescribing decision making software with latest profiles | Practice prescribing visits to review action plans and review performance against indicators | Practice prescribing visits to review action plans and review performance against indicators | 13/14 CIP developed - further opportunities for efficiencies confirmed | Implementation of further national changes as appropriate | Compliance reivew completed | Implementation of further national opportunities as appropriate
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones | [68 empty] | Number of G&A non-elective FFCEs in the period | [32 empty] | Total number of FFCEs in the period | [32 empty] | All first outpatient attendances (consultant-led) in general and acute specialties
(UNIFY indicators) Anticipated performance at period end | [68 empty] | 96279 | 94647 | 93057 | [30 empty] | 119462 | 117075 | 114967 | [30 empty] | 225449 | 218843 | 212474
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s))) | [101 empty] | Number of elective FFCEs - ordinary admissions | [32 empty] | Number of 1st outpatient attendances (consultant-led) following GP referral in general and acute specialties
(Other KPIs) Anticipated performance at period end | [101 empty] | 26824 | 26070 | 25529 | [30 empty] | 141022 | 137794 | 134612
QIPP Initiative Reporting
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-04-30 | 2014-05-31 | [14 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | 2013-09-30 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2014-08-31 | [13 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-08-31 | 2013-10-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-11-30 | [7 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2014-04-30 | 2014-07-31 | [19 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-10-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | [15 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-09-30 | 2014-04-30 | [20 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31
Progress reporting against milestones and Initiative 1 |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall prog |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly ( |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Amber | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Green | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating
[6 empty] | FYE 11/12 transacted through the contracting process | The programme board and infrastructure to deliver this project is now established and progressing the project deliverables |  | Recruitment of project lead. JDs for team leaders developed. Expressions of interest for team leaders circulated and draft project evaluation protocol produced. | Revised IHSC implementation plan in place. | Agreed at last OSC that this project would be placed on Nov/Dec's OSC agenda. | The approach for Stakeholder and Patient Engagement will be agreed at November's Pathway Development Group Meeting | [22 empty] | Milestones are on track in accordance with the new IHSC delivery programme. Financial QIPP delivery is above plan for both City & County. |  |  |  | Anticipated 31% reduction in activity commencing October 12. | Project Manager has been appointed and implementation is progressing. A presentaton to the local OSC is scheduled and the LA has identified resources to support pt flows | Step down beds open and unit opertional | All placements reviewed and patient pathways confirmed and in final stage of confirming appropriate providers individual patients. | The patient identification process has been agreed and regular meetings are taking place. | Project Manager in place to progress and assess workload of patients to discharge into comm rehab | Progress against milestone under assessment by project Lead | [22 empty] | Milestones are largely on track for the Mental Health QIPP Programme. Financial delivery for County is on track with a slight under delivery for City |  |  |  |  | Eye Casualty review has commenced and reprt due at end of September | The process for practice level validation of regular ED attenders has commenced | Recruited 2 ED Consultants to support CDU re config. Bed space accomodated. Same day tariff to be confirmed for ambulatory cases | Capital Works have started | Advert for recruitment of Geriatrician post advertised at the end of August | [23 empty] | Milestones are largely on track for all schemes. Financial delivery is slightly under for City and County. There is an over performance in non elective activity for both County & City for surgical & medical specialties with Respiratory being the main issue at both acute trusts. Further investigation is being undertaken by CCG's and the Information teams. |  |  |  |  | Service specification agreed and advert placed | Shared referral decision making practice has been implemented | Evaluation of referral gateway completed | [25 empty] | Milestones are largely on track. Financial QIPP delivery is above plan at County and slightly under at City. With regards to activity, elective ordinarys are under plan whilst elective day case are above plan partly as a result of Bowel Cancer Awareness Screening |  |  |  |  | The advert was placed and closed at the end of May 2012 | This has been agreed and transacted as part of the 12/13 provider contract (NUH). However, further opportunity is being sort as part of the joint QIPP delivery group (NUH and CCG/Cluster group) | Providers have been shortlisted and in the clarification stage of the procurement process - on target | [25 empty] | Milestones are largely on track. Financial delivery is under delivering at both City & County. With regards to activity, first OP appts are above plan with with a high backlog of patients to be seen at SFH relating to diagnostic waiting times and challenges with C&B slots availability |  |  |  |  | Practive visits commenced. | All QIPP prescribing plans being implemented | Switchscript update completed. | [25 empty] | Milestones are all on track. Financial delivery is over plan for both County & City
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | In progress | Delayed - amber | In progress | In progress | In progress | In progress | In progress | Work not yet commenced | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | [14 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | Completed | Completed | In progress | In progress | Work not yet commenced | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | In progress | Work not yet commenced | Work not yet commenced | [13 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | Completed | Delayed - amber | In progress | In progress | In progress | Work not yet commenced | Work not yet commenced | In progress | In progress | In progress | In progress | In progress | In progress | In progress | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [7 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | In progress | In progress | In progress | Work not yet commenced | In progress | Work not yet commenced | Work not yet commenced | [19 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | Completed | In progress | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | Work not yet commenced | [15 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact |  |  | Completed | Completed | Completed | Completed | Completed | In progress | In progress | Work not yet commenced | Work not yet commenced | Work not yet commenced | [20 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-04-30 | 2014-05-31 | [13 empty] | 0 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | 2013-09-30 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2014-08-31 | [12 empty] | 0 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-08-31 | 2013-10-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-11-30 | [6 empty] | 0 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2014-04-30 | 2014-07-31 | [18 empty] | 0 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-10-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | [14 empty] | 0 |  |  |  | 2012-04-30 | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-09-30 | 2014-04-30 | [19 empty] | 0 | [32 empty] | 0
| Month 2 | 2012-05-31 |  |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-04-30 | 2014-05-31 | [13 empty] | 0 |  |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | 2013-09-30 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2014-08-31 | [12 empty] | 0 |  |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-08-31 | 2013-10-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-11-30 | [6 empty] | 0 |  |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2014-04-30 | 2014-07-31 | [18 empty] | 0 |  |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-10-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | [14 empty] | 0 |  |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-09-30 | 2014-04-30 | [19 empty] | 0 | [32 empty] | 0
| Month 3 | 2012-06-30 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-04-30 | 2014-05-31 | [13 empty] | 0 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | 2013-09-30 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2012-08-31 | [12 empty] | -24.3333 |  |  |  |  | 2012-05-31 | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-08-31 | 2013-10-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-11-30 | [6 empty] | 0 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2014-04-30 | 2014-07-31 | [18 empty] | 0 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-10-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | [14 empty] | 0 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-09-30 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-09-30 | 2014-04-30 | [19 empty] | 0 | [32 empty] | 0
| Month 4 | 2012-07-31 | [5 empty] | 2012-06-30 | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-12-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-04-30 | 2014-05-31 | [13 empty] | 0 | [6 empty] | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | 2013-09-30 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2014-08-31 | [12 empty] | 0 |  |  |  |  | 2012-05-31 |  | 2012-07-31 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-12-31 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-08-31 | 2013-10-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-11-30 | [6 empty] | 0 | [6 empty] | 2012-07-31 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2014-04-30 | 2014-07-31 | [18 empty] | 0 | [6 empty] | 2012-07-31 | 2012-08-31 | 2012-10-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | [14 empty] | 0 | [7 empty] | 2012-09-30 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-09-30 | 2014-04-30 | [19 empty] | 0 | [32 empty] | 0
| Month 5 | 2012-08-31 | [5 empty] | 2012-09-30 |  | 2012-11-30 | 2012-09-30 | 2012-10-31 | 2013-02-28 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-04-30 | 2014-05-31 | [13 empty] | 9 | [7 empty] | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | 2013-09-30 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2014-08-31 | [12 empty] | 0 |  |  |  |  | 2012-09-30 |  | 2012-09-30 | 2012-08-31 | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-08-31 | 2013-10-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-11-30 | [6 empty] | 5.0667 | [7 empty] | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2014-04-30 | 2014-07-31 | [18 empty] | 0 | [7 empty] | 2012-08-31 | 2012-10-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | [14 empty] | 0 | [7 empty] | 2012-09-30 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-09-30 | 2014-04-30 | [19 empty] | 0 | [32 empty] | 0
| Month 6 | 2012-09-30 | [5 empty] | 2012-09-30 |  | 2012-11-30 | 2012-12-31 | 2012-11-30 | 2013-02-28 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-07-31 | 2013-09-30 | 2013-12-31 | 2014-04-30 | 2014-05-31 | [13 empty] | 13.0667 | [8 empty] | 2012-09-30 | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-07-31 | 2013-09-30 | 2014-01-31 | 2014-04-30 | 2014-05-31 | 2014-08-31 | [12 empty] | 0 |  |  |  |  | 2012-09-30 |  | 2012-09-30 |  | 2012-10-31 | 2012-10-31 | 2012-11-30 | 2012-11-30 | 2013-01-31 | 2013-02-28 | 2013-03-31 | 2013-04-30 | 2013-05-31 | 2013-06-30 | 2013-08-31 | 2013-10-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-07-31 | 2014-08-31 | 2014-11-30 | [6 empty] | 6.1 | [7 empty] | 2012-10-31 | 2012-11-30 | 2013-03-31 | 2013-04-30 | 2013-08-31 | 2014-04-30 | 2014-07-31 | [18 empty] | 0 | [8 empty] | 2012-10-31 | 2013-01-31 | 2013-03-31 | 2013-04-30 | 2013-06-30 | 2013-08-31 | 2013-12-31 | 2014-04-30 | 2014-06-30 | 2014-08-31 | [14 empty] | 0 | [7 empty] | 2012-09-30 | 2012-12-31 | 2013-02-28 | 2013-04-30 | 2013-09-30 | 2014-04-30 | [19 empty] | 0 | [32 empty] | 0
| Month 7 | 2012-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone | [5 empty] | 4 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 4 | 3 | 3 | 2 | 3 | 3 | 3 | [17 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | [16 empty] | 1 | 4 | 1 | 4 | 4 | 4 | 1 | 4 | 4 | 1 | 4 | 4 | 3 | 1 | 4 | 6 | 4 | 4 | 4 | 6 | 4 | 6 | 6 | [10 empty] | 1 | 2 | 3 | 1 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | [22 empty] | 1 | 4 | 4 | 4 | 1 | 4 | 1 | 6 | 6 | 4 | 4 | 6 | 6 | 6 | 6 | [18 empty] | 6 | 1 | 6 | 1 | 6 | 6 | 6 | 6 | 6 | 6
Number of CCGs who have completed this milestone | [5 empty] | 4 | 2 | 2 | 2 | [29 empty] | 6 | 6 | 6 | 6 | [29 empty] | 1 | 4 | 1 | [31 empty] | 2 | 3 | [30 empty] | 1 | 4 | 4 | 4 | [29 empty] | 6 | 1 | 6 | 1
Percentage of PCTs completing this milestone |  |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 100% | 100% | 100% | 0% | 0% | [18 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | bar: 2012-10-31 to 2014-11-30

## EM
Derb | Number of Milestones |  | Completed | In progress | Delayed - amber | Delayed - red | Work not yet commenced | Blank Cells | Total (-blanks) | Total | Nothamp+MK | Number of Milestones |  | Completed | In progress | Delayed - amber | Delayed - red | Work not yet commenced | Blank Cells | Total (-blanks) | Total
Initiative 1 | 23 |  | 2 | 16 | 5 | 0 | 0 | 0 | 23 | 23 | Initiative 1 | 16 |  | 4 | 0 | 0 | 0 | 12 | 0 | 16 | 16
Initiative 2 | 17 |  | 3 | 11 | 3 | 0 | 0 | 0 | 17 | 17 | Initiative 2 | 17 |  | 3 | 0 | 5 | 0 | 9 | 0 | 17 | 17
Initiative 3 | 15 |  | 2 | 11 | 2 | 0 | 0 | 0 | 15 | 15 | Initiative 3 | 29 |  | 4 | 5 | 1 | 0 | 19 | 0 | 29 | 29
Initiative 4 | 15 |  | 2 | 11 | 2 | 0 | 0 | 0 | 15 | 15 | Initiative 4 | 10 |  | 2 | 1 | 1 | 0 | 6 | 0 | 10 | 10
Initiative 5 | 12 |  | 2 | 10 | 0 | 0 | 0 | 0 | 12 | 12 | Initiative 5 | 14 |  | 3 | 2 | 2 | 0 | 7 | 0 | 14 | 14
Initiative 6 | 19 |  | 2 | 15 | 2 | 0 | 0 | 0 | 19 | 19 | Initiative 6 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initiative 7 | 21 |  | 4 | 14 | 3 | 0 | 0 | 0 | 21 | 21 | Initiative 7 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total: | 122 |  | 17 | 88 | 17 | 0 | 0 | 0 | 122 | 122 | Total: | 86 | 0 | 16 | 8 | 9 | 0 | 53 | 0 | 86 | 86
Leics | Number of Milestones |  | Completed | In progress | Delayed - amber | Delayed - red | Work not yet commenced | Blank Cells | Total (-blanks) | Total | Notts | Number of Milestones |  | Completed | In progress | Delayed - amber | Delayed - red | Work not yet commenced | Blank Cells | Total (-blanks) | Total
Initiative 1 | 15 |  | 5 | 0 | 0 | 0 | 0 | 10 | 5 | 15 | Initiative 1 | 16 |  | 4 | 7 | 1 | 0 | 4 | 0 | 16 | 16
Initiative 2 | 15 |  | 2 | 0 | 1 | 0 | 0 | 12 | 3 | 15 | Initiative 2 | 17 |  | 6 | 4 | 0 | 0 | 7 | 0 | 17 | 17
Initiative 3 | 14 |  | 4 | 0 | 0 | 0 | 0 | 10 | 4 | 14 | Initiative 3 | 23 |  | 5 | 11 | 1 | 0 | 6 | 0 | 23 | 23
Initiative 4 | 9 |  | 2 | 0 | 0 | 0 | 0 | 7 | 2 | 9 | Initiative 4 | 11 |  | 4 | 4 | 0 | 0 | 3 | 0 | 11 | 11
Initiative 5 | 10 |  | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 10 | Initiative 5 | 15 |  | 5 | 2 | 0 | 0 | 8 | 0 | 15 | 15
Initiative 6 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Initiative 6 | 10 |  | 5 | 2 | 0 | 0 | 3 | 0 | 10 | 10
Initiative 7 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Initiative 7 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total: | 63 |  | 14 | 0 | 1 | 0 | 0 | 48 | 15 | 63 | Total: | 92 |  | 29 | 30 | 2 | 0 | 31 | 0 | 92 | 92
Linc | Number of Milestones |  | Completed | In progress | Delayed - amber | Delayed - red | Work not yet commenced | Blank Cells | Total (-blanks) | Total
Initiative 1 | 16 |  | 4 | 2 | 2 | 0 | 8 | 0 | 16 | 16
Initiative 2 | 22 |  | 4 | 12 | 2 | 0 | 4 | 0 | 22 | 22
Initiative 3 | 18 |  | 7 | 5 | 1 | 0 | 5 | 0 | 18 | 18
Initiative 4 | 13 |  | 5 | 7 | 0 | 0 | 1 | 0 | 13 | 13
Initiative 5 | 6 |  | 3 | 0 | 0 | 0 | 3 | 0 | 6 | 6
Initiative 6 | 12 |  | 3 | 4 | 0 | 0 | 5 | 0 | 12 | 12
Initiative 7 | 8 |  | 4 | 4 | 0 | 0 | 0 | 0 | 8 | 8
Total: | 95 | 0 | 30 | 34 | 5 | 0 | 26 | 0 | 95 | 95
East Midlands | Number of Milestones |  | Completed | In progress | Delayed - amber | Delayed - red | Work not yet commenced | Blank Cells | Total (-blanks) | Total
Initiative 1 | 86 | 0 | 19 | 25 | 8 | 0 | 24 | 10 | 76 | 86
Initiative 2 | 88 | 0 | 18 | 27 | 11 | 0 | 20 | 12 | 76 | 88
Initiative 3 | 99 | 0 | 22 | 32 | 5 | 0 | 30 | 10 | 89 | 99
Initiative 4 | 58 | 0 | 15 | 23 | 3 | 0 | 10 | 7 | 51 | 58
Initiative 5 | 57 | 0 | 14 | 14 | 2 | 0 | 18 | 9 | 48 | 57
Initiative 6 | 41 | 0 | 10 | 21 | 2 | 0 | 8 | 0 | 41 | 41
Initiative 7 | 29 | 0 | 8 | 18 | 3 | 0 | 0 | 0 | 29 | 29
Total: | 458 | 0 | 106 | 160 | 34 | 0 | 110 | 48 | 410 | 458

## PCTcluster6_QIPPmilestones (hidden)
2012- 2013 Milestone Tracker |  |  | QIPP Initiative 1 | [32 empty] | QIPP Initiative 2 | [32 empty] | QIPP Initiative 3 | [32 empty] | QIPP Initiative 4 | [32 empty] | QIPP Initiative 5 | [32 empty] | QIPP Initiative 6 | [32 empty] | QIPP Initiative 7
QIPP Overview and finances
SHA cluster:
PCT Cluster :
Number of CCGs in cluster:
Report for the month of:
QIPP Challenge (£000s)
FIMS Plan: Savings for CSR period (£000s)
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s)
Yr 2 Plan FIMS savings for 2012-13 (£000s)
Yr 3 Plan FIMS savings for 2013-14 (£000s)
Yr 4 Plan FIMS savings for 2014-15 (£000s)
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 0
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be >50% of years 2-4 (Cells C10:C12)) |  | 0
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 13-14 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative.
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones
(UNIFY indicators) Anticipated performance at period end
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s)))
(Other KPIs) Anticipated performance at period end
QIPP Initiative Reporting
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31
Progress reporting against milestones and Initiative 1 |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall prog |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly ( |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2012-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2012-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2012-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2012-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2012-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2012-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone
Number of CCGs who have completed this milestone
Percentage of PCTs completing this milestone |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## PCTcluster7_QIPPmilestones (hidden)
2012- 2013 Milestone Tracker |  |  | QIPP Initiative 1 | [32 empty] | QIPP Initiative 2 | [32 empty] | QIPP Initiative 3 | [32 empty] | QIPP Initiative 4 | [32 empty] | QIPP Initiative 5 | [32 empty] | QIPP Initiative 6 | [32 empty] | QIPP Initiative 7
QIPP Overview and finances
SHA cluster:
PCT Cluster :
Number of CCGs in cluster:
Report for the month of:
QIPP Challenge (£000s)
FIMS Plan: Savings for CSR period (£000s)
Yr 1 FIMS savings delivered (forecast outturn) 2011-12 (£000s)
Yr 2 Plan FIMS savings for 2012-13 (£000s)
Yr 3 Plan FIMS savings for 2013-14 (£000s)
Yr 4 Plan FIMS savings for 2014-15 (£000s)
Total savings years 1-4 (£000's) (should equal savings for the CSR period (Cell C8)) |  | 0
Estimated value of centrally reported QIPP initiatives in remaining CSR period (£000's) (Should be >50% of years 2-4 (Cells C10C12)) |  | 0
QIPP Initiative Planning
QIPP Initiative scale and title (this should be one of the 5-7 sub-programme area which will contribute to material savings in FIMS Categories) |  |  | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title | [29 empty] | Scale |  |  | Title
FIMS Categories where this initiative will impact (n.b. the sum of savings across all initiatives should be <50% of planned savings) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  |  | Primary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Secondary FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's) |  | Additional FIMS category for savings |  | Estimated savings 2012-13 (£000's) |  | Estimated savings 2013-14 (£000's) |  | Estimated savings 2014-15 (£000's)
Totals of planned savings from this initiative (£000's) |  |  |  |  | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0 | [25 empty] | FIMS savings 2012-13 |  | FIMS savings 2013-14 |  | FIMS savings 2014-15 |  | Total for CSR period | 0
QIPP workstreams supporting this initiative (title / description narrative required) |  |  | Workstream 1A |  |  | Workstream 1B |  |  | Workstream 1C |  |  | Workstream 1D |  |  | Workstream 1E |  |  | Workstream 1F |  |  | Workstream 1G |  |  | Workstream 1H |  |  | Workstream 1I |  |  | Workstream 1J |  |  | Workstream 1K |  |  | Workstream 2A |  |  | Workstream 2B |  |  | Workstream 2C |  |  | Workstream 2D |  |  | Workstream 2E |  |  | Workstream 2F |  |  | Workstream 2G |  |  | Workstream 2H |  |  | Workstream 2I |  |  | Workstream 2J |  |  | Workstream 2K |  |  | Workstream 3A |  |  | Workstream 3B |  |  | Workstream 3C |  |  | Workstream 3D |  |  | Workstream 3E |  |  | Workstream 3F |  |  | Workstream 3G |  |  | Workstream 3H |  |  | Workstream 3I |  |  | Workstream 3J |  |  | Workstream 3K |  |  | Workstream 4A |  |  | Workstream 4B |  |  | Workstream 4C |  |  | Workstream 4D |  |  | Workstream 4E |  |  | Workstream 4F |  |  | Workstream 4G |  |  | Workstream 4H |  |  | Workstream 4I |  |  | Workstream 4J |  |  | Workstream 4K |  |  | Workstream 5A |  |  | Workstream 5B |  |  | Workstream 5C |  |  | Workstream 5D |  |  | Workstream 5E |  |  | Workstream 5F |  |  | Workstream 5G |  |  | Workstream 5H |  |  | Workstream 5I |  |  | Workstream 5J |  |  | Workstream 6K |  |  | Workstream 6A |  |  | Workstream 6B |  |  | Workstream 6C |  |  | Workstream 6D |  |  | Workstream 6E |  |  | Workstream 6F |  |  | Workstream 6G |  |  | Workstream 6H |  |  | Workstream 6I |  |  | Workstream 6J |  |  | Workstream 6K |  |  | Workstream 7A |  |  | Workstream 7B |  |  | Workstream 7C |  |  | Workstream 7D |  |  | Workstream 7E |  |  | Workstream 7F |  |  | Workstream 7G |  |  | Workstream 7H |  |  | Workstream 7I |  |  | Workstream 7J |  |  | Workstream 7K
Focus of workstreams
Optional SHA FIMS Categories (Use where these have been defined within your SHA) |  |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year |  |  | Estimated savings in-year
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 | QIPP LM 1.2 | QIPP LM 1.3 | QIPP LM 1.4 | QIPP LM 1.5 | QIPP LM 1.6 | QIPP LM 1.7 | QIPP LM 1.8 | QIPP LM 1.9 | QIPP LM 1.10 | QIPP LM 1.11 | QIPP LM 1.12 | QIPP LM 1.13 | QIPP LM 1.14 | QIPP LM 1.15 | QIPP LM 1.16 | QIPP LM 1.17 | QIPP LM 1.18 | QIPP LM 1.19 | QIPP LM 1.20 | QIPP LM 1.21 | QIPP LM 1.22 | QIPP LM 1.23 | QIPP LM 1.24 | QIPP LM 1.25 | QIPP LM 1.26 | QIPP LM 1.27 | QIPP LM 1.28 | QIPP LM 1.29 | Risks and issues (initiative level) | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 | QIPP LM 2.2 | QIPP LM 2.3 | QIPP LM 2.4 | QIPP LM 2.5 | QIPP LM 2.6 | QIPP LM 2.7 | QIPP LM 2.8 | QIPP LM 2.9 | QIPP LM 2.10 | QIPP LM 2.11 | QIPP LM 2.12 | QIPP LM 2.13 | QIPP LM 2.14 | QIPP LM 2.15 | QIPP LM 2.16 | QIPP LM 2.17 | QIPP LM 2.18 | QIPP LM 2.19 | QIPP LM 2.20 | QIPP LM 2.21 | QIPP LM 2.22 | QIPP LM 2.23 | QIPP LM 2.24 | QIPP LM 2.25 | QIPP LM 2.26 | QIPP LM 2.27 | QIPP LM 2.28 | QIPP LM 2.29 | Risks and issues (initiative level) | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 14-15 | QIPP LM 3.1 | QIPP LM 3.2 | QIPP LM 3.3 | QIPP LM 3.4 | QIPP LM 3.5 | QIPP LM 3.6 | QIPP LM 3.7 | QIPP LM 3.8 | QIPP LM 3.9 | QIPP LM 3.10 | QIPP LM 3.11 | QIPP LM 3.12 | QIPP LM 3.13 | QIPP LM 3.14 | QIPP LM 3.15 | QIPP LM 3.16 | QIPP LM 3.17 | QIPP LM 3.18 | QIPP LM 3.19 | QIPP LM 3.20 | QIPP LM 3.21 | QIPP LM 3.22 | QIPP LM 3.23 | QIPP LM 3.24 | QIPP LM 3.25 | QIPP LM 3.26 | QIPP LM 3.27 | QIPP LM 3.28 | QIPP LM 3.29 | Risks and issues (initiative level) | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 | QIPP LM 4.2 | QIPP LM 4.3 | QIPP LM 4.4 | QIPP LM 4.5 | QIPP LM 4.6 | QIPP LM 4.7 | QIPP LM 4.8 | QIPP LM 4.9 | QIPP LM 4.10 | QIPP LM 4.11 | QIPP LM 4.12 | QIPP LM 4.13 | QIPP LM 4.14 | QIPP LM 4.15 | QIPP LM 4.16 | QIPP LM 4.17 | QIPP LM 4.18 | QIPP LM 4.19 | QIPP LM 4.20 | QIPP LM 4.21 | QIPP LM 4.22 | QIPP LM 4.23 | QIPP LM 4.24 | QIPP LM 4.25 | QIPP LM 4.26 | QIPP LM 4.27 | QIPP LM 4.28 | QIPP LM 4.29 | Risks and issues (initiative level) | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 | QIPP LM 5.2 | QIPP LM 5.3 | QIPP LM 5.4 | QIPP LM 5.5 | QIPP LM 5.6 | QIPP LM 5.7 | QIPP LM 5.8 | QIPP LM 5.9 | QIPP LM 5.10 | QIPP LM 5.11 | QIPP LM 5.12 | QIPP LM 5.13 | QIPP LM 5.14 | QIPP LM 5.15 | QIPP LM 5.16 | QIPP LM 5.17 | QIPP LM 5.18 | QIPP LM 5.19 | QIPP LM 5.20 | QIPP LM 5.21 | QIPP LM 5.22 | QIPP LM 5.23 | QIPP LM 5.24 | QIPP LM 5.25 | QIPP LM 5.26 | QIPP LM 5.27 | QIPP LM 5.28 | QIPP LM 5.29 | Risks and issues (initiative level) | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 13-14 | QIPP LM 6.1 | QIPP LM 6.2 | QIPP LM 6.3 | QIPP LM 6.4 | QIPP LM 6.5 | QIPP LM 6.6 | QIPP LM 6.7 | QIPP LM 6.8 | QIPP LM 6.9 | QIPP LM 6.10 | QIPP LM 6.11 | QIPP LM 6.12 | QIPP LM 6.13 | QIPP LM 6.14 | QIPP LM 6.15 | QIPP LM 6.16 | QIPP LM 6.17 | QIPP LM 6.18 | QIPP LM 6.19 | QIPP LM 6.20 | QIPP LM 6.21 | QIPP LM 6.22 | QIPP LM 6.23 | QIPP LM 6.24 | QIPP LM 6.25 | QIPP LM 6.26 | QIPP LM 6.27 | QIPP LM 6.28 | QIPP LM 6.29 | Risks and issues (initiative level) | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 | QIPP LM 7.2 | QIPP LM 7.3 | QIPP LM 7.4 | QIPP LM 7.5 | QIPP LM 7.6 | QIPP LM 7.7 | QIPP LM 7.8 | QIPP LM 7.9 | QIPP LM 7.10 | QIPP LM 7.11 | QIPP LM 7.12 | QIPP LM 7.13 | QIPP LM 7.14 | QIPP LM 7.15 | QIPP LM 7.16 | QIPP LM 7.17 | QIPP LM 7.18 | QIPP LM 7.19 | QIPP LM 7.20 | QIPP LM 7.21 | QIPP LM 7.22 | QIPP LM 7.23 | QIPP LM 7.24 | QIPP LM 7.25 | QIPP LM 7.26 | QIPP LM 7.27 | QIPP LM 7.28 | QIPP LM 7.29 | Risks and issues (initiative level)
End state: Enter a description of how the initiative will affect the local healthcare sytem e.g. activity, transfers, quality/adverse quality indicators, health inequalities, incidence/prevalence of illness, morbidity/mortality from specified acute or long term health conditions. And; quantify the number / percentage change you are planning to effect. Provide at least one end state ideally for 2015. For some initiatives, it may be more appropriate to break this down into end states for each remaining year in the CSR period or an end state which falls before 2015. Milestone Descriptors: Enter descriptions of the high level milestones from your integrated plan. Milestones should be provided for key deliverables or outcomes such as decision points (go or no go) and review points that will do to bring about the changes in the local healthcare system as described in the end state. Risks/issues: Enter descriptions of risks or issues which relate to the initiative.
Relevant SUS performance indicators Activity indicators being monitored to identify progress against milestones
(SUS indicators) Anticipated performance at period end
Relevant UNIFY performance indicators Other operating framework measures being tracked to identify progress against milestones
(UNIFY indicators) Anticipated performance at period end
Relevant ESR / workforce performance indicators
(ESR / workforce indicators) Anticipated performance at period end
Relevant other key performance indicator(s)))
(Other KPIs) Anticipated performance at period end
QIPP Initiative Reporting
Milestone type |  |  | QIPP 1 End state 12-13 | QIPP 1 End state 13-14 | QIPP 1 End state 14-15 | QIPP LM 1.1 end | QIPP LM 1.2 end | QIPP LM 1.3 end | QIPP LM 1.4 end | QIPP LM 1.5 end | QIPP LM 1.6 end | QIPP LM 1.7 end | QIPP LM 1.8 end | QIPP LM 1.9 end | QIPP LM 1.10 end | QIPP LM 1.11 end | QIPP LM 1.12 end | QIPP LM 1.13 end | QIPP LM 1.14 end | QIPP LM 1.15 end | QIPP LM 1.16 end | QIPP LM 1.17 end | QIPP LM 1.18 end | QIPP LM 1.19 end | QIPP LM 1.20 end | QIPP LM 1.21 end | QIPP LM 1.22 end | QIPP LM 1.23 end | QIPP LM 1.24 end | QIPP LM 1.25 end | QIPP LM 1.26 end | QIPP LM 1.27 end | QIPP LM 1.28 end | QIPP LM 1.29 end | RAG rating for the Initiative | QIPP 2 End state 12-13 | QIPP 2 End state 13-14 | QIPP 2 End state 14-15 | QIPP LM 2.1 end | QIPP LM 2.2 end | QIPP LM 2.3 end | QIPP LM 2.4 end | QIPP LM 2.5 end | QIPP LM 2.6 end | QIPP LM 2.7 end | QIPP LM 2.8 end | QIPP LM 2.9 end | QIPP LM 2.10 end | QIPP LM 2.11 end | QIPP LM 2.12 end | QIPP LM 2.13 end | QIPP LM 2.14 end | QIPP LM 2.15 end | QIPP LM 2.16 end | QIPP LM 2.17 end | QIPP LM 2.18 end | QIPP LM 2.19 end | QIPP LM 2.20 end | QIPP LM 2.21 end | QIPP LM 2.22 end | QIPP LM 2.23 end | QIPP LM 2.24 end | QIPP LM 2.25 end | QIPP LM 2.26 end | QIPP LM 2.27 end | QIPP LM 2.28 end | QIPP LM 2.29 end | RAG rating for the Initiative | QIPP 3 End state 12-13 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP LM 3.1 end | QIPP LM 3.2 end | QIPP LM 3.3 end | QIPP LM 3.4 end | QIPP LM 3.5 end | QIPP LM 3.6 end | QIPP LM 3.7 end | QIPP LM 3.8 end | QIPP LM 3.9 end | QIPP LM 3.10 end | QIPP LM 3.11 end | QIPP LM 3.12 end | QIPP LM 3.13 end | QIPP LM 3.14 end | QIPP LM 3.15 end | QIPP LM 3.16 end | QIPP LM 3.17 end | QIPP LM 3.18 end | QIPP LM 3.19 end | QIPP LM 3.20 end | QIPP LM 3.21 end | QIPP LM 3.22 end | QIPP LM 3.23 end | QIPP LM 3.24 end | QIPP LM 3.25 end | QIPP LM 3.26 end | QIPP LM 3.27 end | QIPP LM 3.28 end | QIPP LM 3.29 end | RAG rating for the Initiative | QIPP 4 End state 12-13 | QIPP 4 End state 13-14 | QIPP 4 End state 14-15 | QIPP LM 4.1 end | QIPP LM 4.2 end | QIPP LM 4.3 end | QIPP LM 4.4 end | QIPP LM 4.5 end | QIPP LM 4.6 end | QIPP LM 4.7 end | QIPP LM 4.8 end | QIPP LM 4.9 end | QIPP LM 4.10 end | QIPP LM 4.11 end | QIPP LM 4.12 end | QIPP LM 4.13 end | QIPP LM 4.14 end | QIPP LM 4.15 end | QIPP LM 4.16 end | QIPP LM 4.17 end | QIPP LM 4.18 end | QIPP LM 4.19 end | QIPP LM 4.20 end | QIPP LM 4.21 end | QIPP LM 4.22 end | QIPP LM 4.23 end | QIPP LM 4.24 end | QIPP LM 4.25 end | QIPP LM 4.26 end | QIPP LM 4.27 end | QIPP LM 4.28 end | QIPP LM 4.29 end | RAG rating for the Initiative | QIPP 5 End state 12-13 | QIPP 5 End state 13-14 | QIPP 5 End state 14-15 | QIPP LM 5.1 end | QIPP LM 5.2 end | QIPP LM 5.3 end | QIPP LM 5.4 end | QIPP LM 5.5 end | QIPP LM 5.6 end | QIPP LM 5.7 end | QIPP LM 5.8 end | QIPP LM 5.9 end | QIPP LM 5.10 end | QIPP LM 5.11 end | QIPP LM 5.12 end | QIPP LM 5.13 end | QIPP LM 5.14 end | QIPP LM 5.15 end | QIPP LM 5.16 end | QIPP LM 5.17 end | QIPP LM 5.18 end | QIPP LM 5.19 end | QIPP LM 5.20 end | QIPP LM 5.21 end | QIPP LM 5.22 end | QIPP LM 5.23 end | QIPP LM 5.24 end | QIPP LM 5.25 end | QIPP LM 5.26 end | QIPP LM 5.27 end | QIPP LM 5.28 end | QIPP LM 5.29 end | RAG rating for the Initiative | QIPP 6 End state 12-13 | QIPP 6 End state 13-14 | QIPP 6 End state 14-15 | QIPP LM 6.1 end | QIPP LM 6.2 end | QIPP LM 6.3 end | QIPP LM 6.4 end | QIPP LM 6.5 end | QIPP LM 6.6 end | QIPP LM 6.7 end | QIPP LM 6.8 end | QIPP LM 6.9 end | QIPP LM 6.10 end | QIPP LM 6.11 end | QIPP LM 6.12 end | QIPP LM 6.13 end | QIPP LM 6.14 end | QIPP LM 6.15 end | QIPP LM 6.16 end | QIPP LM 6.17 end | QIPP LM 6.18 end | QIPP LM 6.19 end | QIPP LM 6.20 end | QIPP LM 6.21 end | QIPP LM 6.22 end | QIPP LM 6.23 end | QIPP LM 6.24 end | QIPP LM 6.25 end | QIPP LM 6.26 end | QIPP LM 6.27 end | QIPP LM 6.28 end | QIPP LM 6.29 end | RAG rating for the Initiative | QIPP 7 End state 12-13 | QIPP 7 End state 13-14 | QIPP 7 End state 14-15 | QIPP LM 7.1 end | QIPP LM 7.2 end | QIPP LM 7.3 end | QIPP LM 7.4 end | QIPP LM 7.5 end | QIPP LM 7.6 end | QIPP LM 7.7 end | QIPP LM 7.8 end | QIPP LM 7.9 end | QIPP LM 7.10 end | QIPP LM 7.11 end | QIPP LM 7.12 end | QIPP LM 7.13 end | QIPP LM 7.14 end | QIPP LM 7.15 end | QIPP LM 7.16 end | QIPP LM 7.17 end | QIPP LM 7.18 end | QIPP LM 7.19 end | QIPP LM 7.20 end | QIPP LM 7.21 end | QIPP LM 7.22 end | QIPP LM 7.23 end | QIPP LM 7.24 end | QIPP LM 7.25 end | QIPP LM 7.26 end | QIPP LM 7.27 end | QIPP LM 7.28 end | QIPP LM 7.29 end | RAG rating for the Initiative
Milestone due date |  |  | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31 | [30 empty] | 2013-03-31 | 2014-03-31 | 2015-03-31
Progress reporting against milestones and Initiative |  |  | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact on delivery (KPIs and £). Guidance for reporting progress of the initiative ▪ Monthly (optional) Report overall prog |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £) with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly ( |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating | Guidance for reporting progress on milestones This should be updated monthly as required. Slippage should be reported highlighting impact (particularly on KPIs and £)with mitigating actions Guidance for reporting progress for the workstream ▪ Monthly (o |  |  | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | Progress against milestone | RAG Rating
Milestone status |  |  | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact | [32 empty] | Completed = on time and in full; in-progress; Delayed - amber = due date has passed but no material impact on delivery scope or impact; Delayed - red = due date has passed and there is / will be material impact on delivery scope or impact
Date |  |  | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined) | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Forecast delivery | Delays (Combined)
R e p o r t i n g p e r i o d | Month 9 | 2011-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2012-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2012-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2012-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2012-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2012-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2012-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2012-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2012-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2012-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2012-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2012-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2012-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2013-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2013-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2013-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2013-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2013-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2013-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2013-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2013-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2013-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2013-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2013-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2013-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2014-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2014-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2014-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2014-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 2 | 2014-05-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 3 | 2014-06-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 4 | 2014-07-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 5 | 2014-08-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 6 | 2014-09-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 7 | 2014-10-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 8 | 2014-11-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 9 | 2014-12-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 10 | 2015-01-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 11 | 2015-02-28 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 12 | 2015-03-31 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
| Month 1 | 2015-04-30 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0 | [32 empty] | 0
Number of CCGs signed up to this milestone
Number of CCGs who have completed this milestone
Percentage of PCTs completing this milestone |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## lists (hidden)
SHA Milestone Type commissioning support | SHA Milestone end date commissioning support | SHA Milestone Type Clinical Commissioning Groups | SHA Milestone end date Clinical Commissioning Groups | SHA Milestone Type Direct Commissioning | SHA Milestone end date Direct Commissioning | SHA Milestone Type Any Qualified Provider | SHA Milestone end date Any Qualified Provider | SHA Milestone Type Health and Well Being Boards | SHA Milestone end date Health and Well Being Boards | SHA Milestone Type Public Health Transfer to Local Authorities | SHA Milestone end date Public Health Transfer to Local Authorities | SHA Milestone Type Public Health Transfer to Public Health England | SHA Milestone end date Public Health Transfer to Public Health England | PCT Milestone Type commissioning support | PCT Milestone end date commissioning support | PCT Milestone Type Clinical Commissioning Groups | PCT Milestone end date Clinical Commissioning Groups | PCT Milestone Type Direct Commissioning | PCT Milestone end date Direct Commissioning | PCT Milestone Type Any Qualified Provider | PCT Milestone end date Any Qualified Provider | PCT Milestone Type Health and Well Being Boards | PCT Milestone end date Health and Well Being Boards | PCT Milestone Type Public Health Transfer to Local Authorities | PCT Milestone end date Public Health Transfer to Local Authorities | PCT Milestone Type Public Health Transfer to Public Health England | PCT Milestone end date Public Health Transfer to Public Health England | PCT Milestone Type QIPP Initiative 1 | PCT Milestone end date QIPP Initiative 1 | PCT Milestone Type QIPP Initiative 2 | PCT Milestone end date QIPP Initiative 2 | PCT Milestone Type QIPP Initiative 3 | PCT Milestone end date QIPP Initiative 3 | PCT Milestone Type QIPP Initiative 4 | PCT Milestone end date QIPP Initiative 4 | PCT Milestone Type QIPP Initiative 5 | PCT Milestone end date QIPP Initiative 5 | PCT Milestone Type QIPP Initiative 6 | PCT Milestone end date QIPP Initiative 6 | PCT Milestone Type QIPP Initiative 7 | PCT Milestone end date QIPP Initiative 7 | PCT Milestone Type QIPP Initiative 8 | PCT Milestone end date QIPP Initiative 8 | PCT Milestone Type QIPP Initiative 9 | PCT Milestone end date QIPP Initiative 9 | PCT Milestone Type Foundation Trusts | PCT Milestone end date Foundation Trusts | Date | QIPP Workstream focus | Scale of QIPP workstream | FIMS Categories | FIMS Categories Level 2 SHA | Project Categories | RAG Rating | Milestone status | SHA Cluster | PCT cluster | CCG | Number of organisations
SHA CS End state 12-13 | SHA CS End state 12-13 | SHA CCG End state 12-13 | SHA CCG End state 12-13 | SHA DC End state 12-13 | SHA DC End state 12-13 | SHA AQP End state 12-13 | SHA AQP End state 12-13 | SHA HWB End state 12-13 | SHA HWB End state 12-13 | SHA PHT LAs End state 12-13 | SHA PHT LAs End state 12-13 | SHA PHT PHE End state 12-13 | SHA PHT PHE End state 12-13 | PCT CS End state 12-13 | PCT CS End state 12-13 | PCT CCG End state 12-13 | PCT CCG End state 12-13 | PCT DC End state 12-13 | PCT DC End state 12-13 | PCT AQP End state 12-13 | PCT AQP End state 12-13 | PCT HWB End state 12-13 | PCT HWB End state 12-13 | PCT PHT LAs End state 12-13 | PCT PHT LAs End state 12-13 | PCT PHT PHE End state 12-13 | PCT PHT PHE End state 12-13 | QIPP 1 End state 12-13 | QIPP 1 End state 12-13 | QIPP 2 End state 12-13 | QIPP 2 End state 12-13 | QIPP 3 End state 12-13 | QIPP 3 End state 12-13 | QIPP 4 End state 12-13 | QIPP 4 End state 12-13 | QIPP 5 End state 12-13 | QIPP 5 End state 12-13 | QIPP 6 End state 12-13 | QIPP 6 End state 12-13 | QIPP 7 End state 12-13 | QIPP 7 End state 12-13 | QIPP 8 End state 12-13 | QIPP 8 End state 12-13 | QIPP 9 End state 12-13 | QIPP 9 End state 12-13 | FTs End state 12-13 | FTs End state 12-13 | 2011-12-31 | Quality | CCG | Not applicable | Not applicable | Mental health | Red | Completed | NHS London | Bristol & N Somerset & S Gloucestershire |  | N/A
SHA CS NME 1 | SHA CS NME 1 end | SHA CCG NME 1 | SHA CCG NME 1 end | SHA DC NME 1 | SHA DC NME 1 end | SHA AQP NME 1 | SHA AQP NME 1 end | SHA HWB NME 1 | SHA HWB NME 1 end | SHA PHT LAs NME 1 | SHA PHT LAs NME 1 end | SHA PHT PHE NME 1 | SHA PHT PHE NME 1 end | PCT CS NME 1 | PCT CS NME 1 end | PCT CCG NME 1 | PCT CCG NME 1 end | PCT DC NME 1 | PCT DC NME 1 end | PCT AQP NME 1 | PCT AQP NME 1 end | PCT HWB NME 1 | PCT HWB NME 1 end | PCT PHT LAs NME 1 | PCT PHT LAs NME 1 end | PCT PHT PHE NME 1 | PCT PHT PHE NME 1 end | QIPP 1 End state 13-14 | QIPP 1 End state 13-14 | QIPP 2 End state 13-14 | QIPP 2 End state 13-14 | QIPP 3 End state 13-14 | QIPP 3 End state 13-14 | QIPP 4 End state 13-14 | QIPP 4 End state 13-14 | QIPP 5 End state 13-14 | QIPP 5 End state 13-14 | QIPP 6 End state 13-14 | QIPP 6 End state 13-14 | QIPP 7 End state 13-14 | QIPP 7 End state 13-14 | QIPP 8 End state 13-14 | QIPP 8 End state 13-14 | QIPP 9 End state 13-14 | QIPP 9 End state 13-14 | FTs NME 1 | FTs NME 1 end | 2012-01-31 | Activity | PCT | Acute Contracts (Elective) | Productivity | Acute Sector | Amber | In progress | NHS Midlands and East | Bournemouth Poole & Dorset |  | 1
SHA CS NME 2 | SHA CS NME 2 end | SHA CCG NME 2 | SHA CCG NME 2 end | SHA DC NME 2 | SHA DC NME 2 end | SHA AQP NME 2 | SHA AQP NME 2 end | SHA HWB NME 2 | SHA HWB NME 2 end | SHA PHT LAs NME 2 | SHA PHT LAs NME 2 end | SHA PHT PHE NME 2 | SHA PHT PHE NME 2 end | PCT CS NME 2 | PCT CS NME 2 end | PCT CCG NME 2 | PCT CCG NME 2 end | PCT DC NME 2 | PCT DC NME 2 end | PCT AQP NME 2 | PCT AQP NME 2 end | PCT HWB NME 2 | PCT HWB NME 2 end | PCT PHT LAs NME 2 | PCT PHT LAs NME 2 end | PCT PHT PHE NME 2 | PCT PHT PHE NME 2 end | QIPP 1 End state 14-15 | QIPP 1 End state 14-15 | QIPP 2 End state 14-15 | QIPP 2 End state 14-15 | QIPP 3 End state 14-15 | QIPP 3 End state 14-15 | QIPP 4 End state 14-15 | QIPP 4 End state 14-15 | QIPP 5 End state 14-15 | QIPP 5 End state 14-15 | QIPP 6 End state 14-15 | QIPP 6 End state 14-15 | QIPP 7 End state 14-15 | QIPP 7 End state 14-15 | QIPP 8 End state 14-15 | QIPP 8 End state 14-15 | QIPP 9 End state 14-15 | QIPP 9 End state 14-15 | FTs NME 2 | FTs NME 2 end | 2012-02-28 | Workforce | PCT cluster | Acute Contracts (Non Elective) | Integrated care | Primary care productivity | Green | Delayed - amber | NHS North of England | Devon & Torbay |  | 2
SHA CS NME 3 | SHA CS NME 3 end | SHA CCG NME 3 | SHA CCG NME 3 end | SHA DC NME 3 | SHA DC NME 3 end | SHA AQP NME 3 | SHA AQP NME 3 end | SHA HWB NME 3 | SHA HWB NME 3 end | SHA PHT LAs NME 3 | SHA PHT LAs NME 3 end | SHA PHT PHE NME 3 | SHA PHT PHE NME 3 end | PCT CS NME 3 | PCT CS NME 3 end | PCT CCG NME 3 | PCT CCG NME 3 end | PCT DC NME 3 | PCT DC NME 3 end | PCT AQP NME 3 | PCT AQP NME 3 end | PCT HWB NME 3 | PCT HWB NME 3 end | PCT PHT LAs NME 3 | PCT PHT LAs NME 3 end | PCT PHT PHE NME 3 | PCT PHT PHE NME 3 end | QIPP LM 1.1 | QIPP LM 1.1 end | QIPP LM 2.1 | QIPP LM 2.1 end | QIPP LM 3.1 | QIPP LM 3.1 end | QIPP LM 4.1 | QIPP LM 4.1 end | QIPP LM 5.1 | QIPP LM 5.1 end | QIPP LM 6.1 | QIPP LM 6.1 end | QIPP LM 7.1 | QIPP LM 7.1 end | QIPP LM 8.1 | QIPP LM 8.1 end | QIPP LM 9.1 | QIPP LM 9.1 end | FTs NME 3 | FTs NME 3 end | 2012-03-31 | Finance | Pan SHA | Acute Contracts (Outpatients) | Procurement | Community support services | No rating | Delayed - red | NHS South of England | Gloucestershire (& Swindon) |  | 3
SHA CS NME 4 | SHA CS NME 4 end | SHA CCG NME 4 | SHA CCG NME 4 end | SHA DC NME 4 | SHA DC NME 4 end | SHA AQP NME 4 | SHA AQP NME 4 end | SHA HWB NME 4 | SHA HWB NME 4 end | SHA PHT LAs NME 4 | SHA PHT LAs NME 4 end | SHA PHT PHE NME 4 | SHA PHT PHE NME 4 end | PCT CS NME 4 | PCT CS NME 4 end | PCT CCG NME 4 | PCT CCG NME 4 end | PCT DC NME 4 | PCT DC NME 4 end | PCT AQP NME 4 | PCT AQP NME 4 end | PCT HWB NME 4 | PCT HWB NME 4 end | PCT PHT LAs NME 4 | PCT PHT LAs NME 4 end | PCT PHT PHE NME 4 | PCT PHT PHE NME 4 end | QIPP LM 1.2 | QIPP LM 1.2 end | QIPP LM 2.2 | QIPP LM 2.2 end | QIPP LM 3.2 | QIPP LM 3.2 end | QIPP LM 4.2 | QIPP LM 4.2 end | QIPP LM 5.2 | QIPP LM 5.2 end | QIPP LM 6.2 | QIPP LM 6.2 end | QIPP LM 7.2 | QIPP LM 7.2 end | QIPP LM 8.2 | QIPP LM 8.2 end | QIPP LM 9.2 | QIPP LM 9.2 end | FTs NME 4 | FTs NME 4 end | 2012-04-30 | Quality & activity | SHA Cluster | Acute Contracts (Direct Access) | Demand management | Activity shifts |  | Work not yet commenced |  | Swindon (& Gloucestershire) |  | 4
SHA CS NME 5 | SHA CS NME 5 end | SHA CCG NME 5 | SHA CCG NME 5 end | SHA DC NME 5 | SHA DC NME 5 end | SHA AQP NME 5 | SHA AQP NME 5 end | SHA HWB NME 5 | SHA HWB NME 5 end | SHA PHT LAs NME 5 | SHA PHT LAs NME 5 end | SHA PHT PHE NME 5 | SHA PHT PHE NME 5 end | PCT CS NME 5 | PCT CS NME 5 end | PCT CCG NME 5 | PCT CCG NME 5 end | PCT DC NME 5 | PCT DC NME 5 end | PCT AQP NME 5 | PCT AQP NME 5 end | PCT HWB NME 5 | PCT HWB NME 5 end | PCT PHT LAs NME 5 | PCT PHT LAs NME 5 end | PCT PHT PHE NME 5 | PCT PHT PHE NME 5 end | QIPP LM 1.3 | QIPP LM 1.3 end | QIPP LM 2.3 | QIPP LM 2.3 end | QIPP LM 3.3 | QIPP LM 3.3 end | QIPP LM 4.3 | QIPP LM 4.3 end | QIPP LM 5.3 | QIPP LM 5.3 end | QIPP LM 6.3 | QIPP LM 6.3 end | QIPP LM 7.3 | QIPP LM 7.3 end | QIPP LM 8.3 | QIPP LM 8.3 end | QIPP LM 9.3 | QIPP LM 9.3 end | FTs NME 5 | FTs NME 5 end | 2012-05-31 | Quality & workforce |  | Acute Contracts (Other) | Running costs | Long Term Conditions |  |  |  | Bath NE Somerset & Wiltshire |  | 5
SHA CS NME 6 | SHA CS NME 6 end | SHA CCG NME 6 | SHA CCG NME 6 end | SHA DC NME 6 | SHA DC NME 6 end | SHA AQP NME 6 | SHA AQP NME 6 end | SHA HWB NME 6 | SHA HWB NME 6 end | SHA PHT LAs NME 6 | SHA PHT LAs NME 6 end | SHA PHT PHE NME 6 | SHA PHT PHE NME 6 end | PCT CS NME 6 | PCT CS NME 6 end | PCT CCG NME 6 | PCT CCG NME 6 end | PCT DC NME 6 | PCT DC NME 6 end | PCT AQP NME 6 | PCT AQP NME 6 end | PCT HWB NME 6 | PCT HWB NME 6 end | PCT PHT LAs NME 6 | PCT PHT LAs NME 6 end | PCT PHT PHE NME 6 | PCT PHT PHE NME 6 end | QIPP LM 1.4 | QIPP LM 1.4 end | QIPP LM 2.4 | QIPP LM 2.4 end | QIPP LM 3.4 | QIPP LM 3.4 end | QIPP LM 4.4 | QIPP LM 4.4 end | QIPP LM 5.4 | QIPP LM 5.4 end | QIPP LM 6.4 | QIPP LM 6.4 end | QIPP LM 7.4 | QIPP LM 7.4 end | QIPP LM 8.4 | QIPP LM 8.4 end | QIPP LM 9.4 | QIPP LM 9.4 end | FTs NME 6 | FTs NME 6 end | 2012-06-30 | Quality & finance |  | Mental Health & Learning Disabilities Contracts | Clinical overheads | Urgent Care |  |  |  | Cornwall & Isle of Scilly |  | 6
SHA CS NME 7 | SHA CS NME 7 end | SHA CCG NME 7 | SHA CCG NME 7 end | SHA DC NME 7 | SHA DC NME 7 end | SHA AQP NME 7 | SHA AQP NME 7 end | SHA HWB NME 7 | SHA HWB NME 7 end | SHA PHT LAs NME 7 | SHA PHT LAs NME 7 end | SHA PHT PHE NME 7 | SHA PHT PHE NME 7 end | PCT CS NME 7 | PCT CS NME 7 end | PCT CCG NME 7 | PCT CCG NME 7 end | PCT DC NME 7 | PCT DC NME 7 end | PCT AQP NME 7 | PCT AQP NME 7 end | PCT HWB NME 7 | PCT HWB NME 7 end | PCT PHT LAs NME 7 | PCT PHT LAs NME 7 end | PCT PHT PHE NME 7 | PCT PHT PHE NME 7 end | QIPP LM 1.5 | QIPP LM 1.5 end | QIPP LM 2.5 | QIPP LM 2.5 end | QIPP LM 3.5 | QIPP LM 3.5 end | QIPP LM 4.5 | QIPP LM 4.5 end | QIPP LM 5.5 | QIPP LM 5.5 end | QIPP LM 6.5 | QIPP LM 6.5 end | QIPP LM 7.5 | QIPP LM 7.5 end | QIPP LM 8.5 | QIPP LM 8.5 end | QIPP LM 9.5 | QIPP LM 9.5 end | FTs NME 7 | FTs NME 7 end | 2012-07-31 | Activity & Workforce |  | Community Contracts | Reducing drug spend | Planned Care |  |  |  | Somerset |  | 7
SHA CS NME 8 | SHA CS NME 8 end | SHA CCG NME 8 | SHA CCG NME 8 end | SHA DC NME 8 | SHA DC NME 8 end | SHA AQP NME 8 | SHA AQP NME 8 end | SHA HWB NME 8 | SHA HWB NME 8 end | SHA PHT LAs NME 8 | SHA PHT LAs NME 8 end | SHA PHT PHE NME 8 | SHA PHT PHE NME 8 end | PCT CS NME 8 | PCT CS NME 8 end | PCT CCG NME 8 | PCT CCG NME 8 end | PCT DC NME 8 | PCT DC NME 8 end | PCT AQP NME 8 | PCT AQP NME 8 end | PCT HWB NME 8 | PCT HWB NME 8 end | PCT PHT LAs NME 8 | PCT PHT LAs NME 8 end | PCT PHT PHE NME 8 | PCT PHT PHE NME 8 end | QIPP LM 1.6 | QIPP LM 1.6 end | QIPP LM 2.6 | QIPP LM 2.6 end | QIPP LM 3.6 | QIPP LM 3.6 end | QIPP LM 4.6 | QIPP LM 4.6 end | QIPP LM 5.6 | QIPP LM 5.6 end | QIPP LM 6.6 | QIPP LM 6.6 end | QIPP LM 7.6 | QIPP LM 7.6 end | QIPP LM 8.6 | QIPP LM 8.6 end | QIPP LM 9.6 | QIPP LM 9.6 end | FTs NME 8 | FTs NME 8 end | 2012-08-31 | Activity & finance |  | Ambulance Contracts | Unidentified | End of Life Care |  |  |  | Berkshire |  | 8
SHA CS NME 9 | SHA CS NME 9 end | SHA CCG NME 9 | SHA CCG NME 9 end | SHA DC NME 9 | SHA DC NME 9 end | SHA AQP NME 9 | SHA AQP NME 9 end | SHA HWB NME 9 | SHA HWB NME 9 end | SHA PHT LAs NME 9 | SHA PHT LAs NME 9 end | SHA PHT PHE NME 9 | SHA PHT PHE NME 9 end | PCT CS NME 9 | PCT CS NME 9 end | PCT CCG NME 9 | PCT CCG NME 9 end | PCT DC NME 9 | PCT DC NME 9 end | PCT AQP NME 9 | PCT AQP NME 9 end | PCT HWB NME 9 | PCT HWB NME 9 end | PCT PHT LAs NME 9 | PCT PHT LAs NME 9 end | PCT PHT PHE NME 9 | PCT PHT PHE NME 9 end | QIPP LM 1.7 | QIPP LM 1.7 end | QIPP LM 2.7 | QIPP LM 2.7 end | QIPP LM 3.7 | QIPP LM 3.7 end | QIPP LM 4.7 | QIPP LM 4.7 end | QIPP LM 5.7 | QIPP LM 5.7 end | QIPP LM 6.7 | QIPP LM 6.7 end | QIPP LM 7.7 | QIPP LM 7.7 end | QIPP LM 8.7 | QIPP LM 8.7 end | QIPP LM 9.7 | QIPP LM 9.7 end | FTs NME 9 | FTs NME 9 end | 2012-09-30 | Workforce & finance |  | Specialised Commissioning |  | Prevention |  |  |  | Oxfordshire & Buckinghamshire - Oxford |  | 9
SHA CS NME 10 | SHA CS NME 10 end | SHA CCG NME 10 | SHA CCG NME 10 end | SHA DC NME 10 | SHA DC NME 10 end | SHA AQP NME 10 | SHA AQP NME 10 end | SHA HWB NME 10 | SHA HWB NME 10 end | SHA PHT LAs NME 10 | SHA PHT LAs NME 10 end | SHA PHT PHE NME 10 | SHA PHT PHE NME 10 end | PCT CS NME 10 | PCT CS NME 10 end | PCT CCG NME 10 | PCT CCG NME 10 end | PCT DC NME 10 | PCT DC NME 10 end | PCT AQP NME 10 | PCT AQP NME 10 end | PCT HWB NME 10 | PCT HWB NME 10 end | PCT PHT LAs NME 10 | PCT PHT LAs NME 10 end | PCT PHT PHE NME 10 | PCT PHT PHE NME 10 end | QIPP LM 1.8 | QIPP LM 1.8 end | QIPP LM 2.8 | QIPP LM 2.8 end | QIPP LM 3.8 | QIPP LM 3.8 end | QIPP LM 4.8 | QIPP LM 4.8 end | QIPP LM 5.8 | QIPP LM 5.8 end | QIPP LM 6.8 | QIPP LM 6.8 end | QIPP LM 7.8 | QIPP LM 7.8 end | QIPP LM 8.8 | QIPP LM 8.8 end | QIPP LM 9.8 | QIPP LM 9.8 end | FTs NME 10 | FTs NME 10 end | 2012-10-31 | Quality, activity & finance |  | Non-NHS Healthcare Contracts (inc reablement) |  | Staying Healthy |  |  |  | Oxfordshire & Buckinghamshire - Bucks |  | 10
SHA CS NME 11 | SHA CS NME 11 end | SHA CCG NME 11 | SHA CCG NME 11 end | SHA DC NME 11 | SHA DC NME 11 end | SHA AQP NME 11 | SHA AQP NME 11 end | SHA HWB NME 11 | SHA HWB NME 11 end | SHA PHT LAs NME 11 | SHA PHT LAs NME 11 end | SHA PHT PHE NME 11 | SHA PHT PHE NME 11 end | PCT CS NME 11 | PCT CS NME 11 end | PCT CCG NME 11 | PCT CCG NME 11 end | PCT DC NME 11 | PCT DC NME 11 end | PCT AQP NME 11 | PCT AQP NME 11 end | PCT HWB NME 11 | PCT HWB NME 11 end | PCT PHT LAs NME 11 | PCT PHT LAs NME 11 end | PCT PHT PHE NME 11 | PCT PHT PHE NME 11 end | QIPP LM 1.9 | QIPP LM 1.9 end | QIPP LM 2.9 | QIPP LM 2.9 end | QIPP LM 3.9 | QIPP LM 3.9 end | QIPP LM 4.9 | QIPP LM 4.9 end | QIPP LM 5.9 | QIPP LM 5.9 end | QIPP LM 6.9 | QIPP LM 6.9 end | QIPP LM 7.9 | QIPP LM 7.9 end | QIPP LM 8.9 | QIPP LM 8.9 end | QIPP LM 9.9 | QIPP LM 9.9 end | FTs NME 11 | FTs NME 11 end | 2012-11-30 | Quality, activity & workforce |  | Continuing Healthcare |  | Non Clinical Procurement |  |  |  | SHIP |  | 11
SHA CS NME 12 | SHA CS NME 12 end | SHA CCG NME 12 | SHA CCG NME 12 end | SHA DC NME 12 | SHA DC NME 12 end | SHA AQP NME 12 | SHA AQP NME 12 end | SHA HWB NME 12 | SHA HWB NME 12 end | SHA PHT LAs NME 12 | SHA PHT LAs NME 12 end | SHA PHT PHE NME 12 | SHA PHT PHE NME 12 end | PCT CS NME 12 | PCT CS NME 12 end | PCT CCG NME 12 | PCT CCG NME 12 end | PCT DC NME 12 | PCT DC NME 12 end | PCT AQP NME 12 | PCT AQP NME 12 end | PCT HWB NME 12 | PCT HWB NME 12 end | PCT PHT LAs NME 12 | PCT PHT LAs NME 12 end | PCT PHT PHE NME 12 | PCT PHT PHE NME 12 end | QIPP LM 1.10 | QIPP LM 1.10 end | QIPP LM 2.10 | QIPP LM 2.10 end | QIPP LM 3.10 | QIPP LM 3.10 end | QIPP LM 4.10 | QIPP LM 4.10 end | QIPP LM 5.10 | QIPP LM 5.10 end | QIPP LM 6.10 | QIPP LM 6.10 end | QIPP LM 7.10 | QIPP LM 7.10 end | QIPP LM 8.10 | QIPP LM 8.10 end | QIPP LM 9.10 | QIPP LM 9.10 end | FTs NME 12 | FTs NME 12 end | 2012-12-31 | Quality, activity workforce & finance |  | Primary Care Prescribing |  | Decommissioning ineffective procedures |  |  |  | Surrey |  | 12
SHA CS NME 13 | SHA CS NME 13 end | SHA CCG NME 13 | SHA CCG NME 13 end | SHA DC NME 13 | SHA DC NME 13 end | SHA AQP NME 13 | SHA AQP NME 13 end | SHA HWB NME 13 | SHA HWB NME 13 end | SHA PHT LAs NME 13 | SHA PHT LAs NME 13 end | SHA PHT PHE NME 13 | SHA PHT PHE NME 13 end | PCT CS NME 13 | PCT CS NME 13 end | PCT CCG NME 13 | PCT CCG NME 13 end | PCT DC NME 13 | PCT DC NME 13 end | PCT AQP NME 13 | PCT AQP NME 13 end | PCT HWB NME 13 | PCT HWB NME 13 end | PCT PHT LAs NME 13 | PCT PHT LAs NME 13 end | PCT PHT PHE NME 13 | PCT PHT PHE NME 13 end | QIPP LM 1.11 | QIPP LM 1.11 end | QIPP LM 2.11 | QIPP LM 2.11 end | QIPP LM 3.11 | QIPP LM 3.11 end | QIPP LM 4.11 | QIPP LM 4.11 end | QIPP LM 5.11 | QIPP LM 5.11 end | QIPP LM 6.11 | QIPP LM 6.11 end | QIPP LM 7.11 | QIPP LM 7.11 end | QIPP LM 8.11 | QIPP LM 8.11 end | QIPP LM 9.11 | QIPP LM 9.11 end | FTs NME 13 | FTs NME 13 end | 2013-01-31 | Activity workforce & finance |  | Excluded Drugs & Devices |  | Enhanced recovery |  |  |  | Sussex |  | 13
SHA CS NME 14 | SHA CS NME 14 end | SHA CCG NME 14 | SHA CCG NME 14 end | SHA DC NME 14 | SHA DC NME 14 end | SHA AQP NME 14 | SHA AQP NME 14 end | SHA HWB NME 14 | SHA HWB NME 14 end | SHA PHT LAs NME 14 | SHA PHT LAs NME 14 end | SHA PHT PHE NME 14 | SHA PHT PHE NME 14 end | PCT CS NME 14 | PCT CS NME 14 end | PCT CCG NME 14 | PCT CCG NME 14 end | PCT DC NME 14 | PCT DC NME 14 end | PCT AQP NME 14 | PCT AQP NME 14 end | PCT HWB NME 14 | PCT HWB NME 14 end | PCT PHT LAs NME 14 | PCT PHT LAs NME 14 end | PCT PHT PHE NME 14 | PCT PHT PHE NME 14 end | QIPP LM 1.12 | QIPP LM 1.12 end | QIPP LM 2.12 | QIPP LM 2.12 end | QIPP LM 3.12 | QIPP LM 3.12 end | QIPP LM 4.12 | QIPP LM 4.12 end | QIPP LM 5.12 | QIPP LM 5.12 end | QIPP LM 6.12 | QIPP LM 6.12 end | QIPP LM 7.12 | QIPP LM 7.12 end | QIPP LM 8.12 | QIPP LM 8.12 end | QIPP LM 9.12 | QIPP LM 9.12 end | FTs NME 14 | FTs NME 14 end | 2013-02-28 | Quality workforce & finance |  | Primary Care, Dental, Pharmacy, Opthalmic |  | Referral management |  |  |  | Kent & Medway |  | 14
SHA CS NME 15 | SHA CS NME 15 end | SHA CCG NME 15 | SHA CCG NME 15 end | SHA DC NME 15 | SHA DC NME 15 end | SHA AQP NME 15 | SHA AQP NME 15 end | SHA HWB NME 15 | SHA HWB NME 15 end | SHA PHT LAs NME 15 | SHA PHT LAs NME 15 end | SHA PHT PHE NME 15 | SHA PHT PHE NME 15 end | PCT CS NME 15 | PCT CS NME 15 end | PCT CCG NME 15 | PCT CCG NME 15 end | PCT DC NME 15 | PCT DC NME 15 end | PCT AQP NME 15 | PCT AQP NME 15 end | PCT HWB NME 15 | PCT HWB NME 15 end | PCT PHT LAs NME 15 | PCT PHT LAs NME 15 end | PCT PHT PHE NME 15 | PCT PHT PHE NME 15 end | QIPP LM 1.13 | QIPP LM 1.13 end | QIPP LM 2.13 | QIPP LM 2.13 end | QIPP LM 3.13 | QIPP LM 3.13 end | QIPP LM 4.13 | QIPP LM 4.13 end | QIPP LM 5.13 | QIPP LM 5.13 end | QIPP LM 6.13 | QIPP LM 6.13 end | QIPP LM 7.13 | QIPP LM 7.13 end | QIPP LM 8.13 | QIPP LM 8.13 end | QIPP LM 9.13 | QIPP LM 9.13 end | FTs NME 15 | FTs NME end | 2013-03-31 |  |  | PCT Running Costs |  | Back office |  |  |  | Black Country |  | 15
SHA CS NME 16 | SHA CS NME 16 end | SHA CCG NME 16 | SHA CCG NME 16 end | SHA DC NME 16 | SHA DC NME 16 end | SHA AQP NME 16 | SHA AQP NME 16 end | SHA HWB NME 16 | SHA HWB NME 16 end | SHA PHT LAs NME 16 | SHA PHT LAs NME 16 end | SHA PHT PHE NME 16 | SHA PHT PHE NME 16 end | PCT CS NME 16 | PCT CS NME 16 end | PCT CCG NME 16 | PCT CCG NME 16 end | PCT DC NME 16 | PCT DC NME 16 end | PCT AQP NME 16 | PCT AQP NME 16 end | PCT HWB NME 16 | PCT HWB NME 16 end | PCT PHT LAs NME 16 | PCT PHT LAs NME 16 end | PCT PHT PHE NME 16 | PCT PHT PHE NME 16 end | QIPP LM 1.14 | QIPP LM 1.14 end | QIPP LM 2.14 | QIPP LM 2.14 end | QIPP LM 3.14 | QIPP LM 3.14 end | QIPP LM 4.14 | QIPP LM 4.14 end | QIPP LM 5.14 | QIPP LM 5.14 end | QIPP LM 6.14 | QIPP LM 6.14 end | QIPP LM 7.14 | QIPP LM 7.14 end | QIPP LM 8.14 | QIPP LM 8.14 end | QIPP LM 9.14 | QIPP LM 9.14 end | FTs NME 16 | FTs NME 16 end | 2013-04-30 |  |  | Other |  | Estates |  |  |  | Staffordshire |  | 16
SHA CS NME 17 | SHA CS NME 17 end | SHA CCG NME 17 | SHA CCG NME 17 end | SHA DC NME 17 | SHA DC NME 17 end | SHA AQP NME 17 | SHA AQP NME 17 end | SHA HWB NME 17 | SHA HWB NME 17 end | SHA PHT LAs NME 17 | SHA PHT LAs NME 17 end | SHA PHT PHE NME 17 | SHA PHT PHE NME 17 end | PCT CS NME 17 | PCT CS NME 17 end | PCT CCG NME 17 | PCT CCG NME 17 end | PCT DC NME 17 | PCT DC NME 17 end | PCT AQP NME 17 | PCT AQP NME 17 end | PCT HWB NME 17 | PCT HWB NME 17 end | PCT PHT LAs NME 17 | PCT PHT LAs NME 17 end | PCT PHT PHE NME 17 | PCT PHT PHE NME 17 end | QIPP LM 1.15 | QIPP LM 1.15 end | QIPP LM 2.15 | QIPP LM 2.15 end | QIPP LM 3.15 | QIPP LM 3.15 end | QIPP LM 4.15 | QIPP LM 4.15 end | QIPP LM 5.15 | QIPP LM 5.15 end | QIPP LM 6.15 | QIPP LM 6.15 end | QIPP LM 7.15 | QIPP LM 7.15 end | QIPP LM 8.15 | QIPP LM 8.15 end | QIPP LM 9.15 | QIPP LM 9.15 end | FTs NME 17 | FTs NME 17 end | 2013-05-31 |  |  |  |  | Staffing |  |  |  | West Mercia |  | 17
SHA CS NME 18 | SHA CS NME 18 end | SHA CCG NME 18 | SHA CCG NME 18 end | SHA DC NME 18 | SHA DC NME 18 end | SHA AQP NME 18 | SHA AQP NME 18 end | SHA HWB NME 18 | SHA HWB NME 18 end | SHA PHT LAs NME 18 | SHA PHT LAs NME 18 end | SHA PHT PHE NME 18 | SHA PHT PHE NME 18 end | PCT CS NME 18 | PCT CS NME 18 end | PCT CCG NME 18 | PCT CCG NME 18 end | PCT DC NME 18 | PCT DC NME 18 end | PCT AQP NME 18 | PCT AQP NME 18 end | PCT HWB NME 18 | PCT HWB NME 18 end | PCT PHT LAs NME 18 | PCT PHT LAs NME 18 end | PCT PHT PHE NME 18 | PCT PHT PHE NME 18 end | QIPP LM 1.16 | QIPP LM 1.16 end | QIPP LM 2.16 | QIPP LM 2.16 end | QIPP LM 3.16 | QIPP LM 3.16 end | QIPP LM 4.16 | QIPP LM 4.16 end | QIPP LM 5.16 | QIPP LM 5.16 end | QIPP LM 6.16 | QIPP LM 6.16 end | QIPP LM 7.16 | QIPP LM 7.16 end | QIPP LM 8.16 | QIPP LM 8.16 end | QIPP LM 9.16 | QIPP LM 9.16 end | FTs NME 18 | FTs NME 18 end | 2013-06-30 |  |  |  |  | Clinical support rationalisation |  |  |  | Arden |  | 18
SHA CS NME 19 | SHA CS NME 19 end | SHA CCG NME 19 | SHA CCG NME 19 end | SHA DC NME 19 | SHA DC NME 19 end | SHA AQP NME 19 | SHA AQP NME 19 end | SHA HWB NME 19 | SHA HWB NME 19 end | SHA PHT LAs NME 19 | SHA PHT LAs NME 19 end | SHA PHT PHE NME 19 | SHA PHT PHE NME 19 end | PCT CS NME 19 | PCT CS NME 19 end | PCT CCG NME 19 | PCT CCG NME 19 end | PCT DC NME 19 | PCT DC NME 19 end | PCT AQP NME 19 | PCT AQP NME 19 end | PCT HWB NME 19 | PCT HWB NME 19 end | PCT PHT LAs NME 19 | PCT PHT LAs NME 19 end | PCT PHT PHE NME 19 | PCT PHT PHE NME 19 end | QIPP LM 1.17 | QIPP LM 1.17 end | QIPP LM 2.17 | QIPP LM 2.17 end | QIPP LM 3.17 | QIPP LM 3.17 end | QIPP LM 4.17 | QIPP LM 4.17 end | QIPP LM 5.17 | QIPP LM 5.17 end | QIPP LM 6.17 | QIPP LM 6.17 end | QIPP LM 7.17 | QIPP LM 7.17 end | QIPP LM 8.17 | QIPP LM 8.17 end | QIPP LM 9.17 | QIPP LM 9.17 end | FTs NME 19 | FTs NME 19 end | 2013-07-31 |  |  |  |  | Diagnostics |  |  |  | Birmingham and Solihull |  | 19
SHA CS NME 20 | SHA CS NME 20 end | SHA CCG NME 20 | SHA CCG NME 20 end | SHA DC NME 20 | SHA DC NME 20 end | SHA AQP NME 20 | SHA AQP NME 20 end | SHA HWB NME 20 | SHA HWB NME 20 end | SHA PHT LAs NME 20 | SHA PHT LAs NME 20 end | SHA PHT PHE NME 20 | SHA PHT PHE NME 20 end | PCT CS NME 20 | PCT CS NME 20 end | PCT CCG NME 20 | PCT CCG NME 20 end | PCT DC NME 20 | PCT DC NME 20 end | PCT AQP NME 20 | PCT AQP NME 20 end | PCT HWB NME 20 | PCT HWB NME 20 end | PCT PHT LAs NME 20 | PCT PHT LAs NME 20 end | PCT PHT PHE NME 20 | PCT PHT PHE NME 20 end | QIPP LM 1.18 | QIPP LM 1.18 end | QIPP LM 2.18 | QIPP LM 2.18 end | QIPP LM 3.18 | QIPP LM 3.18 end | QIPP LM 4.18 | QIPP LM 4.18 end | QIPP LM 5.18 | QIPP LM 5.18 end | QIPP LM 6.18 | QIPP LM 6.18 end | QIPP LM 7.18 | QIPP LM 7.18 end | QIPP LM 8.18 | QIPP LM 8.18 end | QIPP LM 9.18 | QIPP LM 9.18 end | FTs NME 20 | FTs NME 20 end | 2013-08-31 |  |  |  |  | Direct access |  |  |  | Northamptonshire and Milton Keynes |  | 20
SHA CS NME 21 | SHA CS NME 21 end | SHA CCG NME 21 | SHA CCG NME 21 end | SHA DC NME 21 | SHA DC NME 21 end | SHA AQP NME 21 | SHA AQP NME 21 end | SHA HWB NME 21 | SHA HWB NME 21 end | SHA PHT LAs NME 21 | SHA PHT LAs NME 21 end | SHA PHT PHE NME 21 | SHA PHT PHE NME 21 end | PCT CS NME 21 | PCT CS NME 21 end | PCT CCG NME 21 | PCT CCG NME 21 end | PCT DC NME 21 | PCT DC NME 21 end | PCT AQP NME 21 | PCT AQP NME 21 end | PCT HWB NME 21 | PCT HWB NME 21 end | PCT PHT LAs NME 21 | PCT PHT LAs NME 21 end | PCT PHT PHE NME 21 | PCT PHT PHE NME 21 end | QIPP LM 1.19 | QIPP LM 1.19 end | QIPP LM 2.19 | QIPP LM 2.19 end | QIPP LM 3.19 | QIPP LM 3.19 end | QIPP LM 4.19 | QIPP LM 4.19 end | QIPP LM 5.19 | QIPP LM 5.19 end | QIPP LM 6.19 | QIPP LM 6.19 end | QIPP LM 7.19 | QIPP LM 7.19 end | QIPP LM 8.19 | QIPP LM 8.19 end | QIPP LM 9.19 | QIPP LM 9.19 end | FTs NME 21 | FTs NME 21 end | 2013-09-30 |  |  |  |  | Medicines use |  |  |  | Nottinghamshire |  | 21
SHA CS NME 22 | SHA CS NME 22 end | SHA CCG NME 22 | SHA CCG NME 22 end | SHA DC NME 22 | SHA DC NME 22 end | SHA AQP NME 22 | SHA AQP NME 22 end | SHA HWB NME 22 | SHA HWB NME 22 end | SHA PHT LAs NME 22 | SHA PHT LAs NME 22 end | SHA PHT PHE NME 22 | SHA PHT PHE NME 22 end | PCT CS NME 22 | PCT CS NME 22 end | PCT CCG NME 22 | PCT CCG NME 22 end | PCT DC NME 22 | PCT DC NME 22 end | PCT AQP NME 22 | PCT AQP NME 22 end | PCT HWB NME 22 | PCT HWB NME 22 end | PCT PHT LAs NME 22 | PCT PHT LAs NME 22 end | PCT PHT PHE NME 22 | PCT PHT PHE NME 22 end | QIPP LM 1.20 | QIPP LM 1.20 end | QIPP LM 2.20 | QIPP LM 2.20 end | QIPP LM 3.20 | QIPP LM 3.20 end | QIPP LM 4.20 | QIPP LM 4.20 end | QIPP LM 5.20 | QIPP LM 5.20 end | QIPP LM 6.20 | QIPP LM 6.20 end | QIPP LM 7.20 | QIPP LM 7.20 end | QIPP LM 8.20 | QIPP LM 8.20 end | QIPP LM 9.20 | QIPP LM 9.20 end | FTs NME 22 | FTs NME 22 end | 2013-10-31 |  |  |  |  | Prescribing |  |  |  | Leicestershire |  | 22
SHA CS NME 23 | SHA CS NME 23 end | SHA CCG NME 23 | SHA CCG NME 23 end | SHA DC NME 23 | SHA DC NME 23 end | SHA AQP NME 23 | SHA AQP NME 23 end | SHA HWB NME 23 | SHA HWB NME 23 end | SHA PHT LAs NME 23 | SHA PHT LAs NME 23 end | SHA PHT PHE NME 23 | SHA PHT PHE NME 23 end | PCT CS NME 23 | PCT CS NME 23 end | PCT CCG NME 23 | PCT CCG NME 23 end | PCT DC NME 23 | PCT DC NME 23 end | PCT AQP NME 23 | PCT AQP NME 23 end | PCT HWB NME 23 | PCT HWB NME 23 end | PCT PHT LAs NME 23 | PCT PHT LAs NME 23 end | PCT PHT PHE NME 23 | PCT PHT PHE NME 23 end | QIPP LM 1.21 | QIPP LM 1.21 end | QIPP LM 2.21 | QIPP LM 2.21 end | QIPP LM 3.21 | QIPP LM 3.21 end | QIPP LM 4.21 | QIPP LM 4.21 end | QIPP LM 5.21 | QIPP LM 5.21 end | QIPP LM 6.21 | QIPP LM 6.21 end | QIPP LM 7.21 | QIPP LM 7.21 end | QIPP LM 8.21 | QIPP LM 8.21 end | QIPP LM 9.21 | QIPP LM 9.21 end | FTs NME 23 | FTs NME 23 end | 2013-11-30 |  |  |  |  | Unidentified |  |  |  | Derbyshire |  | 23
SHA CS NME 24 | SHA CS NME 24 end | SHA CCG NME 24 | SHA CCG NME 24 end | SHA DC NME 24 | SHA DC NME 24 end | SHA AQP NME 24 | SHA AQP NME 24 end | SHA HWB NME 24 | SHA HWB NME 24 end | SHA PHT LAs NME 24 | SHA PHT LAs NME 24 end | SHA PHT PHE NME 24 | SHA PHT PHE NME 24 end | PCT CS NME 24 | PCT CS NME 24 end | PCT CCG NME 24 | PCT CCG NME 24 end | PCT DC NME 24 | PCT DC NME 24 end | PCT AQP NME 24 | PCT AQP NME 24 end | PCT HWB NME 24 | PCT HWB NME 24 end | PCT PHT LAs NME 24 | PCT PHT LAs NME 24 end | PCT PHT PHE NME 24 | PCT PHT PHE NME 24 end | QIPP LM 1.22 | QIPP LM 1.22 end | QIPP LM 2.22 | QIPP LM 2.22 end | QIPP LM 3.22 | QIPP LM 3.22 end | QIPP LM 4.22 | QIPP LM 4.22 end | QIPP LM 5.22 | QIPP LM 5.22 end | QIPP LM 6.22 | QIPP LM 6.22 end | QIPP LM 7.22 | QIPP LM 7.22 end | QIPP LM 8.22 | QIPP LM 8.22 end | QIPP LM 9.22 | QIPP LM 9.22 end | FTs NME 24 | FTs NME 24 end | 2013-12-31 | [8 empty] | Lincolnshire |  | 24
SHA CS NME 25 | SHA CS NME 25 end | SHA CCG NME 25 | SHA CCG NME 25 end | SHA DC NME 25 | SHA DC NME 25 end | SHA AQP NME 25 | SHA AQP NME 25 end | SHA HWB NME 25 | SHA HWB NME 25 end | SHA PHT LAs NME 25 | SHA PHT LAs NME 25 end | SHA PHT PHE NME 25 | SHA PHT PHE NME 25 end | PCT CS NME 25 | PCT CS NME 25 end | PCT CCG NME 25 | PCT CCG NME 25 end | PCT DC NME 25 | PCT DC NME 25 end | PCT AQP NME 25 | PCT AQP NME 25 end | PCT HWB NME 25 | PCT HWB NME 25 end | PCT PHT LAs NME 25 | PCT PHT LAs NME 25 end | PCT PHT PHE NME 25 | PCT PHT PHE NME 25 end | QIPP LM 1.23 | QIPP LM 1.23 end | QIPP LM 2.23 | QIPP LM 2.23 end | QIPP LM 3.23 | QIPP LM 3.23 end | QIPP LM 4.23 | QIPP LM 4.23 end | QIPP LM 5.23 | QIPP LM 5.23 end | QIPP LM 6.23 | QIPP LM 6.23 end | QIPP LM 7.23 | QIPP LM 7.23 end | QIPP LM 8.23 | QIPP LM 8.23 end | QIPP LM 9.23 | QIPP LM 9.23 end | FTs NME 25 | FTs NME 25 end | 2014-01-31 | [8 empty] | North East Essex |  | 25
SHA CS LMS 1 | SHA CS LMS 1 end | SHA CCG LMS 1 | SHA CCG LMS 1 end | SHA DC LMS 1 | SHA DC LMS 1 end | SHA AQP LMS 1 | SHA AQP LMS 1 end | SHA HWB LMS 1 | SHA HWB LMS 1 end | SHA PHT LAs LMS 1 | SHA PHT LAs LMS 1 end | SHA PHT PHE LMS 1 | SHA PHT PHE LMS 1 end | PCT CS LMS 1 | PCT CS LMS 1 end | PCT CCG LMS 1 | PCT CCG LMS 1 end | PCT DC LMS 1 | PCT DC LMS 1 end | PCT AQP LMS 1 | PCT AQP LMS 1 end | PCT HWB LMS 1 | PCT HWB LMS 1 end | PCT PHT LAs LMS 1 | PCT PHT LAs LMS 1 end | PCT PHT PHE LMS 1 | PCT PHT PHE LMS 1 end | QIPP LM 1.24 | QIPP LM 1.24 end | QIPP LM 2.24 | QIPP LM 2.24 end | QIPP LM 3.24 | QIPP LM 3.24 end | QIPP LM 4.24 | QIPP LM 4.24 end | QIPP LM 5.24 | QIPP LM 5.24 end | QIPP LM 6.24 | QIPP LM 6.24 end | QIPP LM 7.24 | QIPP LM 7.24 end | QIPP LM 8.24 | QIPP LM 8.24 end | QIPP LM 9.24 | QIPP LM 9.24 end | FTs LMS 1 | FTs LMS 1 end | 2014-02-28 | [8 empty] | South Essex |  | 26
SHA CS LMS 2 | SHA CS LMS 2 end | SHA CCG LMS 2 | SHA CCG LMS 2 end | SHA DC LMS 2 | SHA DC LMS 2 end | SHA AQP LMS 2 | SHA AQP LMS 2 end | SHA HWB LMS 2 | SHA HWB LMS 2 end | SHA PHT LAs LMS 2 | SHA PHT LAs LMS 2 end | SHA PHT PHE LMS 2 | SHA PHT PHE LMS 2 end | PCT CS LMS 2 | PCT CS LMS 2 end | PCT CCG LMS 2 | PCT CCG LMS 2 end | PCT DC LMS 2 | PCT DC LMS 2 end | PCT AQP LMS 2 | PCT AQP LMS 2 end | PCT HWB LMS 2 | PCT HWB LMS 2 end | PCT PHT LAs LMS 2 | PCT PHT LAs LMS 2 end | PCT PHT PHE LMS 2 | PCT PHT PHE LMS 2 end | QIPP LM 1.25 | QIPP LM 1.25 end | QIPP LM 2.25 | QIPP LM 2.25 end | QIPP LM 3.25 | QIPP LM 3.25 end | QIPP LM 4.25 | QIPP LM 4.25 end | QIPP LM 5.25 | QIPP LM 5.25 end | QIPP LM 6.25 | QIPP LM 6.25 end | QIPP LM 7.25 | QIPP LM 7.25 end | QIPP LM 8.25 | QIPP LM 8.25 end | QIPP LM 9.25 | QIPP LM 9.25 end | FTs LMS 2 | FTs LMS 2 end | 2014-03-31 | [8 empty] | Bedfordshire and Luton |  | 27
SHA CS LMS 3 | SHA CS LMS 3 end | SHA CCG LMS 3 | SHA CCG LMS 3 end | SHA DC LMS 3 | SHA DC LMS 3 end | SHA AQP LMS 3 | SHA AQP LMS 3 end | SHA HWB LMS 3 | SHA HWB LMS 3 end | SHA PHT LAs LMS 3 | SHA PHT LAs LMS 3 end | SHA PHT PHE LMS 3 | SHA PHT PHE LMS 3 end | PCT CS LMS 3 | PCT CS LMS 3 end | PCT CCG LMS 3 | PCT CCG LMS 3 end | PCT DC LMS 3 | PCT DC LMS 3 end | PCT AQP LMS 3 | PCT AQP LMS 3 end | PCT HWB LMS 3 | PCT HWB LMS 3 end | PCT PHT LAs LMS 3 | PCT PHT LAs LMS 3 end | PCT PHT PHE LMS 3 | PCT PHT PHE LMS 3 end | QIPP LM 1.26 | QIPP LM 1.26 end | QIPP LM 2.26 | QIPP LM 2.26 end | QIPP LM 3.26 | QIPP LM 3.26 end | QIPP LM 4.26 | QIPP LM 4.26 end | QIPP LM 5.26 | QIPP LM 5.26 end | QIPP LM 6.26 | QIPP LM 6.26 end | QIPP LM 7.26 | QIPP LM 7.26 end | QIPP LM 8.26 | QIPP LM 8.26 end | QIPP LM 9.26 | QIPP LM 9.26 end | FTs LMS 3 | FTs LMS 3 end | 2014-04-30 | [8 empty] | Cambridgeshire & Peterborough |  | 28
SHA CS LMS 4 | SHA CS LMS 4 end | SHA CCG LMS 4 | SHA CCG LMS 4 end | SHA DC LMS 4 | SHA DC LMS 4 end | SHA AQP LMS 4 | SHA AQP LMS 4 end | SHA HWB LMS 4 | SHA HWB LMS 4 end | SHA PHT LAs LMS 4 | SHA PHT LAs LMS 4 end | SHA PHT PHE LMS 4 | SHA PHT PHE LMS 4 end | PCT CS LMS 4 | PCT CS LMS 4 end | PCT CCG LMS 4 | PCT CCG LMS 4 end | PCT DC LMS 4 | PCT DC LMS 4 end | PCT AQP LMS 4 | PCT AQP LMS 4 end | PCT HWB LMS 4 | PCT HWB LMS 4 end | PCT PHT LAs LMS 4 | PCT PHT LAs LMS 4 end | PCT PHT PHE LMS 4 | PCT PHT PHE LMS 4 end | QIPP LM 1.27 | QIPP LM 1.27 end | QIPP LM 2.27 | QIPP LM 2.27 end | QIPP LM 3.27 | QIPP LM 3.27 end | QIPP LM 4.27 | QIPP LM 4.27 end | QIPP LM 5.27 | QIPP LM 5.27 end | QIPP LM 6.27 | QIPP LM 6.27 end | QIPP LM 7.27 | QIPP LM 7.27 end | QIPP LM 8.27 | QIPP LM 8.27 end | QIPP LM 9.27 | QIPP LM 9.27 end | FTs LMS 4 | FTs LMS 4 end | 2014-05-31 | [8 empty] | Hertfordshire |  | 29
SHA CS LMS 5 | SHA CS LMS 5 end | SHA CCG LMS 5 | SHA CCG LMS 5 end | SHA DC LMS 5 | SHA DC LMS 5 end | SHA AQP LMS 5 | SHA AQP LMS 5 end | SHA HWB LMS 5 | SHA HWB LMS 5 end | SHA PHT LAs LMS 5 | SHA PHT LAs LMS 5 end | SHA PHT PHE LMS 5 | SHA PHT PHE LMS 5 end | PCT CS LMS 5 | PCT CS LMS 5 end | PCT CCG LMS 5 | PCT CCG LMS 5 end | PCT DC LMS 5 | PCT DC LMS 5 end | PCT AQP LMS 5 | PCT AQP LMS 5 end | PCT HWB LMS 5 | PCT HWB LMS 5 end | PCT PHT LAs LMS 5 | PCT PHT LAs LMS 5 end | PCT PHT PHE LMS 5 | PCT PHT PHE LMS 5 end | QIPP LM 1.28 | QIPP LM 1.28 end | QIPP LM 2.28 | QIPP LM 2.28 end | QIPP LM 3.28 | QIPP LM 3.28 end | QIPP LM 4.28 | QIPP LM 4.28 end | QIPP LM 5.28 | QIPP LM 5.28 end | QIPP LM 6.28 | QIPP LM 6.28 end | QIPP LM 7.28 | QIPP LM 7.28 end | QIPP LM 8.28 | QIPP LM 8.28 end | QIPP LM 9.28 | QIPP LM 9.28 end | FTs LMS 5 | FTs LMS 5 end | 2014-06-30 | [8 empty] | Suffolk |  | 30
SHA CS LMS 6 | SHA CS LMS 6 end | SHA CCG LMS 6 | SHA CCG LMS 6 end | SHA DC LMS 6 | SHA DC LMS 6 end | SHA AQP LMS 6 | SHA AQP LMS 6 end | SHA HWB LMS 6 | SHA HWB LMS 6 end | SHA PHT LAs LMS 6 | SHA PHT LAs LMS 6 end | SHA PHT PHE LMS 6 | SHA PHT PHE LMS 6 end | PCT CS LMS 6 | PCT CS LMS 6 end | PCT CCG LMS 6 | PCT CCG LMS 6 end | PCT DC LMS 6 | PCT DC LMS 6 end | PCT AQP LMS 6 | PCT AQP LMS 6 end | PCT HWB LMS 6 | PCT HWB LMS 6 end | PCT PHT LAs LMS 6 | PCT PHT LAs LMS 6 end | PCT PHT PHE LMS 6 | PCT PHT PHE LMS 6 end | QIPP LM 1.29 | QIPP LM 1.29 end | QIPP LM 2.29 | QIPP LM 2.29 end | QIPP LM 3.29 | QIPP LM 3.29 end | QIPP LM 4.29 | QIPP LM 4.29 end | QIPP LM 5.29 | QIPP LM 5.29 end | QIPP LM 6.29 | QIPP LM 6.29 end | QIPP LM 7.29 | QIPP LM 7.29 end | QIPP LM 8.29 | QIPP LM 8.29 end | QIPP LM 9.29 | QIPP LM 9.29 end | FTs LMS 6 | FTs LMS 6 end | 2014-07-31 | [8 empty] | Norfolk, Greater Yarmouth & Waveney |  | 31
SHA CS LMS 7 | SHA CS LMS 7 end | SHA CCG LMS 7 | SHA CCG LMS 7 end | SHA DC LMS 7 | SHA DC LMS 7 end | SHA AQP LMS 7 | SHA AQP LMS 7 end | SHA HWB LMS 7 | SHA HWB LMS 7 end | SHA PHT LAs LMS 7 | SHA PHT LAs LMS 7 end | SHA PHT PHE LMS 7 | SHA PHT PHE LMS 7 end | PCT CS LMS 7 | PCT CS LMS 7 end | PCT CCG LMS 7 | PCT CCG LMS 7 end | PCT DC LMS 7 | PCT DC LMS 7 end | PCT AQP LMS 7 | PCT AQP LMS 7 end | PCT HWB LMS 7 | PCT HWB LMS 7 end | PCT PHT LAs LMS 7 | PCT PHT LAs LMS 7 end | PCT PHT PHE LMS 7 | PCT PHT PHE LMS 7 end | QIPP LM 1.30 | QIPP LM 1.30 end | QIPP LM 2.30 | QIPP LM 2.30 end | QIPP LM 3.30 | QIPP LM 3.30 end | QIPP LM 4.30 | QIPP LM 4.30 end | QIPP LM 5.30 | QIPP LM 5.30 end | QIPP LM 6.30 | QIPP LM 6.30 end | QIPP LM 7.30 | QIPP LM 7.30 end | QIPP LM 8.30 | QIPP LM 8.30 end | QIPP LM 9.30 | QIPP LM 9.30 end | FTs LMS 7 | FTs LMS 7 end | 2014-08-31 | [8 empty] | Inner North East London |  | 32
SHA CS LMS 8 | SHA CS LMS 8 end | SHA CCG LMS 8 | SHA CCG LMS 8 end | SHA DC LMS 8 | SHA DC LMS 8 end | SHA AQP LMS 8 | SHA AQP LMS 8 end | SHA HWB LMS 8 | SHA HWB LMS 8 end | SHA PHT LAs LMS 8 | SHA PHT LAs LMS 8 end | SHA PHT PHE LMS 8 | SHA PHT PHE LMS 8 end | PCT CS LMS 8 | PCT CS LMS 8 end | PCT CCG LMS 8 | PCT CCG LMS 8 end | PCT DC LMS 8 | PCT DC LMS 8 end | PCT AQP LMS 8 | PCT AQP LMS 8 end | PCT HWB LMS 8 | PCT HWB LMS 8 end | PCT PHT LAs LMS 8 | PCT PHT LAs LMS 8 end | PCT PHT PHE LMS 8 | PCT PHT PHE LMS 8 end | QIPP LM 1.31 | QIPP LM 1.31 end | QIPP LM 2.31 | QIPP LM 2.31 end | QIPP LM 3.31 | QIPP LM 3.31 end | QIPP LM 4.31 | QIPP LM 4.31 end | QIPP LM 5.31 | QIPP LM 5.31 end | QIPP LM 6.31 | QIPP LM 6.31 end | QIPP LM 7.31 | QIPP LM 7.31 end | QIPP LM 8.31 | QIPP LM 8.31 end | QIPP LM 9.31 | QIPP LM 9.31 end | FTs LMS 8 | FTs LMS 8 end | 2014-09-30 | [8 empty] | Outer North East London |  | 33
SHA CS LMS 9 | SHA CS LMS 9 end | SHA CCG LMS 9 | SHA CCG LMS 9 end | SHA DC LMS 9 | SHA DC LMS 9 end | SHA AQP LMS 9 | SHA AQP LMS 9 end | SHA HWB LMS 9 | SHA HWB LMS 9 end | SHA PHT LAs LMS 9 | SHA PHT LAs LMS 9 end | SHA PHT PHE LMS 9 | SHA PHT PHE LMS 9 end | PCT CS LMS 9 | PCT CS LMS 9 end | PCT CCG LMS 9 | PCT CCG LMS 9 end | PCT DC LMS 9 | PCT DC LMS 9 end | PCT AQP LMS 9 | PCT AQP LMS 9 end | PCT HWB LMS 9 | PCT HWB LMS 9 end | PCT PHT LAs LMS 9 | PCT PHT LAs LMS 9 end | PCT PHT PHE LMS 9 | PCT PHT PHE LMS 9 end | QIPP LM 1.32 | QIPP LM 1.32 end | QIPP LM 2.32 | QIPP LM 2.32 end | QIPP LM 3.32 | QIPP LM 3.32 end | QIPP LM 4.32 | QIPP LM 4.32 end | QIPP LM 5.32 | QIPP LM 5.32 end | QIPP LM 6.32 | QIPP LM 6.32 end | QIPP LM 7.32 | QIPP LM 7.32 end | QIPP LM 8.32 | QIPP LM 8.32 end | QIPP LM 9.32 | QIPP LM 9.32 end | FTs LMS 9 | FTs LMS 9 end | 2014-10-31 | [8 empty] | North Central London |  | 34
SHA CS LMS 10 | SHA CS LMS 10 end | SHA CCG LMS 10 | SHA CCG LMS 10 end | SHA DC LMS 10 | SHA DC LMS 10 end | SHA AQP LMS 10 | SHA AQP LMS 10 end | SHA HWB LMS 10 | SHA HWB LMS 10 end | SHA PHT LAs LMS 10 | SHA PHT LAs LMS 10 end | SHA PHT PHE LMS 10 | SHA PHT PHE LMS 10 end | PCT CS LMS 10 | PCT CS LMS 10 end | PCT CCG LMS 10 | PCT CCG LMS 10 end | PCT DC LMS 10 | PCT DC LMS 10 end | PCT AQP LMS 10 | PCT AQP LMS 10 end | PCT HWB LMS 10 | PCT HWB LMS 10 end | PCT PHT LAs LMS 10 | PCT PHT LAs LMS 10 end | PCT PHT PHE LMS 10 | PCT PHT PHE LMS 10 end | QIPP LM 1.33 | QIPP LM 1.33 end | QIPP LM 2.33 | QIPP LM 2.33 end | QIPP LM 3.33 | QIPP LM 3.33 end | QIPP LM 4.33 | QIPP LM 4.33 end | QIPP LM 5.33 | QIPP LM 5.33 end | QIPP LM 6.33 | QIPP LM 6.33 end | QIPP LM 7.33 | QIPP LM 7.33 end | QIPP LM 8.33 | QIPP LM 8.33 end | QIPP LM 9.33 | QIPP LM 9.33 end | FTs LMS 10 | FTs LMS 10 end | 2014-11-30 | [8 empty] | South East London |  | 35
SHA CS LMS 11 | SHA CS LMS 11 end | SHA CCG LMS 11 | SHA CCG LMS 11 end | SHA DC LMS 11 | SHA DC LMS 11 end | SHA AQP LMS 11 | SHA AQP LMS 11 end | SHA HWB LMS 11 | SHA HWB LMS 11 end | SHA PHT LAs LMS 11 | SHA PHT LAs LMS 11 end | SHA PHT PHE LMS 11 | SHA PHT PHE LMS 11 end | PCT CS LMS 11 | PCT CS LMS 11 end | PCT CCG LMS 11 | PCT CCG LMS 11 end | PCT DC LMS 11 | PCT DC LMS 11 end | PCT AQP LMS 11 | PCT AQP LMS 11 end | PCT HWB LMS 11 | PCT HWB LMS 11 end | PCT PHT LAs LMS 11 | PCT PHT LAs LMS 11 end | PCT PHT PHE LMS 11 | PCT PHT PHE LMS 11 end | QIPP LM 1.34 | QIPP LM 1.34 end | QIPP LM 2.34 | QIPP LM 2.34 end | QIPP LM 3.34 | QIPP LM 3.34 end | QIPP LM 4.34 | QIPP LM 4.34 end | QIPP LM 5.34 | QIPP LM 5.34 end | QIPP LM 6.34 | QIPP LM 6.34 end | QIPP LM 7.34 | QIPP LM 7.34 end | QIPP LM 8.34 | QIPP LM 8.34 end | QIPP LM 9.34 | QIPP LM 9.34 end | FTs LMS 11 | FTs LMS 11 end | 2014-12-31 | [8 empty] | South West London |  | 36
SHA CS LMS 12 | SHA CS LMS 12 end | SHA CCG LMS 12 | SHA CCG LMS 12 end | SHA DC LMS 12 | SHA DC LMS 12 end | SHA AQP LMS 12 | SHA AQP LMS 12 end | SHA HWB LMS 12 | SHA HWB LMS 12 end | SHA PHT LAs LMS 12 | SHA PHT LAs LMS 12 end | SHA PHT PHE LMS 12 | SHA PHT PHE LMS 12 end | PCT CS LMS 12 | PCT CS LMS 12 end | PCT CCG LMS 12 | PCT CCG LMS 12 end | PCT DC LMS 12 | PCT DC LMS 12 end | PCT AQP LMS 12 | PCT AQP LMS 12 end | PCT HWB LMS 12 | PCT HWB LMS 12 end | PCT PHT LAs LMS 12 | PCT PHT LAs LMS 12 end | PCT PHT PHE LMS 12 | PCT PHT PHE LMS 12 end | QIPP LM 1.35 | QIPP LM 1.35 end | QIPP LM 2.35 | QIPP LM 2.35 end | QIPP LM 3.35 | QIPP LM 3.35 end | QIPP LM 4.35 | QIPP LM 4.35 end | QIPP LM 5.35 | QIPP LM 5.35 end | QIPP LM 6.35 | QIPP LM 6.35 end | QIPP LM 7.35 | QIPP LM 7.35 end | QIPP LM 8.35 | QIPP LM 8.35 end | QIPP LM 9.35 | QIPP LM 9.35 end | FTs LMS 12 | FTs LMS 12 end | 2015-01-31 | [8 empty] | North West London |  | 37
SHA CS LMS 13 | SHA CS LMS 13 end | SHA CCG LMS 13 | SHA CCG LMS 13 end | SHA DC LMS 13 | SHA DC LMS 13 end | SHA AQP LMS 13 | SHA AQP LMS 13 end | SHA HWB LMS 13 | SHA HWB LMS 13 end | SHA PHT LAs LMS 13 | SHA PHT LAs LMS 13 end | SHA PHT PHE LMS 13 | SHA PHT PHE LMS 13 end | PCT CS LMS 13 | PCT CS LMS 13 end | PCT CCG LMS 13 | PCT CCG LMS 13 end | PCT DC LMS 13 | PCT DC LMS 13 end | PCT AQP LMS 13 | PCT AQP LMS 13 end | PCT HWB LMS 13 | PCT HWB LMS 13 end | PCT PHT LAs LMS 13 | PCT PHT LAs LMS 13 end | PCT PHT PHE LMS 13 | PCT PHT PHE LMS 13 end | QIPP LM 1.36 | QIPP LM 1.36 end | QIPP LM 2.36 | QIPP LM 2.36 end | QIPP LM 3.36 | QIPP LM 3.36 end | QIPP LM 4.36 | QIPP LM 4.36 end | QIPP LM 5.36 | QIPP LM 5.36 end | QIPP LM 6.36 | QIPP LM 6.36 end | QIPP LM 7.36 | QIPP LM 7.36 end | QIPP LM 8.36 | QIPP LM 8.36 end | QIPP LM 9.36 | QIPP LM 9.36 end | FTs LMS 13 | FTs LMS 13 end | 2015-02-28 | [8 empty] | Cumbria |  | 38
SHA CS LMS 14 | SHA CS LMS 14 end | SHA CCG LMS 14 | SHA CCG LMS 14 end | SHA DC LMS 14 | SHA DC LMS 14 end | SHA AQP LMS 14 | SHA AQP LMS 14 end | SHA HWB LMS 14 | SHA HWB LMS 14 end | SHA PHT LAs LMS 14 | SHA PHT LAs LMS 14 end | SHA PHT PHE LMS 14 | SHA PHT PHE LMS 14 end | PCT CS LMS 14 | PCT CS LMS 14 end | PCT CCG LMS 14 | PCT CCG LMS 14 end | PCT DC LMS 14 | PCT DC LMS 14 end | PCT AQP LMS 14 | PCT AQP LMS 14 end | PCT HWB LMS 14 | PCT HWB LMS 14 end | PCT PHT LAs LMS 14 | PCT PHT LAs LMS 14 end | PCT PHT PHE LMS 14 | PCT PHT PHE LMS 14 end | QIPP LM 1.37 | QIPP LM 1.37 end | QIPP LM 2.37 | QIPP LM 2.37 end | QIPP LM 3.37 | QIPP LM 3.37 end | QIPP LM 4.37 | QIPP LM 4.37 end | QIPP LM 5.37 | QIPP LM 5.37 end | QIPP LM 6.37 | QIPP LM 6.37 end | QIPP LM 7.37 | QIPP LM 7.37 end | QIPP LM 8.37 | QIPP LM 8.37 end | QIPP LM 9.37 | QIPP LM 9.37 end | FTs LMS 14 | FTs LMS 14 end | 2015-03-31 | [8 empty] | Lancashire |  | 39
SHA CS LMS 15 | SHA CS LMS 15 end | SHA CCG LMS 15 | SHA CCG LMS 15 end | SHA DC LMS 15 | SHA DC LMS 15 end | SHA AQP LMS 15 | SHA AQP LMS 15 end | SHA HWB LMS 15 | SHA HWB LMS 15 end | SHA PHT LAs LMS 15 | SHA PHT LAs LMS 15 end | SHA PHT PHE LMS 15 | SHA PHT PHE LMS 15 end | PCT CS LMS 15 | PCT CS LMS 15 end | PCT CCG LMS 15 | PCT CCG LMS 15 end | PCT DC LMS 15 | PCT DC LMS 15 end | PCT AQP LMS 15 | PCT AQP LMS 15 end | PCT HWB LMS 15 | PCT HWB LMS 15 end | PCT PHT LAs LMS 15 | PCT PHT LAs LMS 15 end | PCT PHT PHE LMS 15 | PCT PHT PHE LMS 15 end | QIPP LM 1.38 | QIPP LM 1.38 end | QIPP LM 2.38 | QIPP LM 2.38 end | QIPP LM 3.38 | QIPP LM 3.38 end | QIPP LM 4.38 | QIPP LM 4.38 end | QIPP LM 5.38 | QIPP LM 5.38 end | QIPP LM 6.38 | QIPP LM 6.38 end | QIPP LM 7.38 | QIPP LM 7.38 end | QIPP LM 8.38 | QIPP LM 8.38 end | QIPP LM 9.38 | QIPP LM 9.38 end | FTs LMS 15 | FTs LMS 15 end | 2015-04-30 | [8 empty] | Merseyside |  | 40
SHA CS LMS 16 | SHA CS LMS 16 end | SHA CCG LMS 16 | SHA CCG LMS 16 end | SHA DC LMS 16 | SHA DC LMS 16 end | SHA AQP LMS 16 | SHA AQP LMS 16 end | SHA HWB LMS 16 | SHA HWB LMS 16 end | SHA PHT LAs LMS 16 | SHA PHT LAs LMS 16 end | SHA PHT PHE LMS 16 | SHA PHT PHE LMS 16 end | PCT CS LMS 16 | PCT CS LMS 16 end | PCT CCG LMS 16 | PCT CCG LMS 16 end | PCT DC LMS 16 | PCT DC LMS 16 end | PCT AQP LMS 16 | PCT AQP LMS 16 end | PCT HWB LMS 16 | PCT HWB LMS 16 end | PCT PHT LAs LMS 16 | PCT PHT LAs LMS 16 end | PCT PHT PHE LMS 16 | PCT PHT PHE LMS 16 end | QIPP LM 1.39 | QIPP LM 1.39 end | QIPP LM 2.39 | QIPP LM 2.39 end | QIPP LM 3.39 | QIPP LM 3.39 end | QIPP LM 4.39 | QIPP LM 4.39 end | QIPP LM 5.39 | QIPP LM 5.39 end | QIPP LM 6.39 | QIPP LM 6.39 end | QIPP LM 7.39 | QIPP LM 7.39 end | QIPP LM 8.39 | QIPP LM 8.39 end | QIPP LM 9.39 | QIPP LM 9.39 end | FTs LMS 16 | FTs LMS 16 end | 2015-05-31 | [8 empty] | Greater Manchester |  | 41
SHA CS LMS 17 | SHA CS LMS 17 end | SHA CCG LMS 17 | SHA CCG LMS 17 end | SHA DC LMS 17 | SHA DC LMS 17 end | SHA AQP LMS 17 | SHA AQP LMS 17 end | SHA HWB LMS 17 | SHA HWB LMS 17 end | SHA PHT LAs LMS 17 | SHA PHT LAs LMS 17 end | SHA PHT PHE LMS 17 | SHA PHT PHE LMS 17 end | PCT CS LMS 17 | PCT CS LMS 17 end | PCT CCG LMS 17 | PCT CCG LMS 17 end | PCT DC LMS 17 | PCT DC LMS 17 end | PCT AQP LMS 17 | PCT AQP LMS 17 end | PCT HWB LMS 17 | PCT HWB LMS 17 end | PCT PHT LAs LMS 17 | PCT PHT LAs LMS 17 end | PCT PHT PHE LMS 17 | PCT PHT PHE LMS 17 end | QIPP LM 1.40 | QIPP LM 1.40 end | QIPP LM 2.40 | QIPP LM 2.40 end | QIPP LM 3.40 | QIPP LM 3.40 end | QIPP LM 4.40 | QIPP LM 4.40 end | QIPP LM 5.40 | QIPP LM 5.40 end | QIPP LM 6.40 | QIPP LM 6.40 end | QIPP LM 7.40 | QIPP LM 7.40 end | QIPP LM 8.40 | QIPP LM 8.40 end | QIPP LM 9.40 | QIPP LM 9.40 end | FTs LMS 17 | FTs LMS 17 end | 2015-06-30 | [8 empty] | Cheshire |  | 42
SHA CS LMS 18 | SHA CS LMS 18 end | SHA CCG LMS 18 | SHA CCG LMS 18 end | SHA DC LMS 18 | SHA DC LMS 18 end | SHA AQP LMS 18 | SHA AQP LMS 18 end | SHA HWB LMS 18 | SHA HWB LMS 18 end | SHA PHT LAs LMS 18 | SHA PHT LAs LMS 18 end | SHA PHT PHE LMS 18 | SHA PHT PHE LMS 18 end | PCT CS LMS 18 | PCT CS LMS 18 end | PCT CCG LMS 18 | PCT CCG LMS 18 end | PCT DC LMS 18 | PCT DC LMS 18 end | PCT AQP LMS 18 | PCT AQP LMS 18 end | PCT HWB LMS 18 | PCT HWB LMS 18 end | PCT PHT LAs LMS 18 | PCT PHT LAs LMS 18 end | PCT PHT PHE LMS 18 | PCT PHT PHE LMS 18 end | QIPP LM 1.41 | QIPP LM 1.41 end | QIPP LM 2.41 | QIPP LM 2.41 end | QIPP LM 3.41 | QIPP LM 3.41 end | QIPP LM 4.41 | QIPP LM 4.41 end | QIPP LM 5.41 | QIPP LM 5.41 end | QIPP LM 6.41 | QIPP LM 6.41 end | QIPP LM 7.41 | QIPP LM 7.41 end | QIPP LM 8.41 | QIPP LM 8.41 end | QIPP LM 9.41 | QIPP LM 9.41 end | FTs LMS 18 | FTs LMS 18 end | 2015-07-31 | [8 empty] | County Durham & Darlington |  | 43
SHA CS LMS 19 | SHA CS LMS 19 end | SHA CCG LMS 19 | SHA CCG LMS 19 end | SHA DC LMS 19 | SHA DC LMS 19 end | SHA AQP LMS 19 | SHA AQP LMS 19 end | SHA HWB LMS 19 | SHA HWB LMS 19 end | SHA PHT LAs LMS 19 | SHA PHT LAs LMS 19 end | SHA PHT PHE LMS 19 | SHA PHT PHE LMS 19 end | PCT CS LMS 19 | PCT CS LMS 19 end | PCT CCG LMS 19 | PCT CCG LMS 19 end | PCT DC LMS 19 | PCT DC LMS 19 end | PCT AQP LMS 19 | PCT AQP LMS 19 end | PCT HWB LMS 19 | PCT HWB LMS 19 end | PCT PHT LAs LMS 19 | PCT PHT LAs LMS 19 end | PCT PHT PHE LMS 19 | PCT PHT PHE LMS 19 end | QIPP LM 1.42 | QIPP LM 1.42 end | QIPP LM 2.42 | QIPP LM 2.42 end | QIPP LM 3.42 | QIPP LM 3.42 end | QIPP LM 4.42 | QIPP LM 4.42 end | QIPP LM 5.42 | QIPP LM 5.42 end | QIPP LM 6.42 | QIPP LM 6.42 end | QIPP LM 7.42 | QIPP LM 7.42 end | QIPP LM 8.42 | QIPP LM 8.42 end | QIPP LM 9.42 | QIPP LM 9.42 end | FTs LMS 19 | FTs LMS 19 end | [9 empty] | North of Tyne |  | 44
SHA CS LMS 20 | SHA CS LMS 20 end | SHA CCG LMS 20 | SHA CCG LMS 20 end | SHA DC LMS 20 | SHA DC LMS 20 end | SHA AQP LMS 20 | SHA AQP LMS 20 end | SHA HWB LMS 20 | SHA HWB LMS 20 end | SHA PHT LAs LMS 20 | SHA PHT LAs LMS 20 end | SHA PHT PHE LMS 20 | SHA PHT PHE LMS 20 end | PCT CS LMS 20 | PCT CS LMS 20 end | PCT CCG LMS 20 | PCT CCG LMS 20 end | PCT DC LMS 20 | PCT DC LMS 20 end | PCT AQP LMS 20 | PCT AQP LMS 20 end | PCT HWB LMS 20 | PCT HWB LMS 20 end | PCT PHT LAs LMS 20 | PCT PHT LAs LMS 20 end | PCT PHT PHE LMS 20 | PCT PHT PHE LMS 20 end | QIPP LM 1.43 | QIPP LM 1.43 end | QIPP LM 2.43 | QIPP LM 2.43 end | QIPP LM 3.43 | QIPP LM 3.43 end | QIPP LM 4.43 | QIPP LM 4.43 end | QIPP LM 5.43 | QIPP LM 5.43 end | QIPP LM 6.43 | QIPP LM 6.43 end | QIPP LM 7.43 | QIPP LM 7.43 end | QIPP LM 8.43 | QIPP LM 8.43 end | QIPP LM 9.43 | QIPP LM 9.43 end | FTs LMS 20 | FTs LMS 20 end | [9 empty] | South of Tyne & Weir |  | 45
SHA CS LMS 21 | SHA CS LMS 21 end | SHA CCG LMS 21 | SHA CCG LMS 21 end | SHA DC LMS 21 | SHA DC LMS 21 end | SHA AQP LMS 21 | SHA AQP LMS 21 end | SHA HWB LMS 21 | SHA HWB LMS 21 end | SHA PHT LAs LMS 21 | SHA PHT LAs LMS 21 end | SHA PHT PHE LMS 21 | SHA PHT PHE LMS 21 end | PCT CS LMS 21 | PCT CS LMS 21 end | PCT CCG LMS 21 | PCT CCG LMS 21 end | PCT DC LMS 21 | PCT DC LMS 21 end | PCT AQP LMS 21 | PCT AQP LMS 21 end | PCT HWB LMS 21 | PCT HWB LMS 21 end | PCT PHT LAs LMS 21 | PCT PHT LAs LMS 21 end | PCT PHT PHE LMS 21 | PCT PHT PHE LMS 21 end | QIPP LM 1.44 | QIPP LM 1.44 end | QIPP LM 2.44 | QIPP LM 2.44 end | QIPP LM 3.44 | QIPP LM 3.44 end | QIPP LM 4.44 | QIPP LM 4.44 end | QIPP LM 5.44 | QIPP LM 5.44 end | QIPP LM 6.44 | QIPP LM 6.44 end | QIPP LM 7.44 | QIPP LM 7.44 end | QIPP LM 8.44 | QIPP LM 8.44 end | QIPP LM 9.44 | QIPP LM 9.44 end | FTs LMS 21 | FTs LMS 21 end | [9 empty] | Tees |  | 46
SHA CS LMS 22 | SHA CS LMS 22 end | SHA CCG LMS 22 | SHA CCG LMS 22 end | SHA DC LMS 22 | SHA DC LMS 22 end | SHA AQP LMS 22 | SHA AQP LMS 22 end | SHA HWB LMS 22 | SHA HWB LMS 22 end | SHA PHT LAs LMS 22 | SHA PHT LAs LMS 22 end | SHA PHT PHE LMS 22 | SHA PHT PHE LMS 22 end | PCT CS LMS 22 | PCT CS LMS 22 end | PCT CCG LMS 22 | PCT CCG LMS 22 end | PCT DC LMS 22 | PCT DC LMS 22 end | PCT AQP LMS 22 | PCT AQP LMS 22 end | PCT HWB LMS 22 | PCT HWB LMS 22 end | PCT PHT LAs LMS 22 | PCT PHT LAs LMS 22 end | PCT PHT PHE LMS 22 | PCT PHT PHE LMS 22 end | QIPP LM 1.45 | QIPP LM 1.45 end | QIPP LM 2.45 | QIPP LM 2.45 end | QIPP LM 3.45 | QIPP LM 3.45 end | QIPP LM 4.45 | QIPP LM 4.45 end | QIPP LM 5.45 | QIPP LM 5.45 end | QIPP LM 6.45 | QIPP LM 6.45 end | QIPP LM 7.45 | QIPP LM 7.45 end | QIPP LM 8.45 | QIPP LM 8.45 end | QIPP LM 9.45 | QIPP LM 9.45 end | FTs LMS 22 | FTs LMS 22 end | [9 empty] | South Yorkshire & Bassetlaw |  | 47
SHA CS LMS 23 | SHA CS LMS 23 end | SHA CCG LMS 23 | SHA CCG LMS 23 end | SHA DC LMS 23 | SHA DC LMS 23 end | SHA AQP LMS 23 | SHA AQP LMS 23 end | SHA HWB LMS 23 | SHA HWB LMS 23 end | SHA PHT LAs LMS 23 | SHA PHT LAs LMS 23 end | SHA PHT PHE LMS 23 | SHA PHT PHE LMS 23 end | PCT CS LMS 23 | PCT CS LMS 23 end | PCT CCG LMS 23 | PCT CCG LMS 23 end | PCT DC LMS 23 | PCT DC LMS 23 end | PCT AQP LMS 23 | PCT AQP LMS 23 end | PCT HWB LMS 23 | PCT HWB LMS 23 end | PCT PHT LAs LMS 23 | PCT PHT LAs LMS 23 end | PCT PHT PHE LMS 23 | PCT PHT PHE LMS 23 end | QIPP LM 1.46 | QIPP LM 1.46 end | QIPP LM 2.46 | QIPP LM 2.46 end | QIPP LM 3.46 | QIPP LM 3.46 end | QIPP LM 4.46 | QIPP LM 4.46 end | QIPP LM 5.46 | QIPP LM 5.46 end | QIPP LM 6.46 | QIPP LM 6.46 end | QIPP LM 7.46 | QIPP LM 7.46 end | QIPP LM 8.46 | QIPP LM 8.46 end | QIPP LM 9.46 | QIPP LM 9.46 end | FTs LMS 23 | FTs LMS 23 end | [9 empty] | Calderdale, Kirklees & Wakefield |  | 48
SHA CS LMS 24 | SHA CS LMS 24 end | SHA CCG LMS 24 | SHA CCG LMS 24 end | SHA DC LMS 24 | SHA DC LMS 24 end | SHA AQP LMS 24 | SHA AQP LMS 24 end | SHA HWB LMS 24 | SHA HWB LMS 24 end | SHA PHT LAs LMS 24 | SHA PHT LAs LMS 24 end | SHA PHT PHE LMS 24 | SHA PHT PHE LMS 24 end | PCT CS LMS 24 | PCT CS LMS 24 end | PCT CCG LMS 24 | PCT CCG LMS 24 end | PCT DC LMS 24 | PCT DC LMS 24 end | PCT AQP LMS 24 | PCT AQP LMS 24 end | PCT HWB LMS 24 | PCT HWB LMS 24 end | PCT PHT LAs LMS 24 | PCT PHT LAs LMS 24 end | PCT PHT PHE LMS 24 | PCT PHT PHE LMS 24 end | QIPP LM 1.47 | QIPP LM 1.47 end | QIPP LM 2.47 | QIPP LM 2.47 end | QIPP LM 3.47 | QIPP LM 3.47 end | QIPP LM 4.47 | QIPP LM 4.47 end | QIPP LM 5.47 | QIPP LM 5.47 end | QIPP LM 6.47 | QIPP LM 6.47 end | QIPP LM 7.47 | QIPP LM 7.47 end | QIPP LM 8.47 | QIPP LM 8.47 end | QIPP LM 9.47 | QIPP LM 9.47 end | FTs LMS 24 | FTs LMS 24 end | [9 empty] | The Humber |  | 49
SHA CS LMS 25 | SHA CS LMS 25 end | SHA CCG LMS 25 | SHA CCG LMS 25 end | SHA DC LMS 25 | SHA DC LMS 25 end | SHA AQP LMS 25 | SHA AQP LMS 25 end | SHA HWB LMS 25 | SHA HWB LMS 25 end | SHA PHT LAs LMS 25 | SHA PHT LAs LMS 25 end | SHA PHT PHE LMS 25 | SHA PHT PHE LMS 25 end | PCT CS LMS 25 | PCT CS LMS 25 end | PCT CCG LMS 25 | PCT CCG LMS 25 end | PCT DC LMS 25 | PCT DC LMS 25 end | PCT AQP LMS 25 | PCT AQP LMS 25 end | PCT HWB LMS 25 | PCT HWB LMS 25 end | PCT PHT LAs LMS 25 | PCT PHT LAs LMS 25 end | PCT PHT PHE LMS 25 | PCT PHT PHE LMS 25 end | QIPP LM 1.48 | QIPP LM 1.48 end | QIPP LM 2.48 | QIPP LM 2.48 end | QIPP LM 3.48 | QIPP LM 3.48 end | QIPP LM 4.48 | QIPP LM 4.48 end | QIPP LM 5.48 | QIPP LM 5.48 end | QIPP LM 6.48 | QIPP LM 6.48 end | QIPP LM 7.48 | QIPP LM 7.48 end | QIPP LM 8.48 | QIPP LM 8.48 end | QIPP LM 9.48 | QIPP LM 9.48 end | FTs LMS 25 | FTs LMS 25 end | [9 empty] | Leeds and Bradford |  | 50
SHA CS LMS 26 | SHA CS LMS 26 end | SHA CCG LMS 26 | SHA CCG LMS 26 end | SHA DC LMS 26 | SHA DC LMS 26 end | SHA AQP LMS 26 | SHA AQP LMS 26 end | SHA HWB LMS 26 | SHA HWB LMS 26 end | SHA PHT LAs LMS 26 | SHA PHT LAs LMS 26 end | SHA PHT PHE LMS 26 | SHA PHT PHE LMS 26 end | PCT CS LMS 26 | PCT CS LMS 26 end | PCT CCG LMS 26 | PCT CCG LMS 26 end | PCT DC LMS 26 | PCT DC LMS 26 end | PCT AQP LMS 26 | PCT AQP LMS 26 end | PCT HWB LMS 26 | PCT HWB LMS 26 end | PCT PHT LAs LMS 26 | PCT PHT LAs LMS 26 end | PCT PHT PHE LMS 26 | PCT PHT PHE LMS 26 end | QIPP LM 1.49 | QIPP LM 1.49 end | QIPP LM 2.49 | QIPP LM 2.49 end | QIPP LM 3.49 | QIPP LM 3.49 end | QIPP LM 4.49 | QIPP LM 4.49 end | QIPP LM 5.49 | QIPP LM 5.49 end | QIPP LM 6.49 | QIPP LM 6.49 end | QIPP LM 7.49 | QIPP LM 7.49 end | QIPP LM 8.49 | QIPP LM 8.49 end | QIPP LM 9.49 | QIPP LM 9.49 end | FTs LMS 26 | FTs LMS 26 end | [9 empty] | North Yorkshire & York
SHA CS LMS 27 | SHA CS LMS 27 end | SHA CCG LMS 27 | SHA CCG LMS 27 end | SHA DC LMS 27 | SHA DC LMS 27 end | SHA AQP LMS 27 | SHA AQP LMS 27 end | SHA HWB LMS 27 | SHA HWB LMS 27 end | SHA PHT LAs LMS 27 | SHA PHT LAs LMS 27 end | SHA PHT PHE LMS 27 | SHA PHT PHE LMS 27 end | PCT CS LMS 27 | PCT CS LMS 27 end | PCT CCG LMS 27 | PCT CCG LMS 27 end | PCT DC LMS 27 | PCT DC LMS 27 end | PCT AQP LMS 27 | PCT AQP LMS 27 end | PCT HWB LMS 27 | PCT HWB LMS 27 end | PCT PHT LAs LMS 27 | PCT PHT LAs LMS 27 end | PCT PHT PHE LMS 27 | PCT PHT PHE LMS 27 end | QIPP LM 1.50 | QIPP LM 1.50 end | QIPP LM 2.50 | QIPP LM 2.50 end | QIPP LM 3.50 | QIPP LM 3.50 end | QIPP LM 4.50 | QIPP LM 4.50 end | QIPP LM 5.50 | QIPP LM 5.50 end | QIPP LM 6.50 | QIPP LM 6.50 end | QIPP LM 7.50 | QIPP LM 7.50 end | QIPP LM 8.50 | QIPP LM 8.50 end | QIPP LM 9.50 | QIPP LM 9.50 end | FTs LMS 27 | FTs LMS 27 end
SHA CS LMS 28 | SHA CS LMS 28 end | SHA CCG LMS 28 | SHA CCG LMS 28 end | SHA DC LMS 28 | SHA DC LMS 28 end | SHA AQP LMS 28 | SHA AQP LMS 28 end | SHA HWB LMS 28 | SHA HWB LMS 28 end | SHA PHT LAs LMS 28 | SHA PHT LAs LMS 28 end | SHA PHT PHE LMS 28 | SHA PHT PHE LMS 28 end | PCT CS LMS 28 | PCT CS LMS 28 end | PCT CCG LMS 28 | PCT CCG LMS 28 end | PCT DC LMS 28 | PCT DC LMS 28 end | PCT AQP LMS 28 | PCT AQP LMS 28 end | PCT HWB LMS 28 | PCT HWB LMS 28 end | PCT PHT LAs LMS 28 | PCT PHT LAs LMS 28 end | PCT PHT PHE LMS 28 | PCT PHT PHE LMS 28 end | QIPP LM 1.51 | QIPP LM 1.51 end | QIPP LM 2.51 | QIPP LM 2.51 end | QIPP LM 3.51 | QIPP LM 3.51 end | QIPP LM 4.51 | QIPP LM 4.51 end | QIPP LM 5.51 | QIPP LM 5.51 end | QIPP LM 6.51 | QIPP LM 6.51 end | QIPP LM 7.51 | QIPP LM 7.51 end | QIPP LM 8.51 | QIPP LM 8.51 end | QIPP LM 9.51 | QIPP LM 9.51 end | FTs LMS 28 | FTs LMS 28 end
SHA CS LMS 29 | SHA CS LMS 29 end | SHA CCG LMS 29 | SHA CCG LMS 29 end | SHA DC LMS 29 | SHA DC LMS 29 end | SHA AQP LMS 29 | SHA AQP LMS 29 end | SHA HWB LMS 29 | SHA HWB LMS 29 end | SHA PHT LAs LMS 29 | SHA PHT LAs LMS 29 end | SHA PHT PHE LMS 29 | SHA PHT PHE LMS 29 end | PCT CS LMS 29 | PCT CS LMS 29 end | PCT CCG LMS 29 | PCT CCG LMS 29 end | PCT DC LMS 29 | PCT DC LMS 29 end | PCT AQP LMS 29 | PCT AQP LMS 29 end | PCT HWB LMS 29 | PCT HWB LMS 29 end | PCT PHT LAs LMS 29 | PCT PHT LAs LMS 29 end | PCT PHT PHE LMS 29 | PCT PHT PHE LMS 29 end | QIPP LM 1.52 | QIPP LM 1.52 end | QIPP LM 2.52 | QIPP LM 2.52 end | QIPP LM 3.52 | QIPP LM 3.52 end | QIPP LM 4.52 | QIPP LM 4.52 end | QIPP LM 5.52 | QIPP LM 5.52 end | QIPP LM 6.52 | QIPP LM 6.52 end | QIPP LM 7.52 | QIPP LM 7.52 end | QIPP LM 8.52 | QIPP LM 8.52 end | QIPP LM 9.52 | QIPP LM 9.52 end | FTs LMS 29 | FTs LMS 29 end
SHA CS LMS 30 | SHA CS LMS 30 end | SHA CCG LMS 30 | SHA CCG LMS 30 end | SHA DC LMS 30 | SHA DC LMS 30 end | SHA AQP LMS 30 | SHA AQP LMS 30 end | SHA HWB LMS 30 | SHA HWB LMS 30 end | SHA PHT LAs LMS 30 | SHA PHT LAs LMS 30 end | SHA PHT PHE LMS 30 | SHA PHT PHE LMS 30 end | PCT CS LMS 30 | PCT CS LMS 30 end | PCT CCG LMS 30 | PCT CCG LMS 30 end | PCT DC LMS 30 | PCT DC LMS 30 end | PCT AQP LMS 30 | PCT AQP LMS 30 end | PCT HWB LMS 30 | PCT HWB LMS 30 end | PCT PHT LAs LMS 30 | PCT PHT LAs LMS 30 end | PCT PHT PHE LMS 30 | PCT PHT PHE LMS 30 end | QIPP LM 1.53 | QIPP LM 1.53 end | QIPP LM 2.53 | QIPP LM 2.53 end | QIPP LM 3.53 | QIPP LM 3.53 end | QIPP LM 4.53 | QIPP LM 4.53 end | QIPP LM 5.53 | QIPP LM 5.53 end | QIPP LM 6.53 | QIPP LM 6.53 end | QIPP LM 7.53 | QIPP LM 7.53 end | QIPP LM 8.53 | QIPP LM 8.53 end | QIPP LM 9.53 | QIPP LM 9.53 end | FTs LMS 30 | FTs LMS 30 end