## Sheet1
WAVE 1 | Allocated up to (£m) | Lead Organistion | How much received so far? (£m) | Scheme Description |  | Next step in securing the money?
Buckinghamshire, Oxfordshire and Berkshire West | 5 | Various | 0.9 | Rapid assessment and treatment centre and observation unit at Stoke Mandeville Hospital | - | The trust is planning additional refurbishment work and improvements within A&E and urgent care pathway and will receive £4.2m to fund this work
Cumbria and North East | 105 | North Cumbria University Hospitals Trust | 8 | New cancer centre and equipment at Cumberland Infirmary in Carlisle, as well as significant refurbishment and rebuilding work at West Cumberland Hospital, and the development of eight integrated care hubs | - | Next business cases being prepared
Derbyshire | 20 | Royal Derby and Burton Hospitals FT | 0 | Expand the emergency department at Royal Derby Hospital, creating space for 37 more minor injury beds, 10 emergency bays and additional resus facilities. The money will also allow the hospital to co-locate mental health assessment, GP care and out of hours services, and create a new facility that collocates community services, outpatient clinics, testing and diagnostics, and specialist rehabilitation services together in one place. | - | No drawdown available until FBC submitted
Dorset | 100 | Royal Bournemouth and Poole Hospitals | 0 | Major consolidation of emergency and planned care services between Bournemouth and Poole hospitals. | - | Outline business case and full business case required
Greater Manchester | 50 | Various | 0 | Healthier Together reconfiguration | - | Business case with HMT
Greater Manchester | 30 | Salford Royal FT | 0 | Trauma centre | - | Business case with HMT
Hereford and Worcestershire | 30 | Worcestershire Acute Hospitals | 11 | Consolidate maternity services, emergency surgery, and children’s services at Worcestershire Royal Hospital. The plan is to withdrawn these services from Alexandra Hospital in Redditch, which will receive investment for elective care, endoscopy, children’s outpatients and theatre upgrades. | - | The FBC for the Acute Scheme (£30m) has yet to be approved by HMT, latest projections suggest December.
Lancashire and South Cumbria | 30 | East Lancashire Hospitals Trust and Lancashire Care FT | 12.7 | Modernise mental health facilities and expand accident and emergency facilities at the Royal Blackburn Hospital | -
Leicester, Leicestershire and Rutland | 50 | University Hospitals of Leicester NHS Trust & Leicestershire Partnership NHS Trust | 8.6 | CAMHS relocation to new 15 bed inpatient unit at Glenfield General Hospital to bring specialist mental health provision together with other services (LPT). Also to fund an expansion of intensive care (UHL) | - | ICU Project has an approved funding stream of £30.8m. The spend/drawdown is: 2018/19 - £8.6m; 2019/20 £21.6m; 2020/21 - £0.6m (the profile is matched to when we estimate the capital project will incur costs across the 3 years.) CAMHS Project has an approved funding stream of £8m. The spend/drawdown is: 2019/20 - £5.1m; 2020/21 - £2.9
Mid and South Essex | 15 | Various | 0 | Expand capacity for diagnostics and improve outpatient services | - | Case referred to Secretary of State for Health and Social Care
Milton Keynes, Bedfordshire and Luton | 5 | Bedford Hopsitals Trust | 1.5 | Primary care hub | -
Norfolk and Waveney | 5 | Norfolk & Suffolk NHS Foundation Trust | 5 | Mental health beds in west Norfolk | -
North East London | 0.5 | Various | 0 | Redesigning the urgent care centre at King George’s Hospital | - | Funding withheld pending future decision on King George's Hospital
Nottinghamshire | 6.3 | Various | 0 | Improve and expand access to primary, community and social care | - | Ongoing business case development
South Yorkshire and Bassetlaw | 10 | Various | 1 | Improve acute hopsital facilities | - | No response
Suffolk and North East Essex | 10 | Various | 0 | New primary care hub in North Clacton, and the relocation of a GP surgery in West Suffolk | - | We are closely following the due process and confident that funding will be allocated very soon for us to progress with our plans'
WAVE 2 | Allocated up to (£m) | Lead Organistion | How much received so far? (£m) | Scheme Description |  | Next step in securing the money?
Birmingham and Solihull | 1.1 | Birmingham Women’s and Children’s NHS Foundation Trust | 0 | Emergency Department scheme to increase emergency care capacity and improve patient experience. | - | Discontinued application as scheme no longer met the original criteria
Buckinghamshire, Oxfordshire and Berkshire West | 8.8 | NHS Chiltern CCG | 0 | The Chiltern and Aylesbury Vale Primary Care Hub scheme to establish an integrated service model to allow the expansion of community teams and care provision outside of traditional hospital settings. | - | The CCG has been working up 4 main schemes to support this investment and expects to produce Full Business Cases by the end of December 2019,
Coventry and Warwickshire | 9.4 | South Warwickshire NHS Foundation Trust (SWFT) | 0 | The South Warwickshire Out of Hospital Care scheme to provide an integrated information system to improve collaboration between providers across the area. | - | To date this funding has not been released so we are continuing to work with the Department of Health to finally secure this money. As an interim measure the Trust has had to use alternative resources to ensure we continue to deliver maximum efficiencies across our out of hospital services. A full business case was submitted to the Department of Health. The Trust is now responding to the latest feedback on this and submitting an updated business case.
Derbyshire | 19.1 | Chesterfield Royal NHS Foundation Trust | 0 | The Chesterfield Urgent Care scheme to upgrade the emergency care department of Chesterfield Royal NHS Foundation Trust to provide a modern urgent care facility to deal with changing patient needs. | - | No drawdown available until FBC submitted
Frimley Health | 28.4 | Frimley Health NHS Foundation Trust | 0 | The Frimley Out of Hospital Integrated Care Hubs scheme to provide integrated hubs to provide better treatment to patients more quickly out of hospital. | - | Work is going on locally on preparing our business cases. Once these business cases have been submitted and approved, capital funding will be received.
Frimley Health | 3 | NHS East Berkshire CCG | 0 | The Bracknell Forest Heathlands scheme to build a new home for nursing and elderly mentally infirm care to improve services for local patients in the community. | - | Work is ongoing locally on preparing our business case. Once the business case has been submitted and approved, capital funding will be transferred. In the specific case of Heathlands, as this is a jointly funded project we are also working with Bracknell Forest Council on completing the Business case in relation to their investment. We are working towards draw down of the ICS funding within financial year 2019/20.
Mid and South Essex | 118 | MSB Hospital Group | 0 | The Mid and South Essex Transforming Health and Care scheme to transform acute and out of hospital services in the local area to improve care delivery. | - | Case referred to Secretary of State for Health and Social Care
South West London | 7.1 | South West London and St George’s NHS Mental Health Trust (SWLSTG) | 7.1 | Estates Modernisation scheme to rationalise the local NHS estate to support clinical strategy, improving the efficiency of inpatient care and freeing up land for housing. | -
South Yorkshire and Bassetlaw | 2.5 | Barnsley Hospital NHS Foundation Trust | 0 | Co-location of Children’s ED and Children's Assessment Unit. Bringing together the Children’s ED and Children’s Assessment Unit in to a collocated integrated model of care to support rapid turnaround of children using an assessment model in place of a traditional predominantly inpatient based model. | - | No response
South Yorkshire and Bassetlaw | 7 | Yorkshire Ambulance Service NHS Trust | 0 | The Doncaster Urgent and Emergency Care scheme to expand, redesign and improve emergency care, including through a new ambulance operational deployment model in the Doncaster area to respond to changing patient needs. | - | No response
The Black Country | 1.3 | Dudley Group NHS Foundation Trust | 1.3 | The Russell’s Hall Hospital Dudley Urgent Care Centre scheme to implement co-location with the Emergency Department and facilitate better integration of services. | -
West Yorkshire | 13 | Leeds Community Healthcare NHS Trust | 0 | The Leeds Community Child and Adolescent Mental Health Inpatient Unit scheme to provide a new specialist inpatient unit to meet the needs of young people and children with mental health conditions. | - | Full Business case to be submitted in October 2019
WAVE 3 | Allocated up to (£m) | Lead Organistion | How much received so far? (£m) | Scheme Description |  | Next step in securing the money?
Bristol, North Somerset, South Gloucestershire | 7.5 | Avon and Wiltshire Mental Health Partnership NHS Trust | 0 | Reconfiguration and relocation of mental health inpatient wards and community teams across the STP to deliver higher quality and more efficient services, and make best use of available estate. | - | Preparing full business case
Bristol, North Somerset, South Gloucestershire | 2 | Avon and Wiltshire Mental Health Partnership NHS Trust | 0 | CAMHS Tier 4. Increase of 15 beds. Trust contributing 0.4m of total cost of £2.4m Beds would open June 2019 | - | Preparing full business case
Buckinghamshire, Oxfordshire and Berkshire | 3 | Oxford Health NHS Foundation Trust | 0 | CAMHS Tier 4. Expansion in beds at Highfield Unit of 8 Psychiatric Intensive Care Unit beds. | - | Awaiting approval of Full Business Case by NHSI/NHSE
Derbyshire | 6.5 | Derby Teaching Hospitals NHS Foundation Trust | 3 | Additional theatre capacity at Royal Derby Hospital NHS Foundation Trust. Maximising community hospital estates infrastructure to support the sustainable delivery of endoscopy and orthopaedics. | - | Beds element complete in 18/19. Endoscopy & Theatres to be complete and paid in 19/20. (£3.5m)
Devon | 26.2 | Plymouth Hospitals NHS Trust | 0 | Hybrid Theatres - 4 new Interventional Theatres to improve the provision of Interventional Radiology | - | The OBC is being finalised and has involved extensive work agreeing the final configuration and costs. OBC is expected to be approved by the Trust Board in July 2019 before submission to NHSE/I. The FBC is expected by March 2020 with money drawn down when it is approved later in 2020.
Devon | 13.3 | Torbay and South Devon NHS Foundation Trust | 0 | Transforming and Developing Urgent Care Environment. The new model of emergency care agreed across the health community envisages a smaller number of minor injury units, two urgent care centres in Newton Abbot and in Torquay and a fit for purpose emergency department in Torbay Hospital. | - | The FBC is due to be submitted to NHSE/I later this year and approval is expected by summer 2020.
Gloucestershire | 39.5 | Gloucestershire Hospitals NHS Foundation Trust; | 0 | New facilities at Gloucestershire Royal with Emergency Department area, fracture clinic, wards and diagnostics, and additional theatres, and additional capacity for urgent care, and reconfiguring elective activities at Cheltenham General Hospital, to enable redesign of the urgent and emergency care pathways | - | Awaiting feedback on strategic outline case, then funding is subject to an outline business case and full business case
Hampshire and Isle of Wight | 17.5 | St Mary's Hospital NHS Trust, Portsmouth Hospitals NHS Trust, University Hospital Southampton NHS Foundation Trust | 0 | Service Development. Investment in new operating theatres at both Portsmouth Hospitals and University Hospital Southampton, pharmacy procurement and distribution, maternity care records and digital outpatients. | - | Said some money has been received, but it's not listed in DHSC accounts
Hampshire and Isle of Wight | 10.3 | Solent NHS Trust | 5.5 | St James Hospital Main Site (Phase 2). Development of clinical services at St Mary’s Hospital - a key hub in the city of Portsmouth for community care and mental health services | -
Hampshire and Isle of Wight | 3 | Southern Health NHS Foundation Trust | 0 | CAMHS Tier 4. 14 additional low secure adolescent beds. | - | Said some money has been received, but it's not listed in DHSC accounts
Humber, Coast and Vale | 7.8 | Humber NHS Foundation Trust | 0 | CAMHS Tier 4. New build CAMHS Inpatient Unit, including 9 general beds and 4 PICU beds to meet needs of young people in the Yorkshire and Humber region. | - | Business cases not complete
Kent & Medway | 1 | Medway NHS Foundation Trust | 0 | Front Door Patient Triage. Creation of an Urgent Treatment Centre at the 'front door' of Medway Maritime Hospital directing patients to the most clinically appropriate service. | - | We remain on course to receive our funding
Kent & Medway | 8.5 | NHS Medway CCG | 0 | Development of Chatham Health and Wellbeing Centre. To develop purpose-built premises in Chatham to provide sustainable and integrated primary and community services in the heart of a growing population | - | We remain on course to receive our funding
Kent & Medway | 6 | NHS Medway CCG | 0 | Development of Strood Health and Wellbeing Centre. To develop a purpose-built premises in Strood to address both GP resilience in the area and health inequality issues. | - | We remain on course to receive our funding
Kent & Medway | 1.5 | South Kent Coast CCG | 0 | Romney Marsh Hub. Expansion of Primary and Community integrated services, providing local care for the growing population of Romney Marsh. | - | We remain on course to receive our funding
Kent & Medway | 2.5 | Thanet CCG | 0 | Margate Hub. Development of the Margate Hub, which will provide integrated primary and community care across the growing local community. | - | We remain on course to receive our funding
Lancashire and South Cumbria | 31.2 | Lancashire Teaching Hospitals NHS Foundation Trust | 0 | Lancashire and South Cumbria Pathology Collaboration. Provision of a single pathology diagnostic service for NHS organisations and associated Clinical Commissioning Groups across Lancashire and South Cumbria. | - | SOC still needs agreement
Milton Keynes, Bedfordshire and Luton | 1 | Bedford Hospital NHS Trust | 0 | Physiotherapy Integration. Integrate physiotherapy services in a Hub Model for the local area. | - | No response
Milton Keynes, Bedfordshire and Luton | 6 | Bedfordshire CCG and Bedford Hospital Trust | 0 | Bedford Central and North Integrated Health and Care Hub. Integrated health and social care hub, Gilbert Hitchcock House, to enable delivery of Primary Care Home Model including primary care services at scale, community health and social care services and specialist services. | - | No response
Norfolk and Waveney | 0.6 | Norfolk and Suffolk NHS Foundation Trust | 0 | Mental Health Crisis Café. To provide a facility to support people in escalating mental health conditions. | - | Funding is on course to be received by NHS Property Services.
North West London | 0.3 | Barnet, Enfield and Haringey Mental Health NHS Trust | 0 | CAMHS. 3 new Tier 4 beds. | - | Following further discussions with commissioners only two additional tier 4 CAMHS beds were commissioned from the trust. This did not require the level of capital investment previously bid for and the trust therefore notified NHSI that we would not require the £300,000 originally awarded.
North West London | 2.1 | Central & North West London NHS Foundation Trust | 2.1 | CAMHS Tier 4. 5 additional beds at Kingswood Hospital for people with learning difficulties/autistic spectrum disorders | -
North West London | 2.1 | Central & North West London NHS Foundation Trust | 2.1 | CAMHS Tier 4. Tier 4 12 additional beds in South Kensington. | -
Shropshire and Telford and Wrekin | 312 | Shrewsbury and Telford Hospital NHS Trust | 0 | Sustainable Services Project. Transforming services across two sites at Princess Royal Hospital Telford and Royal Shrewsbury Hospital, with new emergency care and planned care builds. | - | Project referred to secretary of state
Somerset | 79.4 | Taunton and Somerset NHS Foundation Trust | 0.6 | Replacement of Theatres and Critical Care facilities. Replacement of outdated clinical facilities that are no longer fit for the purpose of providing complex high acuity care for patients | - | Full business case in development
South West London | 9.8 | Croydon CCG | 0 | Croydon Primary & Community Care Transformation. Transformation of services through One Croydon Alliance Out of Hospital Transformation Programme, integrating community networks, ensuring that vulnerable and at-risk patients are better supported out of hospital. | - | Croydon CCG is completeing the full business case to enable the funding to be released
South West London | 2.1 | Croydon Health Services NHS Trust | 2.1 | Consolidation of three procurement functions. Consolidation into a single shared service, providing an overall improvement in the delivery of clinical care and inventory management. | -
South West London | 2.7 | South London & Maudsley NHS Foundation Trust | 2.7 | CAMHS Tier 4. 8 additional beds for people with learning difficulties/autistic spectrum disorders. | -
South West London | 11.1 | South West London and St George's Mental Health NHS Trust | 0 | Barnes Medical Centre development. The new healthcare facility will provide mental health outpatient services, alongside an extended range of general practice services, a range of other community services, and a wide | - | While the sale of the surplus share of the land has been agreed for housing with a special needs school on-site, work is in progress to finalise the use of funding for the remaining space.
Suffolk and North East Essex | 69.3 | Colchester Hospital University NHS Foundation Trust / Ipswich Hospital NHS Trust | 0 | Colchester Hospital and Ipswich Hospital Partnership reconfiguration. New facilities to support clinical strategies post-merger including urgent emergency care hyper, interventional radiology facilities, CT and MRI provision, new dedicated elective care facilities, and expansion of majors and resuscitation capacity. | - | We are closely following the due process and are confident that funding will be allocated very soon for us to progress with our plans
Suffolk and North East Essex | 3.4 | North East Essex CCG | 0 | Harwich and Colchester Primary Care practices. To support practices in inappropriate premises ensuring areas with high demographic growth have the required estates resources to enable new services models and clinical pathways and support new organisational forms in primary care. | - | We are closely following the due process and are confident that funding will be allocated very soon for us to progress with our plans
Suffolk and North East Essex | 14.7 | North East Essex CCG | 0 | Clacton Hospital redevelopment. First phases of the redevelopment of Clacton Hospital Services through the development of Outpatient, Minor Injury, Diagnostic and Primary Care Centre on the site. | - | We are closely following the due process and are confident that funding will be allocated very soon for us to progress with our plans
Surrey Heartlands | 0.5 | Surrey and Borders Partnership NHS Foundation Trust | 0 | Refurbishment of place of safety for mental health crisis, in Guildford and Chertsey. | - | This expenditure is linked to a project covering the wider re-development of our inpatient facilities, which is still at the planning stage.
Sussex and East Surrey | 19.3 | Surrey & Sussex Healthcare NHS Trust | 0 | Sussex and East Surrey pathology hub and laboratory information management system. Centralisation of pathology services between 3 acute trusts as second stage of implementation of pathology network consolidation plan. | - | Need to complete business case before accessing the money
The Black Country | 3.3 | The Royal Wolverhampton NHS Trust | 3.3 | Royal Wolverhampton stroke service. To improve and expand the stroke services for NHS Midlands and East STP. | -
The Black Country | 9 | The Royal Wolverhampton NHS Trust | 0 | Black Country Pathology. To consolidate Pathology services across the Black Country into a single Black Country Pathology Service | - | Formal business case recently approved. Money will now be released.
West Yorkshire | 1.5 | Airedale NHS Foundation Trust | 0 | West Yorkshire Telemedicine in Care Homes. The commissioning of the care home telemedicine service across the STP and upgrading infrastructure to enhance services. | - | Decided to pull the scheme. A bid for capital funding was first put in 18 months ago as we thought we would need to build an IT infrastructure for our telemedicine system. Since that time, the technologies have changed which means that more app based solutions are being used, so it wouldn’t be financially viable to build an IT infrastructure that will soon be outdated.
West Yorkshire | 2 | Calderdale and Huddersfield Foundation Trust | 0.3 | West Yorkshire National Pathology Exchange. To deliver a lab-to-lab messaging solution that connects Laboratory Information Management Systems (LIMS) together to facilitate the electronic transfer of pathology test requests and results. | - | No response
West Yorkshire | 15 | Mid Yorkshire Hospitals NHS Trust | 0 | Adoption of GS1 Standards - using Location coding / Catalogue Management / Patient Identity to support Inventory Management / Purchase-to-Pay / Product recall, to improve patient safety. | - | Business case to access £4m to roll out LTHT Scan for Safety solution across West Yorks under preparation. LTHT is leading on this project.
West Yorkshire | 6.1 | Mid Yorkshire Hospitals NHS Trust | 0 | Yorkshire Imaging Collaborative. Collaborative procurement of enterprise imaging solutions to transform radiology services to meet some of the capacity and demand issues | - | FBC due to be submitted later this year
WAVE 4 | Allocated up to (£m) | Lead Organistion | How much received so far? (£m) | Scheme Description |  | Next step in securing the money?
Bath, Swindon and Wiltshire | 29.6 | Great Western Hospital NHS Foundation Trust | 0 | Integrated Front Door & Transitional Care Facility | - | Going through the business case process
Bath, Swindon and Wiltshire | 16 | Wiltshire CCG | 0 | Trowbridge Integrated Care Centre | - | Going through the business case process
Bristol, North Somerset, South Gloucestershire | 3.2 | Bristol, North Somerset and South Gloucestershire CCG | 0 | North Somerset Primary Care, Central Weston | - | Preparing outline business case
Bristol, North Somerset, South Gloucestershire | 1.6 | North Bristol NHS Trust | 0 | 12 Additional Beds through Conversion of Assisted Bathrooms | - | Preparing full business case
Buckinghamshire, Oxfordshire and Berkshire West | 2.8 | Berkshire Healthcare NHS Foundation Trust | 0 | Relocation of Willow House to Prospect Park Hospital Site | - | No delay. Business Case in development for national approval
Buckinghamshire, Oxfordshire and Berkshire West | 8.6 | Oxford Health NHS Foundation Trust | 0 | 10 Bed Learning Disabilities Low Secure Unit | - | Full business case with NHSE/NHSI for approval
Buckinghamshire, Oxfordshire and Berkshire West | 1.8 | Oxford University Hospitals NHS Foundation Trust | 0 | Delivery Suite Theatre, John Radcliffe Hospital | - | Full business case with NHSE/NHSI for approval
Cambridgeshire and Peterborough | 100 | Cambridge University Hospitals NHS Foundation Trust | 0 | Cambridge Children’s Hospital | - | Funds requested through the STP bidding process are for the construction of the building which is expected to take place in 2022-24. The project is in discussion with NHSI regarding business case funding. SOC currently with NHSI for review. OBC being produced for submission.
Cambridgeshire and Peterborough | 19.2 | Cambridge University Hospitals NHS Foundation Trust | 0 | Capacity solution to enable urgent fire safety works | - | Funds requested through the STP bidding process are for the construction of the building which is expected to take place in 2020-21. The project is in discussion with NHSI regarding business case funding. OBC being produced for submission.
Cambridgeshire and Peterborough | 25.5 | North West Anglia NHS Foundation Trust | 0 | Expansion at Hinchingbrooke Hospital | - | No delays with funding. OBC being produced ready for submission in summer for Urgent Care Outline Business Case. Beds and Theatres OBC to be ready for October 2019.
Cheshire and Merseyside | 7 | Alder Hey Children's NHS Foundation Trust | 0 | CAMHS Tier 4 inpatient beds – Dewi Jones Unit | - | Alder Hey’s business case has been submitted for gateway review and they are planning to draw on the funding this financial year.
Cheshire and Merseyside | 4 | St Helens CCG / St Helens and Knowsley Teaching Hospitals NHS Trust | 0 | Improving Emergency Department capacity and flow | - | St Helens and Knowsley Teaching Hospitals NHS Trust have been developing full details of their scheme and funding will be requested to meet contractual commitments in this financial year.
Cornwall and the Isles of Scilly | 31.3 | Royal Cornwall Hospitals NHS Trust | 0 | Oncology & MRI Re- provision | - | The current position is that we are going through the business case approval process so monies wouldn’t be released until that is all completed and then we’d anticipate starting during the current financial year.
Cornwall and the Isles of Scilly | 9.1 | Royal Cornwall Hospitals NHS Trust | 0 | Peripheral Site Optimisation | - | The current position is that we are going through the business case approval process so monies wouldn’t be released until that is all completed and then we’d anticipate starting during the current financial year.
Cumbria and North East | 54.2 | Northumberland, Tyne & Wear NHS Foundation Trust | 0 | Secure Services / Newcastle and Gateshead Adult Acute Inpatients | - | We are not expecting any release of STP funding until final sign off of the full business case which is planned for July 2020.
Derbyshire | 8.6 | Derbyshire Community Health Services NHS Foundation Trust | 0 | Bakewell Integrated Community Hub | - | No drawdown available until FBC submitted
Devon | 8 | Devon Partnership NHS Trust | 0 | Reducing Out of Area Placements for Adult Acute Mental Health Service Across Devon | - | The Board will be considering the FBC in September before it is submitted to NHSI for approval. Construction of the new adult mental health ward in Torbay is planned to start in Spring 2020 and to be completed by autumn 2021.
Devon | 9.3 | University Hospitals Plymouth NHS Trust | 0 | Devon Imaging Facilities | - | The FBC has been approved by the UHP Trust Board and is being approved by the NDHT Board. FBC is due to be submitted to NHSI for approval in June 2019. Money is planned to be drawn down and the project completed in 2019.
Devon | 3.5 | University Hospitals Plymouth NHS Trust | 0 | Digital Histopathology Devon & Cornwall | - | The FBC is expected to be complete in spring 2020.
Devon | 29.7 | University Hospitals Plymouth NHS Trust | 0 | Transforming Urgent and Emergency Care | - | The OBC is due to be complete in the autumn with FBC to follow in 2020.
Dorset | 5.9 | Dorset HealthCare University NHS Foundation Trust | 0 | Mental Health Estate Development | - | We will not receive the mental health estate development funding until our FBC is approved. We anticipate this will happen around April next year.
Dorset | 4.2 | Dorset HealthCare University NHS Foundation Trust | 0 | Blandford Primary and Community Hub | - | We will not receive any funding until our OBC and FBC are approved. We don't have a definite timetable for these but are planning to work on the OBC this year.
Dorset | 5.1 | The Royal Bournemouth & Christchurch Hospitals NHS Trust | 0 | Pan-Dorset Pathology Laboratory information management system | - | No response
Frimley Health | 1 | North East Hampshire & Farnham CCG | 0 | Alexander House extension | - | Work is going on locally on preparing our business cases. Once these business cases have been submitted and approved, capital funding will be received. We are currently working on an options appraisal for the premises requirement.
Greater Manchester | 4.8 | Pennine Care NHS Foundation Trust | 0 | Proposal for the Development and Provision of Psychiatric Intensive Care Services | - | The design team is in place and the project will be tendered at the beginning of August. The FBC will be presented to the PCFT Board in September and the plan is to submit it to NHSE/I in October. Construction is planned to commence early 2020. No funding was expected to have been released at this time.
Hampshire and the Isle of Wight | 10.2 | Hampshire Hospitals NHS Foundation Trust | 0 | Elective Expansion and Reconfiguration of Royal Hampshire County Hospital Winchester | - | Going through business case approvals process
Hampshire and the Isle of Wight | 2.4 | North Hampshire CCG | 0 | Same Day Access Service - Basingstoke | - | Going through business case approvals process
Hampshire and the Isle of Wight | 2.6 | Portsmouth City CCG | 0 | Relocation of North Harbour Medical Group GP Practice | - | Going through business case approvals process
Hampshire and the Isle of Wight | 58.3 | Portsmouth Hospitals NHS Trust | 0 | Emergency Floor Programme Portsmouth | - | Going through business case approvals process
Hampshire and the Isle of Wight | 15.8 | Solent NHS Trust | 0 | Community bed capacity optimisation, Southampton | - | Going through business case approvals process
Herefordshire and Worcestershire | 3 | Hereford Medical Group | 0 | Hereford Primary Care Hub | - | No reply
Herefordshire and Worcestershire | 4 | Worcestershire Acute Hospitals NHS Trust | 0 | Breast Imaging Improvement Plan | - | No reply
Hertfordshire and West Essex | 7.2 | East and North Hertfordshire NHS Trust | 0 | Hertfordshire and West Essex Vascular Surgery Network | - | Business case not completed
Hertfordshire and West Essex | 4.2 | East and North Hertfordshire NHS Trust | 0 | Luton & Dunstable Renal Dialysis Unit Relocation | - | Business case not completed
Hertfordshire and West Essex | 9.5 | The Princess Alexandra Hospital NHS Trust | 0 | Additional Bed Capacity at Princess Alexandra Hospital | - | Business case not completed
Hertfordshire and West Essex | 11 | West Hertfordshire Hospitals NHS Trust | 0 | Emergency Care Transformation | - | Business case not completed
Humber, Coast and Vale | 88.5 | Humber, Coast and Vale Health and Care Partnership | 0 | Diagnostic equipment and transformation of urgent & emergency care | - | Business cases not complete
Kent & Medway | 6.5 | South East Coast Ambulance Service NHS Foundation Trust | 0 | Medway Make Ready Centre | - | We are working through the governance process regarding this with NHSI and NHSE and expect the funding following the conclusion of this process
Lancashire and South Cumbria | 12.9 | Blackpool Teaching Hospitals NHS Foundation Trust | 0 | Fylde Coast Emergency Department / Critical Care Scheme | - | Buisness cases being developed
Lancashire and South Cumbria | 8.1 | Lancashire Care NHS Foundation Trust | 0 | Fylde Coast Integrated Acute Mental Health Hub | - | Buisness cases being developed
Leicester, Leicestershire and Rutland | 7 | West Leicestershire CCG | 0 | Hinckley and Bosworth Community Health Services | - | Spend/drawdown subject to final approval of the Pre-consultation business case and after consultation
Lincolnshire | 1.5 | United Lincolnshire Hospitals NHS Trust | 0 | Multi-Purpose Education Centre to support University Medical School of Excellence (Lincoln) | - | We're currently reviewing the options available and putting a robust business case together to ensure we meet the requirements to unlock the funding.
Milton Keynes, Bedfordshire and Luton | 10 | Milton Keynes University Hospital NHS Foundation Trust | 0 | Pathway Unit | - | No response
Milton Keynes, Bedfordshire and Luton | 0.8 | NHS Bedfordshire CCG | 0 | Stroke Rehabilitation Unit | - | No response
North Central London | 86 | Camden and Islington NHS Foundation Trust | 0 | St Pancras - transformation of mental health and substance misuse services | - | We have not receivd any PDC so far, nor are we planning to receive any of this PDC funding this financial year because our plan envisages building starting no earlier than 2020 and we would use our own internally generated cash reserves (which stood at £41m in March 2019) to a level compatible with retaining adequate working capital, before drawing down any PDC, which cannot be drawn in advance of need.
North Central London | 18.2 | Moorfields Eye Hospital NHS Foundation Trust | 0 | Project Oriel - a new eye care, research and education facility | - | Did not comment
North West London | 0.5 | Central & North West London NHS Foundation Trust | 0.5 | Northwick Park Mental Health Wards - Single Bedrooms Reconfiguration | -
North West London | 0.5 | Central & North West London NHS Foundation Trust | 0.5 | Oak Tree Ward - Woodlands Mental Health Wards Reconfiguration, Hillingdon | -
North West London | 2.4 | Central & North West London NHS Foundation Trust | 2.4 | Pond Ward - Park Royal Mental Health Wards Reconfiguration | -
North West London | 1.9 | Imperial College NHS Trust | 0 | The Development of an Endovascular Hybrid Theatre | - | We are waiting for NHSI to approve our business case which was submitted on 24 May
North West London | 27 | London North West University Healthcare NHS Trust | 0 | Re-provision of eight compliant theatres | - | Only £2m is centrally funded, balance to come from asset disposals. Trust is reviewing priorities as theatres development is dependent on investment in recovery and that investment bid was not approved
Nottinghamshire | 10.7 | Nottingham University Hospitals NHS Trust | 0 | Emergency Pathway Improvement | - | Ongoing business case development
Somerset | 11.5 | Taunton and Somerset NHS Foundation Trust | 0 | Acute Assessment Hub | - | Full business case required
South East London | 5 | Bromley CCG, Lambeth CCG and Lewisham CCG | 0 | South East London Estate Optimisation | - | Business case still in development
South East London | 3.6 | Greenwich CCG | 0 | New Kidbrooke sub Hub | - | Business case still in development
South East London | 10.5 | Guy’s & St Thomas’ NHS Foundation Trust | 0 | Patient Centric Supply Chain | - | Business case still in development
South East London | 1.3 | Lambeth CCG | 0 | Consolidation of Streatham Common Group Practice at Baldry Gardens Health Centre | - | Business case still in development
South East London | 9.4 | NHS Bromley CCG | 0 | Bromley Health & Wellbeing Centre | - | Business case still in development
South West London | 3.4 | Kingston NHS Foundation Trust | 3.4 | Patient Flow Transformation Programme | -
Staffordshire | 1.6 | North Staffordshire Combined Healthcare | 0 | Urgent Care Centre, Detoxification suites and crisis cafes | - | no response
Staffordshire | 21.9 | University Hospitals of Derby and Burton NHS Foundation Trust | 0 | Outwoods Health Village | - | Full Business to be submitted before drawdown
Suffolk and North East Essex | 18 | East of England Ambulance Service NHS Trust | 0 | Infrastructure & Capacity Transformation: Fleet, Estates & Make Ready Service | - | We are required to submit a final business case before we receive the Wave 4 funding
Suffolk and North East Essex | 13.4 | West Suffolk NHS Foundation Trust | 0 | Emergency Department Strategic Redevelopment | - | We have not received any of the funding as it is subject to the approval of a business case which is due to be completed in November 2019
Surrey Heartlands | 7.4 | Epsom and St Helier University Hospitals NHS Trust | 0 | Transfer of New Epsom and Ewell Cottage Hospital to Epsom General Hospital | - | We haven’t drawn down any of the funds yet but this does not represent a delay as we had not anticipated spending yet. Following completion and approval of the FBC we will draw down the funds from DHSC over the remainder of this and next financial year as the capital works progress. It is likely that only the design works will be completed this financial year, in Q4.
Surrey Heartlands | 4 | Surrey & Borders Partnership NHS Foundation Trust | 0 | Community Hub Programme | - | This expenditure is linked to our programme to improve our community services facilities. This is still in the planning and property search phase.
Sussex and East Surrey | 5.5 | South East Coast Ambulance Service NHS Foundation Trust | 0 | Brighton Make Ready Centre | - | We are working through the governance process regarding this with NHSI and NHSE and expect the funding following the conclusion of this process
Sussex and East Surrey | 6.7 | South East Coast Ambulance Service NHS Foundation Trust | 0 | Expansion of additional floor space at the Trust Headquarters building | - | We are working through the governance process regarding this with NHSI and NHSE and expect the funding following the conclusion of this process
Sussex and East Surrey | 0.2 | South East Coast Ambulance Service NHS Foundation Trust | 0 | Worthing Make Ready Centre | - | We are working through the governance process regarding this with NHSI and NHSE and expect the funding following the conclusion of this process
The Black Country | 7.5 | Black Country Partnership NHS Foundation Trust | 0 | Black Country Transforming Care Partnership LD Service Transformation | - | Business cases being developed for submission to NHS Improvement for next stage of approval process.
The Black Country | 15.4 | Sandwell and West Birmingham Hospitals NHS Trust | 0 | Sandwell and West Birmingham Hospitals Interim Reconfiguration | - | Business cases being developed for submission to NHS Improvement for next stage of approval process.
The Black Country | 17 | The Dudley Group NHS Foundation Trust | 0 | Redevelopment of Emergency Department at Russell's Hall Hospital | - | Business cases being developed for submission to NHS Improvement for next stage of approval process.
The Black Country | 36.2 | Walsall Healthcare NHS Trust | 0 | Emergency Department Development | - | Business cases being developed for submission to NHS Improvement for next stage of approval process.
West Yorkshire | 21.9 | Calderdale & Huddersfield NHS Foundation Trust | 0 | Reconfiguration of hospital services | - | No response
West Yorkshire | 11.2 | Leeds and York Partnership NHS FOUNDATION TRUST (West Yorkshire Mental Health Trusts) | 0 | Rehabilitation and Recovery Repatriation | - | No delay. Capital Business case submission April 2020.
West Yorkshire | 25.8 | Leeds Teaching Hospitals NHS Trust | 0 | Consolidation of Pathology Services | - | Awarded Dec 2018. Leeds Teaching Hospitals is currently developing the Outline Business Case. No funds have been received by the Trust yet.
WAVE NOT KNOWN | Allocated (up to £m) | Lead Organistion | How much received so far? | Scheme Description |  | Next step in securing the money?
Derbyshire | 0 | Derbyshire Community Health Services FT | 0.25 | Unclear
Humber Coast and Vale | 0 | Humber Teaching FT | 5.6 | Unclear