## Sheet1
Wave | STP | Allocated (up to £m) | How much received? | Lead Organisation at the time | Scheme Description | What stage is the project at? | Expected delivery date of project?
Wave 1 | Buckinghamshire, Oxfordshire and Berkshire West | 5 | 5 | Buckinghamshire Healthcare Trust | Rapid assessment and treatment centre and observation unit at Stoke Mandeville Hospital | Completed | Completed
Wave 1 | Cumbria and North East | 69 | 55 | North Cumbria University Hospitals Trust | New cancer centre and equipment at Cumberland Infirmary in Carlisle, as well as significant refurbishment and rebuilding work at West Cumberland Hospital, and the development of eight integrated care hubs | Cancer Centre is completed. West Cumberland Hospital is in progress. Integrated Hubs are completed | Completed
Wave 1 | Derbyshire | 20 | 0 | Royal Derby and Burton Hospitals FT | Expand the emergency department at Royal Derby Hospital. Co-locate mental health assessment, GP care and out of hours services, and create a new facility that collocates community services, outpatient clinics, testing and diagnostics, and specialist rehabilitation services. | NHSE have placed this project on 'Pause' | Information not supplied
Wave 1 | Dorset | 201.8 | 82.3 | Royal Bournemouth and Poole Hospitals | Major consolidation of emergency and planned care services between Bournemouth and Poole hospitals. | In Construction | 30/09/2026 Commissioning completes
Wave 1 | Greater Manchester | 50 | 50 | Various | Healthier Together | Information not supplied | Information not supplied
Wave 1 | Greater Manchester | 30 | 30 | Salford Royal FT | Trauma centre | Final commissioning stages | 2023-06-01
Wave 1 | Hereford and Worcestershire | 30 | 24.02 | Worcestershire Acute Hospitals | Consolidate maternity services, emergency surgery, and children’s services at Worcestershire Royal Hospital. Withdraw these services from Alexandra Hospital in Redditch, which will receive investment for elective care, endoscopy, children’s outpatients and theatre upgrades. | All works complete except for: Endoscopy (Alx Hospital), Maternity/Paeds (WRH Hospital) | 2024-11-01
Wave 1 | Lancashire and South Cumbria | 30 | 9 | East Lancashire Hospitals Trust and Lancashire Care FT | Modernise mental health facilities and expand accident and emergency facilities at the Royal Blackburn Hospital | Mental health facility is completed and in use. Expansion of A&E ongoing | End of 2024 due to additional building works to remove RAAC
Wave 1 | Leicester, Leicestershire and Rutland | 50 | 38.8 | University Hospitals of Leicester FT/Leicester Partnership | 15 bed inpatient unit at Glenfield General Hospital, to bring specialist mental health provision together with other services, and to fund an expansion of intensive care | No information supplied | No information supplied
Wave 1 | Mid and South Essex | 15 | 7 |  | Expand capacity for diagnostics and improve outpatient services | Equipment procured. Planning/Procurement stage | One CDC will open early 2024, another summer 2023
Wave 1 | Milton Keynes, Bedfordshire and Luton | 5 | Information not supplied |  | Primary care hub | No information supplied | No information supplied
Wave 1 | Norfolk and Waveney | 4 | 4 | Norfolk and Suffolk FT | Mental health beds in west Norfolk | Completed | 2022-12-01
Wave 1 | North East London | 0.5 | 0.5 | Barking Havering and Redbridge | Redesigning the urgent care centre at King George’s Hospital | Completed | 2022-12-01
Wave 1 | Nottinghamshire | 15 | 0 |  | Improve and expand access to primary, community and social care | No information supplied | No information supplied
Wave 1 | South Yorkshire and Bassetlaw | 10 | 10 |  | Improve acute hospital facilities | Completed | Completed
Wave 1 | Suffolk and North East Essex | 2.7 | 2.8916 |  | New primary care hub in North Clacton, and the relocation of a GP surgery in West Suffolk | Complete | Completed
Wave 2 | Birmingham and Solihull | 1.1 | 0.5 | Birmingham Women’s and Children’s FT | Emergency Department scheme to increase emergency care capacity and improve patient experience. | Completed | Completed
Wave 2 | Buckinghamshire, Oxfordshire and Berkshire West | 8.8 | 1.487 | NHS Chiltern CCG | The Chiltern and Aylesbury Vale Primary Care Hub scheme to establish an integrated service model to allow the expansion of community teams and care provision outside of traditional hospital settings. | Funding drawn down is for Chalfont Project. The business cases for the remaining projects remain with DHSC for approval | Chalfont Project, phase one May 2023 and phase two July 2023.
Wave 2 | Coventry and Warwickshire | 9.4 | 9.4 | South Warwickshire FT (SWFT) | The South Warwickshire Out of Hospital Care scheme to provide an integrated information system to improve collaboration between providers across the area. | Most elements of the scheme are complete, except for some final works required to complete the community locality hubs element of the scheme | Adults, Children's and Hospice EPR systems and population health system were all fully delivered in prior years. Completion of locality hubs due in Dec-23
Wave 2 | Derbyshire | 19.1 | 19.1 | Chesterfield Royal FT | The Chesterfield Urgent Care scheme to upgrade the emergency care department of Chesterfield Royal NHS Foundation Trust to provide a modern urgent care facility to deal with changing patient needs. | Build completed. | To open in June 2023
Wave 2 | Frimley Health | 28.4 | 0 | Frimley Health FT | The Frimley Out of Hospital Integrated Care Hubs scheme to provide integrated hubs to provide better treatment to patients more quickly out of hospital. | National pause on Wave Two STP funding has now been lifted, although no funding has been received as yet. The funding is now available until March 2025, which is an extension of one year. | Information not supplied
Wave 2 | Frimley Health | 3 | 3 | NHS East Berkshire CCG | The Bracknell Forest Heathlands scheme to build a new home for nursing and elderly mentally infirm care to improve services for local patients in the community. | Completed | Completed
Wave 2 | Mid and South Essex | 118 | 8 | MSB Hospital Group | The Mid and South Essex Transforming Health and Care scheme to transform acute and out of hospital services in the local area to improve care delivery. | Being delivered in phases. Planning/procurement stage | 2023/24
Wave 2 | South West London | 7.1 | 7.1 | South West London and St George’s NHS Mental Health Trust (SWLSTG) | Estates Modernisation scheme to rationalise the local NHS estate to support clinical strategy, improving the efficiency of inpatient care and freeing up land for housing. | Completed | Completed
Wave 2 | South Yorkshire and Bassetlaw | 2.5 | 2.5 | Barnsley Hospital FT | Co-location of Children’s ED and Children's Assessment Unit. Bringing together the Children’s ED and Children’s Assessment Unit in to a collocated integrated model of care to support rapid turnaround of children using an assessment model in place of a traditional predominantly inpatient based model. | Completed | Completed
Wave 2 | South Yorkshire and Bassetlaw | 7 | 7 | Yorkshire Ambulance Service NHS Trust | The Doncaster Urgent and Emergency Care scheme to expand, redesign and improve emergency care, including through a new ambulance operational deployment model in the Doncaster area to respond to changing patient needs. | Completed | Completed
Wave 2 | The Black Country | 1.3 | 1.3 | Dudley Group FT | The Russell’s Hall Hospital Dudley Urgent Care Centre scheme to implement co-location with the Emergency Department and facilitate better integration of services. | Completed | Completed
Wave 2 | West Yorkshire | 13 | 13 | Leeds Community Healthcare NHS Trust | The Leeds Community Child and Adolescent Mental Health Inpatient Unit scheme to provide a new specialist inpatient unit to meet the needs of young people and children with mental health conditions. | Complete | Completed - opened in January 2022
Wave 3 | Bristol, North Somerset, South Gloucestershire | 7.5 | 1 | Avon and Wiltshire Mental Health Partnership NHS Trust | Reconfiguration and relocation of mental health inpatient wards and community teams across the STP to deliver higher quality and more efficient services, and make best use of available estate. | Fully designed to FBC stage | 2025 dependent on FBC approval
Wave 3 | Bristol, North Somerset, South Gloucestershire | 2 | 2 | Avon and Wiltshire Mental Health Partnership NHS Trust | CAMHS Tier 4. Increase of 15 beds. Trust contributing 0.4m of total cost of £2.4m Beds would open June 2019 | Completed | Completed
Wave 3 | Buckinghamshire, Oxfordshire and Berkshire | 3 | Information not supplied | Oxford Health FT | CAMHS Tier 4. Expansion in beds at Highfield Unit of 8 Psychiatric Intensive Care Unit beds. | Information not supplied | Information not supplied
Wave 3 | Derbyshire | 6.5 | 6.5 | Derby Teaching Hospitals FT | Additional theatre capacity at Royal Derby Hospital NHS Foundation Trust. Maximising community hospital estates infrastructure to support the sustainable delivery of endoscopy and orthopaedics. | Completed and operational | Completed
Wave 3 | Devon | 26.2 | 0 | Plymouth Hospitals NHS Trust | Hybrid Theatres - 4 new Interventional Theatres to improve the provision of Interventional Radiology | Project absorbed into wider and separately funded Future Hospital Scheme. Currently at detailed design stage | N/A
Wave 3 | Devon | 13.3 | 13.3 | Torbay and South Devon FT | Transforming and Developing Urgent Care Environment. The new model of emergency care agreed across the health community envisages a smaller number of minor injury units, two urgent care centres in Newton Abbot and in Torquay and a fit for purpose emergency department in Torbay Hospital. | Complete | 2022-12-01
Wave 3 | Gloucestershire | 39.5 | 39.5 | Gloucestershire Hospitals FT; | New facilities at Gloucestershire Royal with Emergency Department area, fracture clinic, wards and diagnostics, and additional theatres, and additional capacity for urgent care, and reconfiguring elective activities at Cheltenham General Hospital, to enable redesign of the urgent and emergency care pathways | Construction | Final programme of works will be completed in summer 2023
Wave 3 | Hampshire and Isle of Wight | 17.5 | 14.75 | St Mary's Hospital NHS Trust, Portsmouth Hospitals NHS Trust, University Hospital Southampton FT | Service Development. Investment in new operating theatres at both Portsmouth Hospitals and University Hospital Southampton, pharmacy procurement and distribution, maternity care records and digital outpatients. | In Construction | 2024-02-01
Wave 3 | Hampshire and Isle of Wight | 10.3 | 10.3 | Solent NHS Trust | St James Hospital Main Site (Phase 2). Development of clinical services at St Mary’s Hospital - a key hub in the city of Portsmouth for community care and mental health services | in-service | completed
Wave 3 | Hampshire and Isle of Wight | 3 | 3 | Southern Health FT | CAMHS Tier 4. 14 additional low secure adolescent beds. | in-service | completed
Wave 3 | Humber, Coast and Vale | 7.8 | 7.8 | Humber FT | CAMHS Tier 4. New build CAMHS Inpatient Unit, including 9 general beds and 4 PICU beds to meet needs of young people in the Yorkshire and Humber region. | Complete | New unit opened in January 2022
Wave 3 | Kent & Medway | 1 | 0.87 | Medway FT | Front Door Patient Triage. Creation of an Urgent Treatment Centre at the 'front door' of Medway Maritime Hospital directing patients to the most clinically appropriate service. | Completed | Completed
Wave 3 | Kent & Medway | 8.5 | 0 | NHS Medway CCG | Development of Chatham Health and Wellbeing Centre. To develop purpose-built premises in Chatham to provide sustainable and integrated primary and community services in the heart of a growing population | In progress - business cases being developped | March 2025 (subject to business case approvals)
Wave 3 | Kent & Medway | 6 | 0 | NHS Medway CCG | Development of Strood Health and Wellbeing Centre. To develop a purpose-built premises in Strood to address both GP resilience in the area and health inequality issues. | Discussions taking place over delivering project in wider Strood town centre regeneration | TBC
Wave 3 | Kent & Medway | 1.5 | 0 | South Kent Coast CCG | Romney Marsh Hub. Expansion of Primary and Community integrated services, providing local care for the growing population of Romney Marsh. | Trying to find solution given limited capital. Discussions with NHSE for potentional extension of programme | TBC
Wave 3 | Kent & Medway | 2.5 | 0 | Thanet CCG | Margate Hub. Development of the Margate Hub, which will provide integrated primary and community care across the growing local community. | OBC approved, FBC being developed. Discussions with NHSE for potentional extension of programme | March 2025 (subject to business case approvals)
Wave 3 | Lancashire and South Cumbria | 31.2 | 0 | Lancashire Teaching Hospitals FT | Lancashire and South Cumbria Pathology Collaboration. Provision of a single pathology diagnostic service for NHS organisations and associated Clinical Commissioning Groups across Lancashire and South Cumbria. | The network project is progressing with the development of a single pathology service whilst outcome from the OBC awaited. | Dependent on DHSC response to OBC
Wave 3 | Milton Keynes, Bedfordshire and Luton | 1 | 0 | Bedford Hospital NHS Trust | Physiotherapy Integration. Integrate physiotherapy services in a Hub Model for the local area. | FBC submit to NHSE Sep 2023 | Dependent on timing of FBC approval
Wave 3 | Milton Keynes, Bedfordshire and Luton | 6 | 0 | Bedfordshire CCG and Bedford Hospital Trust | Bedford Central and North Integrated Health and Care Hub. Integrated health and social care hub, Gilbert Hitchcock House, to enable delivery of Primary Care Home Model including primary care services at scale, community health and social care services and specialist services. | FBC submit to NHSE Sep 2023 | Dependent on timing of FBC approval
Wave 3 | Norfolk and Waveney | 0.6 | 0.6 | Norfolk and Suffolk FT | Mental Health Crisis Café. To provide a facility to support people in escalating mental health conditions. | Completed | Completed
Wave 3 | North Central London | 0.3 | 0 | Barnet, Enfield and Haringey Mental Health NHS Trust | CAMHS. 3 new Tier 4 beds. | Following further discussions with commissioners only two additional tier 4 CAMHS beds were commissioned from the trust. This did not require the level of capital investment previously bid for and the trust therefore notified NHSI that we would not require the £300,000 originally awarded. | Day service went live in March 2023
Wave 3 | North West London | 2.1 | 2.1 | Central & North West London FT | CAMHS Tier 4. 5 additional beds at Kingswood Hospital for people with learning difficulties/autistic spectrum disorders | Completed and in use | Completed and in use
Wave 3 | North West London | 2.1 | 2.1 | Central & North West London FT | CAMHS Tier 4. Tier 4 12 additional beds in South Kensington. | Completed and in use | Completed and in use
Wave 3 | Shropshire and Telford and Wrekin | 312 | 4.5 | Shrewsbury and Telford Hospital NHS Trust | Sustainable Services Project. Transforming services across two sites at Princess Royal Hospital Telford and Royal Shrewsbury Hospital, with new emergency care and planned care builds. | FBC due to be submitted in autumn 2023
Wave 3 | Somerset | 79.4 | 36.6 | Taunton and Somerset FT | Replacement of Theatres and Critical Care facilities. Replacement of outdated clinical facilities that are no longer fit for the purpose of providing complex high acuity care for patients | Building in progress | 2025-01-01
Wave 3 | South West London | 9.8 | 0 | Croydon CCG | Croydon Primary & Community Care Transformation. Transformation of services through One Croydon Alliance Out of Hospital Transformation Programme, integrating community networks, ensuring that vulnerable and at-risk patients are better supported out of hospital. | Construction not started | TBC – Awaiting national/ministerial decision regarding Croydon's request to extend completion deadline in order to undertake a new procurement exercise.
Wave 3 | South West London | 2.1 | 2.1 | Croydon Health Services NHS Trust | Consolidation of three procurement functions. Consolidation into a single shared service, providing an overall improvement in the delivery of clinical care and inventory management. | Completed | Completed
Wave 3 | South West London | 2.7 | 0 | South London & Maudsley FT | CAMHS Tier 4. 8 additional beds for people with learning difficulties/autistic spectrum disorders. | Scheme did not proceed | n/a
Wave 3 | South West London | 11.1 | 0 | South West London and St George's Mental Health NHS Trust | Barnes Medical Centre development. The new healthcare facility will provide mental health outpatient services, alongside an extended range of general practice services, a range of other community services, and a wide | Ready to proceed and business case submitted to national teams, awaiting national/ministerial approval and final planning consent | March 2024 subject to approval
Wave 3 | Suffolk and North East Essex | 69.3 | 32.7 | Colchester Hospital University FT / Ipswich Hospital NHS Trust | Colchester Hospital and Ipswich Hospital Partnership reconfiguration. New facilities to support clinical strategies post-merger including urgent emergency care hyper, interventional radiology facilities, CT and MRI provision, new dedicated elective care facilities, and expansion of majors and resuscitation capacity. | In progress | ED/UTC - March 2024 EOC April 2024
Wave 3 | Suffolk and North East Essex | 3.4 | 0 | North East Essex CCG | Harwich and Colchester Primary Care practices. To support practices in inappropriate premises ensuring areas with high demographic growth have the required estates resources to enable new services models and clinical pathways and support new organisational forms in primary care. | Funding re-aligned to Clacton project | N/A
Wave 3 | Suffolk and North East Essex | 14.7 | 0 | North East Essex CCG | Clacton Hospital redevelopment. First phases of the redevelopment of Clacton Hospital Services through the development of Outpatient, Minor Injury, Diagnostic and Primary Care Centre on the site. | Business case process | Currently under review
Wave 3 | Surrey Heartlands | 0.5 | 0.5 | Surrey and Borders Partnership FT | Refurbishment of place of safety for mental health crisis, in Guildford and Chertsey. | Complete | Completed in March 2022
Wave 3 | Sussex and East Surrey | 19.3 | 0 | Surrey & Sussex Healthcare NHS Trust | Sussex and East Surrey pathology hub and laboratory information management system. Centralisation of pathology services between 3 acute trusts as second stage of implementation of pathology network consolidation plan. | No longer happening | None
Wave 3 | The Black Country | 3.3 | 3.3 | The Royal Wolverhampton NHS Trust | Royal Wolverhampton stroke service. To improve and expand the stroke services for NHS Midlands and East STP. | Completed | Completed
Wave 3 | The Black Country | 9 | 9 | The Royal Wolverhampton NHS Trust | Black Country Pathology. To consolidate Pathology services across the Black Country into a single Black Country Pathology Service | Completed | Completed
Wave 3 | West Yorkshire | 1.5 | 0 | Airedale FT | West Yorkshire Telemedicine in Care Homes. The commissioning of the care home telemedicine service across the STP and upgrading infrastructure to enhance services. | Project withdrawn | None
Wave 3 | West Yorkshire | 2 | 2 | Calderdale and Huddersfield Foundation Trust, | West Yorkshire National Pathology Exchange. To deliver a lab-to-lab messaging solution that connects Laboratory Information Management Systems (LIMS) together to facilitate the electronic transfer of pathology test requests and results. | Complete | Completed
Wave 3 | West Yorkshire | 15 | 3 | Mid Yorkshire Hospitals NHS Trust | Adoption of GS1 Standards - using Location coding / Catalogue Management / Patient Identity to support Inventory Management / Purchase-to-Pay / Product recall, to improve patient safety. | Near completion | 2023-03-30
Wave 3 | West Yorkshire | 6.1 | 4.7 | Mid Yorkshire Hospitals NHS Trust | Yorkshire Imaging Collaborative. Collaborative procurement of enterprise imaging solutions to transform radiology services to meet some of the capacity and demand issues | 95% complete | 2025-03-31
Wave 4 | Bath, Swindon and Wiltshire | 29.6 | 7.4 | Great Western Hospital FT | Integrated Front Door & Transitional Care Facility. (This scheme is now known as 'integrated front door' | Construction | Anticipated summer 2024
Wave 4 | Bath, Swindon and Wiltshire | 16 | 0.426 | Formerly Wiltshire CCG, now BSW ICB | Trowbridge Integrated Care Centre | Full Business Case awaiting decision | Depending on Full Business Case approval
Wave 4 | Bristol, North Somerset, South Gloucestershire | 3.2 | 0.231 | Bristol, North Somerset and South Gloucestershire CCG | North Somerset Primary Care, Central Weston | FBC due to be issued to NHSEI in April 2023 (as of March) | End of March 2024, STP spend deadline
Wave 4 | Bristol, North Somerset, South Gloucestershire | 1.6 | 1.6 | North Bristol NHS Trust | 12 Additional Beds through Conversion of Assisted Bathrooms | No information supplied | No information supplied
Wave 4 | Buckinghamshire, Oxfordshire and Berkshire West | 2.8 | 0 | Berkshire Healthcare FT | Relocation of Willow House to Prospect Park Hospital Site | The project did not proceed | None
Wave 4 | Buckinghamshire, Oxfordshire and Berkshire West | 8.6 | Information not supplied | Oxford Health FT | 10 Bed Learning Disabilities Low Secure Unit | No information supplied | No information supplied
Wave 4 | Buckinghamshire, Oxfordshire and Berkshire West | 1.8 | 1.8 | Oxford University Hospitals FT | Delivery Suite Theatre, John Radcliffe Hospital | Completed | Opened in 2020
Wave 4 | Cambridgeshire and Peterborough | 100 | 10.764 | Cambridge University Hospitals FT | Cambridge Children’s Hospital | £100m confirmed recently. OBC decision expected in autumn 2023. | 2028
Wave 4 | Cambridgeshire and Peterborough | 19.2 | 19.2 | Cambridge University Hospitals FT | Capacity solution to enable urgent fire safety works | Allocation for development of additional capacity. Construction underway. | Late 2023
Wave 4 | Cambridgeshire and Peterborough | 25.5 | 14.7 | North West Anglia FT | Expansion at Hinchingbrooke Hospital | Construction | 2023-12-01
Wave 4 | Cheshire and Merseyside | 7 | 7 | Alder Hey Children's FT | CAMHS Tier 4 inpatient beds – Dewi Jones Unit | Completed | Completed in June 2022
Wave 4 | Cheshire and Merseyside | 4 | 4 | St Helens CCG / St Helens and Knowsley Teaching Hospitals NHS Trust | Improving Emergency Department capacity and flow | Completed | Completed in March 2022
Wave 4 | Cornwall and the Isles of Scilly | 31.3 | 31.3 | Royal Cornwall Hospitals NHS Trust | Oncology & MRI Re- provision | RIBA Stage 4 Construction | 31st May 2023
Wave 4 | Cornwall and the Isles of Scilly | 9.1 | 0 | Royal Cornwall Hospitals NHS Trust | Peripheral Site Optimisation | Awaiting FBC submission approval from DHSC | Unable to confirm
Wave 4 | Cumbria and North East | 54.2 | 54.2 | Cumbria, Northumberland, Tyne & Wear FT | Secure Services / Newcastle and Gateshead Adult Acute Inpatients | Finishing construction. Room inspections in progress | Construction completion is 16/06/2023. Planned operational date of w/c 31/07/2023
Wave 4 | Derbyshire | 21.8 | 0 | University Hospitals Derby and Burton Foundation Trust | To create an intergrated care village at Queen Hospital Burton Outwoods site | Groundworks construction stage | 2024-03-01
Wave 4 | Derbyshire | 8.6 | 0 | Derbyshire Community Health Services FT | Bakewell Integrated Community Hub | No information supplied | No information supplied
Wave 4 | Devon | 8 | 8 | Devon Partnership NHS Trust | Reducing Out of Area Placements for Adult Acute Mental Health Service Across Devon | Completed | Completed in February 2023
Wave 4 | Devon | 9.3 | 9.3 | University Hospitals Plymouth NHS Trust | Devon Imaging Facilities (New CT scanner at North Devon District Hospital and two new MRI scanners at Derriford Hospital, Plymouth) | Complete and in use | Complete
Wave 4 | Devon | 3.5 | 4 | University Hospitals Plymouth NHS Trust | Digital Histopathology Devon & Cornwall | Money received and allocated across all four acute trusts in regions | 2024-03-01
Wave 4 | Devon | 29.7 | 0 | University Hospitals Plymouth NHS Trust | Transforming Urgent and Emergency Care | Project absorbed into wider and separately funded Future Hospital Scheme. Currently at detailed design stage | N/A
Wave 4 | Dorset | 5.9 | 0 | Dorset HealthCare University FT | Mental Health Estate Development | Project was no longer taken forward
Wave 4 | Dorset | 4.2 | 0.12 | Dorset HealthCare University FT | Blandford Primary and Community Hub | RIBA Stage 3 | The majority of the spend will be in the 23/24 capital year. Any further funding requirment will be subject to negotiation.
Wave 4 | Dorset | 5.1 | 5.1 | The Royal Bournemouth & Christchurch Hospitals NHS Trust | Pan-Dorset Pathology Laboratory information management system | Complete | Patient Ready
Wave 4 | Frimley Health | 1 | 0 | North East Hampshire & Farnham CCG | Alexander House extension | Project did not go ahead | n/a
Wave 4 | Greater Manchester | 4.8 | 4.8 | Pennine Care FT | Proposal for the Development and Provision of Psychiatric Intensive Care Services | Completed | 2022-10-01
Wave 4 | Hampshire and the Isle of Wight | 10.2 | 4 | Hampshire Hospitals FT | Elective Expansion and Reconfiguration of Royal Hampshire County Hospital Winchester | Business Case | 2024-08-01
Wave 4 | Hampshire and the Isle of Wight | 2.4 | 0 | North Hampshire CCG | Same Day Access Service - Basingstoke | Business Case | tbc
Wave 4 | Hampshire and the Isle of Wight | 2.6 | 0 | Portsmouth City CCG | Relocation of North Harbour Medical Group GP Practice | Business Case | tbc
Wave 4 | Hampshire and the Isle of Wight | 58.3 | 9.55 | Portsmouth Hospitals NHS Trust | Emergency Floor Programme Portsmouth | In Construction | 2024-11-01
Wave 4 | Hampshire and the Isle of Wight | 15.8 | 5.79 | Solent NHS Trust | Community bed capacity optimisation, Southampton | In Construction | 2024-05-01
Wave 4 | Herefordshire and Worcestershire | 3 | 0 | Hereford Medical Group | Hereford Primary Care Hub | Complete - but alternative source of funds used (EFFT Capital) | Complete
Wave 4 | Herefordshire and Worcestershire | 4 | 4 | Worcestershire Acute Hospitals NHS Trust | Breast Imaging Improvement Plan | Delivered March 2022 | 2022-03-01
Wave 4 | Hertfordshire and West Essex | 7.2 | 1.176 | East and North Hertfordshire NHS Trust | Hertfordshire and West Essex Vascular Surgery Network | Approval outstanding | 2024-07-01
Wave 4 | Hertfordshire and West Essex | 4.2 | 4.2 | East and North Hertfordshire NHS Trust | Luton & Dunstable Renal Dialysis Unit Relocation | Completed | Opened in 2021
Wave 4 | Hertfordshire and West Essex | 9.5 | 9.5 | The Princess Alexandra Hospital NHS Trust | Additional Bed Capacity at Princess Alexandra Hospital | All completed (Adult Assessment Unit, Same Day Emergency Care Unit and Older Person’s Assessment and Liaison Unit) | All opened in 2021
Wave 4 | Hertfordshire and West Essex | 11 | 2.5 | West Hertfordshire Hospitals NHS Trust | Emergency Care Transformation | No information supplied | No information supplied
Wave 4 | Humber, Coast and Vale | 88.5 | 88.5 | Humber, Coast and Vale Health and Care Partnership | Diagnostic equipment and transformation of urgent & emergency care | Partially delivered and rest in progress | The new facilities at Hull Royal Infirmary opened in December 2022. Following commissioning services at all 3 sites will go live in early 2024.
Wave 4 | Kent & Medway | 6.5 | 6.5 | South East Coast Ambulance Service FT | Medway Make Ready Centre | In progress | Summer 2023
Wave 4 | Lancashire and South Cumbria | 12.9 | 12.9 | Blackpool Teaching Hospitals FT | Fylde Coast Emergency Department / Critical Care Scheme | The Critical Care element of the scheme is complete. Phase 2A of the Emergency Department development completes on the 6th April. Phase 2B and 2C commences on the 12th April. Phase 3 commences on 12th July, Phase 4 commences on 9th October 2023. | Practical completion is scheduled for Dec 2023
Wave 4 | Lancashire and South Cumbria | 8.1 | 8.1 | Lancashire Care FT | Fylde Coast Integrated Acute Mental Health Hub | Opened in March 2022 | n/a
Wave 4 | Leicester, Leicestershire and Rutland | 7 | 0 | West Leicestershire CCG | Hinckley and Bosworth Community Health Services | Business case | The anticipated delivery date of the project is March 2025.
Wave 4 | Lincolnshire | 1.5 | 1.5 | United Lincolnshire Hospitals NHS Trust | Multi-Purpose Education Centre to support University Medical School of Excellence (Lincoln) | Completed | Completed
Wave 4 | Milton Keynes, Bedfordshire and Luton | 10 | 10 | Milton Keynes University Hospital FT | Pathway Unit, now called Maple Centre | Completed and in use | Opened in 2022
Wave 4 | Milton Keynes, Bedfordshire and Luton | 0.8 | Information not supplied | NHS Bedfordshire CCG | Stroke Rehabilitation Unit | No information supplied | No information supplied
Wave 4 | North Central London | 86 | 80 | Camden and Islington FT | St Pancras - transformation of mental health and substance misuse services | New hospital at Highgate East is on schedule | Nearing completion by Q3
Wave 4 | North Central London | 110.2 | 37.7 | Moorfields Eye Hospital FT | Project Oriel - a new eye care, research and education facility | FBC approval received and enabling works underway | 2027
Wave 4 | North West London | 0.5 | 0.5 | Central & North West London FT | Northwick Park Mental Health Wards - Single Bedrooms Reconfiguration | Completed and in use | n/a
Wave 4 | North West London | 0.5 | 0.5 | Central & North West London FT | Oak Tree Ward - Woodlands Mental Health Wards Reconfiguration, Hillingdon | Completed and in use | n/a
Wave 4 | North West London | 2.4 | 2.4 | Central & North West London FT | Pond Ward - Park Royal Mental Health Wards Reconfiguration | Completed and in use | n/a
Wave 4 | North West London | 1.9 | 1.9 | Imperial College NHS Trust | The Development of an Endovascular Hybrid Theatre | Completed and in use | n/a
Wave 4 | North West London | 27 | 2.03 | London North West University Healthcare NHS Trust | Re-provision of eight compliant theatres | Trust received only £2.03m in 2020/21. This was allocated for the new pharmacy aseptic unit. Contract for construction let. | To be built 2023/2024
Wave 4 | Nottinghamshire | 10.7 | 4.3 | Nottingham University Hospitals NHS Trust | Emergency Pathway Improvement | £10.7m of potential schemes were included in the draft plan for 2019/20 subject to approval, only £4.3m was approved to proceed which related to Critical care expansion on Ward C6. | Completed November 2020
Wave 4 | Somerset | 11.5 | 11.5 | Taunton and Somerset FT | Acute Assessment Hub | Complete | Open
Wave 4 | South East London | 5 | 2.5 | Bromley CCG, Lambeth CCG and Lewisham CCG | South East London Estate Optimisation | Two of the four elements complete. One at business case stage approval (NHSE) and one element withdrawn. | Outstanding project to be delivered by end of 2023
Wave 4 | South East London | 3.6 | 3.6 | Greenwich CCG | New Kidbrooke sub Hub | Completed
Wave 4 | South East London | 10.5 | 10.5 | Guy’s & St Thomas’ FT | Patient Centric Supply Chain | Final stages/completion | 2023-08-01
Wave 4 | South East London | 1.3 | 0 | Lambeth CCG | Consolidation of Streatham Common Group Practice at Baldry Gardens Health Centre | At Business Case Stage Approval - NHSE | To be delivered by the end of this calendar year
Wave 4 | South East London | 9.4 | 0 | NHS Bromley CCG | Bromley Health & Wellbeing Centre | At Design Stage | To be determined
Wave 4 | South West London | 3.4 | 3.4 | Kingston FT | Patient Flow Transformation Programme | Completed | Completed
Wave 4 | Staffordshire | 1.6 | 0 | North Staffordshire Combined Healthcare | Urgent Care Centre, Detoxification suites and crisis cafes | Project did not go ahead | None
Wave 4 | Suffolk and North East Essex | 18 | 0 | East of England Ambulance Service NHS Trust | Infrastructure & Capacity Transformation: Fleet, Estates & Make Ready Service | Project not taken forward | None
Wave 4 | Suffolk and North East Essex | 13.4 | 0 | West Suffolk FT | Emergency Department Strategic Redevelopment | Project not taken forward | None
Wave 4 | Surrey Heartlands | 7.4 | 0 | Epsom and St Helier University Hospitals NHS Trust | Transfer of New Epsom and Ewell Cottage Hospital to Epsom General Hospital | Remains part of plans | No project completion date yet
Wave 4 | Surrey Heartlands | 4 | 0 | Surrey & Borders Partnership FT | Community Hub Programme | Horizon, Epsom (complete) 18 Mole Business Park, Leatherhead (in progress) | Horizon, Epsom (completed summer 2021). Mole Business Park, Leatherhead (summer 2023)
Wave 4 | Sussex and East Surrey | 5.5 | 5.5 | South East Coast Ambulance Service FT | Brighton Make Ready Centre | Completed and operational
Wave 4 | Sussex and East Surrey | 6.7 | 6.7 | South East Coast Ambulance Service FT | Expansion of additional floor space at the Trust Headquarters building
Wave 4 | Sussex and East Surrey | 0.2 | 0.2 | South East Coast Ambulance Service FT | Worthing Make Ready Centre | Completed | Completed
Wave 4 | The Black Country | 7.5 | 0 | Black Country Partnership FT | Black Country Transforming Care Partnership LD ServiceTransformation | FBC | 2025-03-01
Wave 4 | The Black Country | 15.4 | 15.4 | Sandwell and West Birmingham Hospitals NHS Trust | Sandwell and West Birmingham Hospitals Interim Reconfiguration | Completed | Completed
Wave 4 | The Black Country | 17 | 0 | The Dudley Group FT | Redevelopment of Emergency Department at Russell's Hall Hospital | OBC | 2025-03-01
Wave 4 | The Black Country | 36.2 | 36.2 | Walsall Healthcare NHS Trust | Emergency Department Development | Completed | Completed
Wave 4 | West Yorkshire | 21.9 | 12.8 | Calderdale & Huddersfield FT | Reconfiguration of hospital services | HRI A&E development in construction. OBC for CRH redevelopment in approval stage. | Summer 2023 for A&E development. 2027 for CRH development.
Wave 4 | West Yorkshire | 11.2 | 0 | Leeds and York Partnership FT (West Yorkshire Mental Health Trusts) | Rehabilitation and Recovery Repatriation | Business Case not currently progressing | To be confirmed
Wave 4 | West Yorkshire | 25.8 | 21 | Leeds Teaching Hospitals NHS Trust | Consolidation of Pathology Services | In Construction | Summer/Autumn 2023
|  | Overall allocated (£m) | Overall received (£m) | % received
| All | 2672.3 | 1203.9056 | 45.05%
| Schemes with information on funding | % total
| 139 | 97.2%
How many schemes in total
143
| Number of live schemes who have received £0 | % receive £0
| 30 | 20.98%
| Number of schemes confirmed as scrapped | % total
| 10 | 6.993%
| Number of completed schemes | % total
| 56 | 39.16%
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: At least £55m Cancer centre complete (£35m) and West Cumberland Hospital is partially complete (around £20m of allocated £33m spent)
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total approved scheme value
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Up to Feb 2023
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimate - no official information supplied
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Only requested £39m
Note on H21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.chesterfieldroyal.nhs.uk/news/urgent-and-emergency-care-department
Note on G22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: March 2023 response: Outline Business Case submitted to NHSE. However there is a national pause on the programme
Note on D41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 344 expected spend in March
Note on G44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NHS Kent and Medway has been working with Kent County Council and partners to explore options for the Romney Marsh Hub project, but finding a workable solution within the limited amount of capital available is proving to be a challenge. We continue to work with partners on finding a solution on this.
Note on D46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The Outline Business Case (OBC) is currently being reviewed by the DHSC and an outcome is awaited which will include details of associated financials.
Note on B47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Have chased ICB - didn’t give £
Note on B50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Went to North West (was originally) - told to go to North Central or trust
Note on D50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Day Service scheme now live: 'This did not require capital funding as it is operating within the existing Inpatient Unit'
Note on G50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From previous HSJ story: https://www.hsj.co.uk/finance-and-efficiency/exclusive-capital-billions-promised-by-ministers-fail-to-reach-front-line/7025647.article
Note on D53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Up to March 2023
Note on G53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.hsj.co.uk/shrewsbury-and-telford-hospital-nhs-trust/300m-reconfiguration-gets-go-ahead-after-decade-delay/7033072.article
Note on G55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (though designs for proposals have been developed) due to challenging conditions experienced during the Covid pandemic as well as within the building and property development market, following the decision in July 2021 by the London Borough of Croydon to close its development company (Brick by Brick, our original development partner). The preferred development partner has recently withdrawn from the project.
Note on G63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: When the Trust was part of Frontier Pathology (with Sussex Trusts) we were going to centralise services on the Haywards Heath (Princess Royal) Hospital site. We were allocated £19.3m to do so. When it was known that we would leave Frontier to join Berkshire and Surrey Pathology Services (likely in 2020) this scheme was removed from the STP list as the build wasn’t necessary.
Note on B71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Info as of 2 March
Note on D72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For design costs
Note on G72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From March 2023 FOI response
Note on H72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From March 2023 FOI response
Note on D73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PDC drawn down 2020/2021
Note on D74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: "Funding was never released for this project"
Note on D76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PDC drawn down in 2019/2020
Note on H76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.ouh.nhs.uk/news/article.aspx?id=1339
Note on D78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The £19.2m capital funding was originally given to us to create decant ward facilities to enable us to progress ward refurbishment works that would in turn ensure compliance with fire regulations. With the advent of Covid, the £19.2m funding was put towards creating an additional 120 beds as part of the Surge Centre, some of which are already open, with the remainder opening later this year. We have made good progress with the fire compliance works in the meantime (A block), but the completion of the Surge Centre will enable us to do more. We are therefore delivering against the original brief for the £19.2m.
Note on G78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: £19m originally for decant ward for refurb to ensure fire regulation compliance. With Covid, it was put towards creating extra 120 beds (some already open) as part of surge centre. Trust says progress made with fire compliance works in meantime, but surge centre allows to do more. Says therefore delivering against original brief.
Note on G85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FOI response in April initially said NHSE had placed 'on pause'
Note on E91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nothing to add to spreadsheet
Note on D105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All drawn down in 2020/21
Note on D130: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zero funding was received, decision made project not viable. However the funding may of gone to a separate MH Trust within the Staffordshire footprint.
Note on G130: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The decision was made that the projects were not viable.